## moodel_questions
Manage Team
A) Interpersonal and team skills
B) Communication methods
C) Project funding requirements
D) Organizational process assets
ANSWER: A
Manage Communications
A) Project reporting
B) Decomposition
C) Project management plan
D) Agreements
ANSWER: A
One of the outputs of Plan Procurement Management is
A) Procurement management plan
B) Work performance data
C) Source selection analysis
D) Inspection
ANSWER: A
Plan Procurement Management:
A) Procurement management plan
B) Work performance data
C) Source selection analysis
D) Inspection
ANSWER: A
A 10 km long rail track is estimated to cost $5000 based on verified historical data. Based on this information, it is estimated that 1500 km of rail track would cost $750000. Which estimation technique has been applied here?
A) Analogous estimating
B) Parametric estimating
C) 3-point estimating (PERT technique)
D) Bottom-up estimating
ANSWER: B
A key difference between operations and project is:
A) Operations are temporary
B) Projects yield unique outputs
C) Operations are continuation of projects
D) Projects happen during operations
ANSWER: B
A leader with expert power will:
A) Demonstrate superior skills in one or more subject areas
B) Demonstrate formal authority
C) Be respected or admired by others
D) Be an expert in relationships
ANSWER: A
A project has a BAC (budget at completion) of $10000. The cost incurred so far is $4000. The value of the work completed is $3000. What is the ETC (estimate to complete) of this project assuming the same CPI rate until the end of the project?
A) $6000
B) $7000
C) $9333
D) We do not have sufficient information to calculate it
ANSWER: D
A project has a CPI of 0.7 and an SPI of 1.2. What does this tell us about the project?
A) It is ahead of schedule and over budget
B) It is ahead of schedule and under budget
C) it is behind schedule and over budget
D) it is behind schedule and under budget
ANSWER: A
A project has a risk of losing $16000 with a 50% chance and an opportunity to save $10000 with a 25% chance. What is the EMV (expected monetary value) of risks for this project?
A) $6000
B) -$5500
C) -$6000
D) $26000
ANSWER: B
A project has activities A,B,C,D and E with durations 3,5,7,2 and 4 days respectively. A and B are started together. When A and B both are completed, C and E are started together. When C finishes, D is performed. When B is completed, E is performed. When both D and E are done, the project is completed. What is the total float for activity E?
A) 0 days
B) 2 days
C) 5 days
D) None of the above
ANSWER: C
A stakeholder engagement assessment matrix facilitates which of the following?
A) Identification of stakeholders
B) Prioritization of stakeholders
C) Comparison of current and desired stakeholder engagement levels
D) Mapping of stakeholders as per their power and impact
ANSWER: C
Active listening, cultural awareness, managing stakeholder expectations, skills like persuasion, coaching, motivating, negotiating and resolving conflict are together known as:
A) Communication skills
B) Communication models
C) Communication methods
D) Communication technology
ANSWER: A
Activity list and activity attributes are two of the three key outputs of the Define Activities process. Which is the third one?
A) Activity resource estimates
B) Activity cost estimates
C) Milestone list
D) Activity duration estimates
ANSWER: C
Adaptive life cycle projects make use of which of the following to address the high uncertainty or risk in such projects?
A) Communication planning
B) Frequent product reviews and cross-functional teams
C) Scope planning
D) Risk planning
ANSWER: B
Advertising, bidder conferences and proposal evaluation are techniques in which process?
A) Conduct procurements
B) Control procurements
C) Plan procurement management
D) Manage stakeholder engagement
ANSWER: A
After stakeholder information is captured during stakeholder identification, in which process does the communication and working with stakeholders occur, by which their needs are met, issues are addressed and their involvement is fostered?
A) Plan stakeholder engagement
B) Manage stakeholder engagement
C) Monitor stakeholder engagement
D) Manage communications
ANSWER: B
Agile release planning determines the release plans based on the product vision and product roadmap, and the number of sprints in each release. In which process is this technique applied?
A) Plan schedule management
B) Develop schedule
C) Sequence activities
D) Develop project management plan
ANSWER: B
Among the three projects which have TCPI's (to-complete performance index) of 0.8, 1 and 1.2 do not exceed the original budget, which one is the best performing from a cost perspective?
A) The project with TCPI 1
B) The project with TCPI 0.8
C) The project with TCPI 1.2
D) Cannot be concluded with the given information
ANSWER: B
An activity is most likely expected to take 7 days. The maximum duration is expected to be 10 days and the minimum 5 days. Calculate the expected duration for this activity.
A) 7.16 days
B) 12 days
C) 15 days
D) 17 days
ANSWER: A
An important input for the Develop Project Charter process is the:
A) Project management plan
B) Project scope statement
C) Requirements documentation
D) Business case
ANSWER: D
An important output of the Manage Communications process is:
A) Work performance reports
B) Work performance information
C) Project communications
D) Work performance data
ANSWER: C
An important output of the Manage Knowledge process is the:
A) Knowledge log
B) Knowledge management plan
C) Lessons learned register
D) Knowledge register
ANSWER: C
An output of the Monitor and Control Project Work process is:
A) Work performance data
B) Work performance report
C) Work performance information
D) Project communications
ANSWER: B
Another name for cause and effect diagram is
A) Fish bone diagram
B) Ishikawa diagram
C) Why-why diagram
D) All of the above
ANSWER: D
Another name for storyboarding, mock-ups, user experimentation, small scale products and computer generated 2D/3D models is:
A) Context diagrams
B) Prototypes
C) Observation/conversation
D) Facilitation using JAD, QFD and user stories
ANSWER: B
Another name for the facilitation technique which is used in several project risk management processes is:
A) Risk workshop
B) Risk identification
C) Risk analysis
D) Risk planning
ANSWER: A
Apart from managing a project, the project manager may be also involved in:
A) Evaluation and analysis before project initiation and consulting with business leaders and executives
B) Business benefits related activities and providing assistance for business analysis
C) A and B
D) Providing project funding
ANSWER: C
Apart from Quality Management Plan, which is the other key output of the Plan Quality Management process?
A) Quality metrics
B) Quality report
C) Quality control measurements
D) Quality function deployment (QFD)
ANSWER: A
Apart from the work breakdown structure which is one of the components of the scope baseline created in the Create WBS process, which are the two other components?
A) Project scope statement and WBS dictionary
B) Cost baseline and schedule baseline
C) Work packages and planning packages
D) Requirements documentation and requirements traceability matrix
ANSWER: A
Approved change requests are an output of which process?
A) Perform integrated change control
B) Monitor and control project work
C) Direct and manage project work
D) None of the above
ANSWER: A
Artifacts, knowledge and practices from the performing organizations in the project, project information and historical information like lessons learned are known as:
A) Organizational process assets (OPA)
B) Enterprise environmental factors (EEF)
C) Governance frameworks
D) Management elements
ANSWER: A
As a project manager, which scheduling approach will you use for an agile project?
A) Pull based one-demand scheduling (Kanban)
B) Iterative scheduling using a backlog
C) Create the final detailed schedule once and then begin project execution
D) A and B
ANSWER: D
Audits (quality audits) are performed in which process?
A) Plan quality management
B) Manage quality
C) Control quality
D) None of the above
ANSWER: B
Collaboration and self-organizing teams with generalized specialists are typical in which type of projects?
A) Waterfall or predictive projects
B) Single phase projects
C) Agile projects
D) Multi-phase projects
ANSWER: C
Collection, creation, distribution, storage, management, retrieval and monitoring of project information is done in which process?
A) Plan communications management
B) Manage communications
C) Control communications
D) None of the above
ANSWER: B
Communication has aspects like internal or external, formal or informal, official or unofficial, written or oral, etc. These are known as:
A) Communication skills
B) Dimensions of communications
C) Methods of communication
D) Models of communication
ANSWER: B
Communications competence, feedback, non-verbal communication and presentations are known as:
A) Communication skills
B) Communication methods
C) Communication models
D) None of the above
ANSWER: A
Conditions not under the control of the project team that influence, constrain or direct the project are known as:
A) Organizational project management
B) Organizational process assets (OPA)
C) Enterprise environmental factors (EEF)
D) Organizational systems
ANSWER: C
Contract performance reviews, inspections of seller deliverables, procurement audits and contract closure are techniques and activities of which process?
A) Control procurements
B) Conduct procurements
C) Plan procurement management
D) Close project or phase
ANSWER: A
Deliverables and issue log are created in which process?
A) Create WBS
B) Control quality
C) Validate scope
D) Direct and manage project work
ANSWER: D
During the project, stakeholder relationships have to be watched and strategies to engage them have to be tailored. In which process is this carried out?
A) Monitor stakeholder engagement
B) Plan stakeholder engagement
C) Manage stakeholder engagement
D) Control procurements
ANSWER: A
Ensuring availability of physical resources as planned, monitoring their utilization and taking corrective actions when required are performed in which process?
A) Control resources
B) Manage team
C) Develop team
D) Acquire resources
ANSWER: A
Ensuring meeting logistics like preparing and distributing the meeting agenda, inviting participants, managing meeting timings and recording actions are known as:
A) Facilitation
B) Focus groups
C) Meetings
D) Meeting management
ANSWER: D
Ensuring that the information needs of the project and its stakeholders are met is the purpose of which process?
A) Plan communications management
B) Manage communications
C) Monitor communications
D) Monitor and control project work
ANSWER: C
Failure to meet quality requirements of a project can lead to which of the following?
A) Decreased profits
B) Undetected errors in the product
C) Higher project risk
D) All of the above
ANSWER: D
Fast tracking is used for what purpose in project schedule management and in what way?
A) To compress the project schedule by adding resources
B) To progress the project quickly
C) To compress the project schedule by overlapping activities
D) To meet customer needs related to the project schedule
ANSWER: C
Funding limit reconciliation is a technique in which process?
A) Plan cost management
B) Determine budget
C) Estimate costs
D) Control costs
ANSWER: B
Governance is the framework within which authority is exercised in organizations. It includes rules, policies, processes, procedures, norms, relationships and systems. What does this governance framework influence?
A) How objectives of the organization are set and achieved
B) How risk is monitored and assessed
C) How performance is optimized
D) All of the above
ANSWER: D
How many phases can exist in a project life cycle, irrespective of whether an adaptive or predictive life cycle is used?
A) Only one
B) More than one
C) One or more
D) Minimum two
ANSWER: C
How many times is the Validate Scope process triggered in an agile project?
A) Once towards the end of the project
B) Repeated in each iteration
C) Whenever required
D) This process is not applicable in an agile project
ANSWER: B
Identify the techniques used in the Acquire Resources process from the below:
A) Multi-criteria decision analysis, negotiation
B) Pre-assignment, virtual team
C) A and B
D) Physical resource assignments, project team assignments
ANSWER: C
Identify the two techniques which are unique to the Manage Knowledge process?
A) Knowledge management and information management
B) Meetings and expert judgment
C) Root cause analysis and mind maps
D) Active listening and leadership
ANSWER: A
Identifying quality requirements and documenting how the project will meet quality standards are done in which of the below processes?
A) Control quality
B) Plan quality management
C) Manage quality
D) Assure quality
ANSWER: B
Improving team competencies, interaction and overall team environment in order to enhance project performance are objectives of which process?
A) Plan resource management
B) Control resources
C) Manage team
D) Develop team
ANSWER: D
In an agile project lifecycle, which type of chart is used to track work pending completion in an iteration?
A) Iteration burn up chart
B) Iteration burn down chart
C) Gantt chart
D) Milestone chart
ANSWER: B
In general, who focuses on systems and structure and who on relationships with people?
A) Leader and manager respectively
B) Manager and leader respectively
C) Both leader and manager
D) Depends on the situation
ANSWER: B
In the Manage Communications process, project information is collected and distributed as per the format and level of detail desired by stakeholders. What is the name of this technique?
A) PMIS (project management information system)
B) Project reporting
C) Project communications
D) None of the above
ANSWER: B
In which of the following organizational structure types is the project manager's role full time?
A) Balanced matrix
B) Multi-divisional
C) Project-oriented
D) Functional
ANSWER: C
In which of the following organizational structure types is the project manager's authority weakest?
A) Weak matrix
B) Functional
C) Virtual
D) Balanced matrix
ANSWER: B
In which process are risks prioritized for further analysis or action by assessing their probability, impact and other characteristics?
A) Perform qualitative risk analysis
B) Perform quantitative risk analysis
C) Plan risk responses
D) Implement risk responses
ANSWER: A
In which process group a new project or phase is defined and authorization is given to start it?
A) Planning
B) Initiating
C) Executing
D) Monitoring and controlling
ANSWER: B
In which process is a contract negotiated and signed between the buyer and one or more sellers?
A) Conduct procurements
B) Plan procurement management
C) Control procurements
D) Direct and manage project work
ANSWER: A
In which process is the quality report created for the first time as an output, though it may be updated in this or other processes?
A) Plan quality management
B) Manage quality
C) Control quality
D) Monitor and control project work
ANSWER: B
In which process is the stakeholder register created?
A) Direct and manage project work
B) Identify risks
C) Identify stakeholders
D) Develop project charter
ANSWER: C
In which technique of stakeholder engagement planning are the results of stakeholder analysis (from stakeholder identification) compared with information from other organizations or world class projects?
A) Quality checklist
B) Document analysis
C) Meetings
D) Benchmarking
ANSWER: D
In which type of project life cycle are prototypes and release versions purposefully built to refine requirements? (In such products, the requirements are called backlog)
A) Predictive life cycle
B) Overlapping phases
C) Sequential phases
D) Adaptive or agile lifecycle
ANSWER: D
In which type of projects are communications usually frequent, faster and transparent?
A) Waterfall projects
B) Iterative and incremental
C) Agile projects
D) None of the above
ANSWER: C
Initiating individual and team assessments (a technique) and documenting team performance assessments (an output) are carried out in which process?
A) Manage team
B) Control resources
C) Develop team
D) Acquire resources
ANSWER: C
Just-in-time (JIT) manufacturing, Kaizen, total productive maintenance (TPM) , lean management are trends and practices in which knowledge area of project management?
A) Resource management
B) Schedule management
C) Scope management
D) Cost management
ANSWER: A
Leaders and managers focus on doing things. Identify the correct statement(s) from the below.
A) Leaders do the right things
B) Managers do things right
C) Managers do the right things
D) A and B
ANSWER: D
Of the various types of PMOs (project management office), which type mainly checks for compliance, while providing support to projects as and when required?
A) Supportive PMO
B) Controlling PMO
C) Directing PMO
D) None of the above
ANSWER: B
One of the two key outputs of the Identify Risks process is the risk register. Which is the other one?
A) Risk management plan
B) Risk report
C) Risk breakdown structure
D) Probability and impact matrix
ANSWER: B
Origin or source of requirements and test scenarios are documented in the:
A) Requirements documentation
B) Requirements management plan
C) Work packages
D) Requirements traceability matrix
ANSWER: D
Prioritization and allocation of resources in an organization is an objective of:
A) Portfolio management
B) Program management
C) Project management
D) None of the above
ANSWER: A
Procurement documents, procurement strategy, bid documents, procurement SOW, source selection criteria, make-or-buy decisions and independent cost estimates are outputs of which process?
A) Estimate costs
B) Control procurements
C) Conduct procurements
D) Plan procurement management.
ANSWER: D
Project calendar and schedule baseline are outputs of which process?
A) Estimate activity durations
B) Plan schedule management
C) Develop Schedule
D) Create WBS
ANSWER: C
Project funding requirements are an output of which process?
A) Plan cost management
B) Determine budget
C) Estimate costs
D) Control costs
ANSWER: B
Project integration management is the responsibility of the:
A) Customer
B) Project manager
C) Project sponsor
D) Project team
ANSWER: B
Project Scope Statement is an output of which process?
A) Plan scope management
B) Define scope
C) Create WBS
D) Validate scope
ANSWER: B
You are working in the Project Management Office (PMO) of your organization. Your job responsibility is to:
A) Manage the operational activities in the company
B) Manage human resource and risk management issues for individual projects
C) Provide support functions to project managers in the form of training, providing software, standardizing policies, etc
D) Provide subject matter expertise in the functional areas of the project
ANSWER: C
You are working in the Project Management Office (PMO) of your organization. Your job responsibility is to:
A) Manage the operational activities in the company
B) Manage human resource and risk management issues for individual projects
C) Provide support functions to project managers in the form of training, providing software, standardizing policies, etc
D) Provide subject matter expertise in the functional areas of the project
ANSWER: C
The customer was not satisfied with the finished product`s quality. The cost of poor quality can also be referred to as:
A) Cost of conformance
B) Failure cost
C) Rework cost
D) Opportunity cost
ANSWER: B
You are a project manager in a pharmaceutical company and manage a team of 50 resources in a virtual project team across multiple time zones. There were concerns that team members would not be able to work well in this virtual team structure. However, you are mid-way into the project and team members have successfully figured out efficient ways to work together effectively. The team is in which stage of group development?
A) Performing
B) Forming
C) Smoothing
D) Norming
ANSWER: A
As part of the risk management process, you have just created an overall risk ranking of the project and a list of prioritized identified risks which need additional analysis and determined trends in risk analysis results. What should you do next?
A) Analyze the effect of identified risks on overall project objectives
B) Create a list of identified risks
C) Maintain a risk register
D) Make a list of potential responses to the risks
ANSWER: D
You are considering whether to buy or make a software product. If you want to buy, the cost is $80,000, and the cost of procuring and integrating the product in your company is $1,000. If you want to build it yourself, the product will require seven engineers working for three months. The salary of each software engineer is $4,000 per month. The other related miscellaneous costs allocated to the project are $2,000. Which option will you choose?
A) Buy ┬ب
B) Build
C) Neither build nor buy
D) Need more information on suppliers to make a decision
ANSWER: A
During the Identify Stakeholders process, which document may provide some initial idea of who the stakeholders are for a project?
A) Communications management plan
B) Project charter
C) Human resource contracts
D) Responsibility assignment matrix
ANSWER: B
You are the project manager working on a project to develop a new 4-color erasable pen. The customer, PMstudy.com, is very excited to offer this innovative pen to participants in their PMP prep boot camp class, as it will allow them to erase mistakes made when creating their detailed process chart. PMstudy also wants to use the pen to help promote their other brands like MyITstudy.com and SCRUMstudy.com, so they have asked for their affiliate logos to appear on the pen.They also want the product development to be rushed as they are running low on current inventory and want their next order to consist of the new pen. Since the product is a new concept and the customer is an important one, you decide to create a prototype of the pen during the design phase.After reviewing the prototype, PMstudyظآs CEO advises that he is not happy with the design and the size of the logos. The Quality and Marketing Directors and other PMstudy stakeholders are happy with the prototype and feel that all their requirements were met. What could be the most likely cause of this situation?
A) The CEO changed his requirements after seeing the prototype.
B) The team rushed through collecting the requirements and developing the prototype, since the timeline was tight, so they missed some key requirements.
C) The CEO was not identified as a key project stakeholder.
D) All of the requirements approved for the prototype were not implemented.
ANSWER: C
In the agreement document of the project, the time schedules and deliverables in each phase are clearly stipulated. From a project management perspective, this is:
A) Risk
B) Assumption
C) Constraint
D) Issue
ANSWER: B
In the agreement document of the project, the time schedules and deliverables in each phase are clearly stipulated. From a project management perspective, this is:
A) Risk
B) Assumption
C) Constraint
D) Issue
ANSWER: B
In a job interview, you are asked to define the most important characteristic of a project manager. Which of the following will be the best answer?
A) Subject matter expert
B) Integrator
C) Creative person
D) Risk┬بminimizer
ANSWER: B
In a job interview, you are asked to define the most important characteristic of a project manager. Which of the following will be the best answer?
A) Subject matter expert
B) Integrator
C) Creative person
D) Risk┬بminimizer
ANSWER: B
The customer communicates a request for a change in your project plan. What should be your first step towards addressing the change request?
A) Talk with team members to understand implications of the change.
B) Communicate the change to the management to get their inputs.
C) Open up a change control.
D) Implement the change and communicate to the customer.
ANSWER: A
The scope baseline is a component of the project management plan and is critical for you to verify scope and perform scope control. Which of the following is NOT a component of the scope baseline?
A) Project Scope Statement
B) WBS
C) WBS dictionary
D) Activity list
ANSWER: D
Your company exhibited a car model in two international auto expos and obtained feedback from the global automobile industry, auto magazines, and others. The company decided to go ahead with the designing and manufacturing of the car, taking into consideration the feedback received. Which of the following methods did your company use to make this decision?
A) Observation technique
B) Prototype
C) Requirement documentation
D) Requirement traceability matrix
ANSWER: B
You are taking over a project that is currently in the planning stage. The previous project manager worked with the team to finalize the process of defining activities, and you joined the team at the end of this process. The next process requires the determination and documentation of the relationships among project activities. Of the following, which is a tool and technique used in this process?
A) Schedule Baseline
B) Dependency Determination
C) Activity List
D) Schedule Compression
ANSWER: B
While doing monitoring and controlling for your project, you notice that the cost variance is negative, but schedule variance is positive. This indicates:
A) Cost and schedule are not dependent on each other
B) Project is under budget and behind schedule
C) Project is over budget and ahead of schedule
D) Crashing may be recommended to make the cost variance positive
ANSWER: C
In your project, you estimate the cost of individual activities or work packages, and then roll up the individual estimates for subsequent reporting and tracking purposes. This can be done using:
A) Bottom-up estimating ┬ب
B) Analogous estimating
C) Parametric modeling
D) Top-down estimating
ANSWER: A
Which of the following processes has risk register as a primary output?
A) Perform Qualitative Risk Analysis
B) Control Risks
C) Plan Risk Management
D) Identify Risks
ANSWER: D
Which hierarchical chart shows resources?
A) RBS
B) OBS
C) WBS
D) Scope statement
ANSWER: A
You are the project manager and have decided to outsource a part of the project to a vendor. You have offered a bonus to the vendor if the work is completed in two months. This is an example of _____________.
A) Project incentive
B) Project goal
C) Fixed price contract
D) None
ANSWER: A
The project that you are in charge has been successfully completed. The last of the deliverables have been formally accepted by the client. You had several contractors with whom contracts were prepared. With the project done you decide to communicate the completion details and closure of contracts. Which is the best form of communication
A) Formal written
B) Formal verbal
C) Informal verbal
D) Informal written
ANSWER: A
You are developing strategies to effectively engage stakeholders throughout the project life cycle. What is process you are working on?
A) Plan Stakeholder Management
B) Identify Stakeholders
C) Manage Stakeholder Engagement
D) Control Stakeholder Engagement
ANSWER: A
Two of the resource optimization techniques are:
A) Crashing and fast tracking
B) Logical relationships and dependencies
C) Resource levelling and resource smoothing
D) What-if scenarios and simulation
ANSWER: C
PMI has contacted you regarding an ethics violation of a PMP candidate. The question is in regard to a friend who said he worked as project manager under your guidance. You know this is not true, but to save a friendship, you avoid talking with PMI. This is a violation of which of the following?
A) The PMI Code to cooperate on ethics violations investigations
B) The PMI Code to report accurate information
C) The PMI Code to report any PMP violations
D) The law concerning ethical practices
ANSWER: A
If a project has a Schedule Performance Index (SPI) of 0.90, this means that:
A) 90% of the work planned to date has been completed
B) 90% of the work of the whole project has been completed
C) 90% of the budget planned to date has been spent
D) 90% of the project budget has been spent
ANSWER: A
A project is
A) A revenue-generating activity that needs to be accomplished while achieving customer satisfaction.
B) A temporary endeavor undertaken to create a unique product, service, or result.
C) A set of sequential activities performed in a process or system.
D) A set of sequential activities performed in a process or system.
ANSWER: B
The types of project management office (PMO) structures in organizations include all of the following EXCEPT.
A) Supportive PMOs that provide a consultative role to projects by supplying templates, best practices, training, access to information, and lessons learned from other projects.
B) Controlling PMOs that provide support and require compliance through various means.
C) Directive PMOs that take control of the projects by directly managing the projects
D) Harmonizing PMOs that strive to reduce conflict and improve harmony among project team members.
ANSWER: D
All of the following are components of culture EXCEPT
A) Beliefs
B) Norms
C) Intelligence
D) Values
ANSWER: C
Processes required to establish the scope of the project, refine the objectives, and define the course of action required to attain the objectives that the project was undertaken to achieve.
A) Initiating Process Group
B) Planning Process Group
C) Executing Process Group
D) Closing Process Group
ANSWER: B
Which of the below describes the 100% rule of WBS?
A) The WBS should include all the project and product work
B) The WBS should not include any work which is not part of the project or product work
C) None of the above
D) A and B
ANSWER: D
Which of the following is NOT a characteristic of a project?
A) Constrained by limited resources
B) Planned, executed, and controlled
C) Creates a unique product or service
D) Ongoing and repetitive
ANSWER: D
Develop Project Charter
A) Data gathering
B) Decomposition
C) Accepted deliverables
D) Project management plan
ANSWER: A
One of the tools and techniques used in Develop Project Charter is :
A) Data gathering
B) Decomposition
C) Accepted deliverables
D) Project management plan
ANSWER: A
Develop Project Charter
A) Data gathering
B) Decomposition
C) Accepted deliverables
D) Project management plan
ANSWER: A
The benefit of Develop Project Charter is:
A) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
B) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
C) It allows for documented changes of the overall project objectives or plans.
D) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
ANSWER: A
Which of the following is NOT a characteristic of a project?
A) Constrained by limited resources
B) Planned, executed, and controlled
C) Creates a unique product or service
D) Ongoing and repetitive
ANSWER: D
One of the inputs for Develop Project Charter is:
A) Agreements
B) Project charter
C) Knowledge management
D) Meetings
ANSWER: A
One of the outputs of Develop Project Charter is
A) Project charter
B) Lessons learned register
C) Data gathering
D) Decomposition
ANSWER: A
┬بASSUMING THAT ALL FUTURE WORK WILL BEPERFORMED AT THE BUDGETED RATE, THE ESTIMATE AT COMPLETION (EAC) IS:
A) 200.
B) 220.
C) 240.
D) 260.
ANSWER: C
WHICH OF THE FOLLOWING IS NOT A PROJECT MANAGEMENT KNOWLEDGE AREA:
A) Communications Management
B) Procurement Management
C) Change Control Management
D) Project Integration Management
ANSWER: C
Develop Project Charter
A) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
B) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
C) It allows for documented changes of the overall project objectives or plans.
D) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
ANSWER: A
You are working in the Project Management Office (PMO) of your organization. Your job responsibility is to:
A) Manage the operational activities in the company
B) Manage human resource and risk management issues for individual projects
C) Provide support functions to project managers in the form of training, providing software, standardizing policies, etc.
D) Provide subject matter expertise in the functional areas of the project
ANSWER: C
Develop Project Charter:
A) Agreements
B) Project charter
C) Knowledge management
D) Meetings
ANSWER: A
Processes required to establish the scope of the project, refine the objectives, and define the course of action required to attain the objectives that the project was undertaken to achieve.
A) Initiating Process Group
B) Planning Process Group
C) Executing Process Group
D) Closing Process Group
ANSWER: B
Develop Project Charter:
A) Project charter
B) Lessons learned register
C) Data gathering
D) Decomposition
ANSWER: A
Four project managers are having lunch together and discussing their projects. Most of the time they are just complaining about how hard projects are to manage in their company. Some complain about the stakeholders and the number of changes they cause. Others talk about how hard it is to get people to cooperate and perform. One project manager wants to focus on the advantages of the matrix type organization they all work in for their projects. Which of the following would he mention?
A) Improved project manager control over resources
B) More than one boss for project teams
C) Communications are easier
D) Reporting is easier
ANSWER: C
Which of the below describes the 100% rule of WBS?
A) The WBS should include all the project and product work
B) The WBS should not include any work which is not part of the project or product work
C) None of the above
D) A and B
ANSWER: D
A PROJECT IS:
A) A set of sequential activities performed in a process or system.
B) A revenue-generating activity that needs to be accomplished while achieving customer satisfaction.
C) An ongoing endeavor undertaken to meet customer or market requirements.
D) A temporary endeavor undertaken to create a unique product, service, or result.
ANSWER: D
You are working in the Project Management Office (PMO) of your organization. Your job responsibility is to:
A) Manage the operational activities in the company.
B) Manage human resource and risk management issues for individual projects.
C) Provide support functions to project managers in the form of training, providing software, standardizing policies, etc.
D) Provide subject matter expertise in the functional areas of the project.
ANSWER: C
Two of the resource optimization techniques are:
A) Crashing and fast tracking
B) Logical relationships and dependencies
C) Resource leveling and resource smoothing
D) What-if scenarios and simulation
ANSWER: C
Two of the resource optimization techniques are:
A) Crashing and fast tracking
B) Logical relationships and dependencies
C) Resource levelling and resource smoothing
D) What-if scenarios and simulation
ANSWER: C
Which of the below accuracy ranges is applicable for a definitive cost estimate?
A) -25% to +75%
B) -10% to +25%
C) -5% to +10%
D) None of the above
ANSWER: C
Which of the following is part of the Perform Quality Assurance process?
A) Benchmarking
B) Cost of Quality
C) Design of experiments
D) Quality audits
ANSWER: D
An important input for the Develop Project Charter process is the:
A) Project management plan
B) Project scope statement
C) Requirements documentation
D) Business case
ANSWER: D
Project Risk Management includes all the processes concerned with conducting risk management planning, identification, analysis, response planning, and controlling risk on a project. In this context, which of the following statements about risk is not accurate?
A) Risk is an uncertain event or condition.
B) Risks have to be identified and properly managed.
C) Risk management should be done throughout the project.
D) Risk have a negative impact on the project objective.
E)
ANSWER: D
ALL OF THE FOLLOWING ARE TRUE ABOUT THE STATEMENT OF WORK (SOW) FOR A PROCUREMENT EXCEPT:
A) It describes the procurement item in sufficient detail to allow prospective sellers to determine if they
B) are capable of providing the products, services, or results.
C) It should be as ambiguous, incomplete, and wordy as possible to allow for future negotiations.
D) It can include specifications, quantity desired, quality levels, performance data, period of performance, work location, and other requirements.
E) It can be revised and refined as required as it moves through the procurement process until incorporated into a signed agreement.
ANSWER: B
Collect Requirements
A) Prototypes
B) Decomposition
C) Enterprise environmental factors
D) Business documents
ANSWER: A
One of the tools and techniques used inCollect Requirements is
A) Prototypes
B) Decomposition
C) Rolling wave planning
D) Critical path method
ANSWER: A
Collect Requirements
A) Prototypes
B) Decomposition
C) Rolling wave planning
D) Critical path method
ANSWER: A
The benefit of Define Scope is:
A) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
B) The scope baseline is maintained throughout the project.
C) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
D) The schedule baseline is maintained throughout the project.
ANSWER: A
You are determining whether the project activities comply with organizational and project policies. This will be done as part of:
A) Inspection
B) Quality audits
C) Quality improvement
D) Trend analysis
ANSWER: B
One of the outputs of Define Scope is
A) Project scope statement
B) Work performance information
C) Data analysis
D) Decision making
ANSWER: A
The customer was not satisfied with the finished product`s quality. The cost of poor quality can also be referred to as:
A) Cost of conformance
B) Failure cost
C) Rework cost
D) Opportunity cost
ANSWER: B
One of the inputs for Define Scope is:
A) Project documents
B) Virtual teams
C) Work performance data
D) Inspection
ANSWER: A
_________ IS THE FORMAL PROCEDURE FOR SANCTIONING PROJECT WORK TO ENSURE IT IS DONE AT THE RIGHT TIME.
A) Work-authorization system
B) Organizational procedures
C) Status review
D) Project planning
ANSWER: A
Define Scope
A) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
B) The scope baseline is maintained throughout the project.
C) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
D) The schedule baseline is maintained throughout the project.
ANSWER: A
The customer was not satisfied with the finished product`s quality. The cost of poor quality can also be referred to as:
A) Cost of conformance
B) Failure cost
C) Rework cost
D) Opportunity cost
E)
ANSWER: B
Define Scope:
A) Project scope statement
B) Work performance information
C) Data analysis
D) Decision making
ANSWER: A
ALL OF THE FOLLOWING ARE EXTERNAL ENVIRONMENTAL FACTORS EXCEPT:
A) Legal restrictions
B) Organizational values and principles
C) Competitive movements
D) Economic conditions
ANSWER: B
Define Scope
A) Project documents
B) Virtual teams
C) Work performance data
D) Inspection
ANSWER: A
ALL OF THE FOLLOWING ARE CHARACTERISTICS OF A DECISION TREE EXCEPT:
A) A decision tree is a diagramming and calculation technique for evaluating the implications of a chain of multiple options in the presence of uncertainty
B) Decision tree analysis is a risk analysis tool that can be used to choose the most appropriate responses.
C) A decision tree is primarily a graphical, qualitative risk analysis technique and is not generally used in quantitative risk analysis.
D) Decision tree analysis uses the expected monetary value (EMV) analysis to calculate the average outcomewhen the future includes scenarios that may or may not happen.
ANSWER: C
THE RISK MANAGEMENT PLAN GENERALLY INCLUDESALL OF THE FOLLOWING EXCEPT:
A) Methodology.
B) Risk strategy.
C) Responses to individual risks.
D) Risk categories.
ANSWER: C
THE PERFORM QUALITATIVE RISK ANALYSIS PROCESSASSESSES THE PRIORITY OF IDENTIFIED RISKS USINGALL OF THE FOLLOWING EXCEPT:
A) Relative probability or likelihood of occurrence of identified risks.
B) Impact on project objectives if the identified risks occur.
C) A mathematical technique, such as the expected monetary value (EMV), to create the impression of precision and accuracy.
D) The organizationظآs risk tolerance associated with the project constraints of cost, schedule, scope, and quality.
ANSWER: C
AS AN OUTPUT OF THE MONITOR RISKS PROCESS, AN UPDATED RISK REGISTER GENERALLY INCLUDES SOME OR ALL OF THE FOLLOWING EXCEPT:
A) The work breakdown structure (WBS).
B) Outcomes of risk reassessments, risk audits, and periodic risk reviews.
C) Identification of new risks, updates to probability, impact, priority, response plans, ownership, and other elements of the risk register.
D) Actual outcomes of the projectظآs risks and of the risk responses.
ANSWER: A
SWOT ANALYSIS HAS ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) It is a technique that examines the project from each of the strengths, weaknesses, opportunities and threats (SWOT) perspectives to increase the breadth of identified risks by including internally generated risks.
B) It identifies strengths and weaknesses of the organization, regardless of the specific project or the general business area.
C) It identifies any opportunities for the project that arise from organizational strengths, and any threats arising from organizational weaknesses.
D) It examines the degree to which organizational strengths offset threats, as well as identifies opportunities that may serve to overcome weaknesses.
ANSWER: B
ALL OF THE FOLLOWING ARE INPUTS TO THE IMPLEMENT RISK RESPONSE PROCESS EXCEPT:
A) Project documents.
B) Project risk management plan.
C) Organizational project assets.
D) Expert judgment.
ANSWER: B
ALL OF THE FOLLOWING ARE INPUTS TO THE PLAN PROCUREMENT MANAGEMENT PROCESS EXCEPT:
A) Risk register.
B) Stakeholder register.
C) Procurement strategy.
D) Enterprise environmental factors.
ANSWER: C
GENERALLY, A BID DIFFERS FROM A PROPOSAL IN THAT THE TERM:
A) Bid is used when the seller selection decision will be based on price.
B) Bid is used when technical capability or technical approach are paramount.
C) Proposal is used when the selection decision will be based on price.
D) Proposal is used when the project time frame is limited.
ANSWER: A
APPROVED CHANGE REQUESTS CAN GENERALLY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Modifications to the terms and conditions of the contract.
B) Modification to pricing.
C) Seller invoices.
D) Modification to descriptions of the products, services, or results to be provided.
ANSWER: C
Your projectظآs actual cost has been reported at $200.000. This is equal to the Earned Value. The Budget at completion for your project is $400.000. It is assumed that all future work will be accomplished at the budgeted rate. The EAC (Estimate At Completion) is:
A) $200,000
B) $600,000
C) $400,000
D) Cannot be determined with the information provided
ANSWER: C
Which of the following is the most widely used contract type?
A) Cost plus incentive fee contracts
B) Fixed price incentive fee contracts
C) Cost plus award fee contracts
D) Firm fixed price contracts
ANSWER: D
Define Scope
A) Data analysis
B) Rolling wave planning Rolling wave planning
C) Enterprise environmental factors
D) Project management plan
ANSWER: A
STAKEHOLDERS ARE:
A) The project engineers who design and construct the project.
B) The people, groups, or organizations that could impact or be impacted by a decision, activity, or outcome of the project.
C) The organizationظآs corporate attorneys.
D) The individuals or agencies that control contingency funds and their disbursement through the project management office (PMO).
ANSWER: B
One of the tools and techniques used in Define Scope is
A) Data analysis
B) Rolling wave planning
C) Enterprise environmental factors
D) Project management plan
ANSWER: A
Define Scope
A) Data analysis
B) Rolling wave planning
C) Enterprise environmental factors
D) Project management plan
ANSWER: A
The benefit of Create WBS is:
A) It provides a framework of what has to be delivered.
B) It provides guidance and direction on how the project schedule will be managed throughout the project.
C) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
D) It provides guidance and direction on how the project costs will be managed throughout the project.
ANSWER: A
What is Tuckman`s stages of group development in their respective order?
A) Forming, Norming, Storming, Performing, Adjourning
B) Forming, Storming, Smoothing, Performing, Adjourning
C) Forming, Storming, Norming, Performing, Adjourning
D) Forming, Norming, Storming, Performing, Closing
ANSWER: C
One of the outputs of Create WBS is
A) Scope baseline
B) Schedule management plan
C) Decomposition
D) Variance analysis
ANSWER: A
You are a project manager in a pharmaceutical company and manage a team of 50 resources in a virtual project team across multiple time zones. There were concerns that team members would not be able to work well in this virtual team structure. However, you are mid-way into the project and team members have successfully figured out efficient ways to work together effectively. The team is in which stage of group development?
A) Performing
B) Forming
C) Smoothing
D) Norming
ANSWER: A
One of the inputs for Create WBS is:
A) Project management plan
B) Stakeholder management plan
C) Project reporting
D) Expert judgment
ANSWER: A
WHICH SCOPE MANAGEMENT PROCESS CREATES THE WBS?
A) Initiation
B) Scope planning
C) Scope definition
D) Scope verification
ANSWER: C
Create WBS
A) It provides a framework of what has to be delivered.
B) It provides guidance and direction on how the project schedule will be managed throughout the project.
C) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
D) It provides guidance and direction on how the project costs will be managed throughout the project.
ANSWER: A
You are a project manager in a certain company and manage a team of 50 resources in a virtual project team across multiple time zones. There were concerns that team members would not be able to work well in this virtual team structure. However, you are mid-way into the project and team members have successfully figured out efficient ways to work together effectively. The team is in which stage of group development?
A) Performing
B) Forming
C) Smoothing
D) Norming
ANSWER: A
Create WBS:
A) Scope baseline
B) Schedule management plan
C) Decomposition
D) Variance analysis
ANSWER: A
ALL OF THE FOLLOWING ARE GENERALLY TRUE ABOUT LEADERSHIP IN A PROJECT ENVIRONMENT EXCEPT:
A) It involves focusing the efforts of a group of people toward a common goal and enabling them to work as a team.
B) It is the ability to get things done through others
C) Respect and trust, rather than fear and submission, are the key elements of effective leadership
D) Although important throughout all project phases, effective leadership is critical during the Closing phase of a project when the emphasis is on stakeholder acceptance of the project
ANSWER: D
Create WBS:
A) Project management plan
B) Stakeholder management plan
C) Project reporting
D) Expert judgment
ANSWER: A
WHICH OF THE FOLLOWING IS FALSE ABOUT ADVERTISING AS ONE OF THE TOOLS AND TECHNIQUES OF THE CONDUCT PROCUREMENTS PROCESS?
A) Some government jurisdictions require public advertising of certain types of procurement items
B) Advertisements in general circulation publications and using online resources can cause public- pressure, resulting in bid disputes.
C) Advertising can often be used to expand existing lists of potential sellers.
D) Advertisements can be placed in general circulation publications such as selected newspapers or in specialty trade publications.
ANSWER: B
THE BUYER, USUALLY THROUGH ITS AUTHORIZED PROCUREMENT ADMINISTRATOR, PROVIDES THE SELLER WITH AS AN OUTPUT OF THE CONTROL PROCUREMENT PROCESS.
A) Formal written notice that the contract has been completed
B) Letters of commendation to all project team members
C) Informal notice of acceptance of the deliverables
D) A copy of the internal notice of completion provided to senior management
ANSWER: A
IN WHICH TYPE OF CONTRACTS DO BUYERS NEED TO PRECISELY SPECIFY THE PRODUCT OR SERVICES BEING PROCURED?
A) Cost plus award fee contracts.
B) Fixed-price contracts.
C) Cost-reimbursable contracts.
D) Partnership contracts.
ANSWER: B
WHICH OF THE FOLLOWING IS ONE OF THE TERMS USED TO DESCRIBE CONTESTED CHANGES AND POTENTIAL CONSTRUCTIVE CHANGES WHERE THE BUYER AND SELLER CANNOT REACH AN AGREEMENT ON COMPENSATION FOR THE CHANGE OR CANNOT AGREE THAT A CHANGE HAS OCCURRED?
A) Forcing.
B) Mediation.
C) Complaints.
D) Claims.
ANSWER: D
CONSTRUCTIVE CHANGES ARE:
A) Postponed as long as possible to protect the budget.
B) Viewed as negative, quantified, and tabulated.
C) Uniquely identified and documented by project correspondence.
D) Submitted for bids to the relevant vendor list.
ANSWER: C
ALL LEGAL CONTRACTUAL RELATIONSHIPS GENERALLY FALL INTO ONE OF THE FOLLOWING BROAD CATEGORIES EXCEPT:
A) Request for proposal (RFP)
B) Fixed-price contracts.
C) Cost-reimbursable contracts.
D) Time and material contracts (T&M).
ANSWER: A
SOURCE SELECTION CRITERIA ARE DEVELOPED AND USED TO RATE OR SCORE SELLER PROPOSALS. THESE CRITERIA GENERALLY HAVE ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) They are often included as a part of the procurement documents.
B) They can be objective or subjective.
C) They may be limited to only the purchase price if the procurement item is readily available from a number of acceptable sellers.
D) They generally require specification of the name of the transportation organization responsible for delivery of procured products.
ANSWER: D
ALL OF THE FOLLOWING ARE TOOLS AND TECHNIQUES OF THE CONDUCT PROCUREMENTS PROCESS EXCEPT:
A) Interpersonal and team skills.
B) Bidder conferences.
C) Expert judgment.
D) Proposal evaluation techniques.
ANSWER: D
During the Identify Stakeholders process, which document may provide some initial idea of who the stakeholders are for a project?
A) Communications management plan
B) Project charter
C) Human resource contracts
D) Responsibility assignment matrix
ANSWER: B
Create WBS
A) Decomposition
B) Variance analysis
C) Enterprise environmental factors
D) Project charter
ANSWER: A
One of the tools and techniques used in Create WBS is
A) Decomposition
B) Variance analysis
C) Enterprise environmental factors
D) Project charter
ANSWER: A
ALL OF THE FOLLOWING STATEMENTS ABOUT MANAGE STAKEHOLDER ENGAGEMENT ARE TRUE EXCEPT:
A) Managing stakeholder engagement helps increase the probability of project success.
B) The ability of stakeholders to influence the project is typically highest during the initial stages and gels progressively lower as the project progresses.
C) The ability of stakeholders to influence the project is typically lowest during the initial stages and gets progressively higher as the project progresses.
D) The project manager is responsible for engaging and managing the various stakeholders in a project and may call upon the project sponsor to assist as needed.
ANSWER: C
Create WBS
A) Decomposition
B) Variance analysis
C) Enterprise environmental factors
D) Project charter
ANSWER: A
The benefit of Validate Scope is:
A) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
B) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
C) It provides the amount of time each activity will take to complete.
D) It determines the monetary resources required for the project.
ANSWER: A
Project Risk Management includes all the processes concerned with conducting risk management planning, identification, analysis, response planning, and controlling risk on a project. In this context, which of the following statements about risk is not accurate?
A) Risk is an uncertain event or condition.
B) Risks have to be identified and properly managed.
C) Risk management should be done throughout the project.
D) Risk have a negative impact on the project objective.
ANSWER: D
One of the outputs of Validate Scope is
A) Accepted deliverables
B) Activity list
C) Decision making
D) Decomposition
ANSWER: A
As part of the risk management process, you have just created an overall risk ranking of the project and a list of prioritized identified risks which need additional analysis and determined trends in risk analysis results. What should you do next?
A) Analyze the effect of identified risks on overall project objectives
B) Create a list of identified risks
C) Maintain a risk register
D) Make a list of potential responses to the risks
ANSWER: D
One of the inputs for Validate Scope is:
A) Verified deliverables
B) Project charter
C) Expert judgment
D) Data analysis
ANSWER: A
WHICH OF THE FOLLOWING IS NOT A TOOL OR TECHNIQUE OF PROJECT PLAN EXECUTION?
A) PM Information system
B) Change control system
C) Organizational procedures
D) General management skills
ANSWER: B
Validate Scope
A) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
B) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
C) It provides the amount of time each activity will take to complete.
D) It determines the monetary resources required for the project.
ANSWER: A
As part of the risk management process, you have just created an overall risk ranking of the project and a list of prioritized identified risks which need additional analysis and determined trends in risk analysis results. What should you do next?
A) Analyze the effect of identified risks on overall project objectives
B) Create a list of identified risks
C) Maintain a risk register
D) Make a list of potential responses to the risks
ANSWER: D
Validate Scope:
A) Accepted deliverables
B) Activity list
C) Decision making
D) Decomposition
ANSWER: A
Validate Scope:
A) Verified deliverables
B) Project charter
C) Expert judgment
D) Data analysis
ANSWER: A
WHICH OF THE FOLLOWING IS NOT A PROCESS IN PROJECT STAKEHOLDER MANAGEMENT?
A) Identify Stakeholders.
B) Control Stakeholder Engagement.
C) Monitor Stakeholder Engagement.
D) Manage Stakeholder Engagement
ANSWER: B
TO INCREASE THE CHANCES OF ACHIEVING PROJECT SUCCESS, THE PROJECT MANAGER SHOULD DO ALL OF THE FOLLOWING EXCEPT:
A) Identify the stakeholders early in the project or phase.
B) Analyze the stakeholders' levels of interest and individual expectations as well as their importance and influence.
C) As much as possible, create conflicts among various stakeholders to allow the project team to get optimal work done.
D) Communicate and work with stakeholders to meet their needs/expectations.
ANSWER: C
YOU ARE DEVELOPING MANAGEMENT STRATEGIES TO EFFECTIVELY ENGAGE STAKEHOLDERS THROUGHOUT THE PROJECT LIFE CYCLE, BASED ON THE ANALYSIS OF THEIR NEEDS, INTERESTS, AND POTENTIAL IMPACT ON PROJECT SUCCESS. THIS IS KNOWN AS:
A) Manage Stakeholder Engagement.
B) Monitor Stakeholder Engagement.
C) Plan Stakeholder Engagement.
D) Plan Stakeholder Management.
ANSWER: C
YOU ARE INVOLVED IN THE PROCESS OF COMMUNICATING AND WORKING WITH STAKEHOLDER, TO MEET THEIR NEEDS/EXPECTATIONS, ADDRESS ISSUES AS THEY OCCUR, AND FOSTER APPROPRIATE STAKEHOLDER ENGAGEMENT IN PROJECT ACTIVITIES THROUGHOUT THE PROJECT LIFE CYCLE. THIS IS KNOWN AS:
A) Manage Stakeholder Engagement.
B) Monitor Stakeholder Engagement.
C) Plan Stakeholder Management.
D) Plan Stakeholder Engagement.
ANSWER: A
You are monitoring overall project stakeholder relationships and adjusting strategies and ????for engaging stakeholders. This is known as:
A) Manage Stakeholder Engagement.
B) Plan Stakeholder Engagement.
C) Stakeholdersظآ Relationship Engagement.
D) Monitor Stakeholder Engagement.
ANSWER: D
YOU ARE USING A CLASSIFICATION MODEL FOR STAKEHOLDERS' ANALYSIS THAT GROUPS THE STAKEHOLDERS BASED ON THEIR LEVEL OF AUTHORITY AND THEIR LEVEL OR CONCERN REGARDING THE PROJECT OUTCOMES. THIS IS KNOWN AS:
A) Power/influence grid.
B) Influence/impact grid.
C) Power/interest grid.
D) Salience model.
ANSWER: C
IN DEVELOPING A STAKEHOLDER REGISTER, YOU NEED TO INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Identification information.
B) Assessment information.
C) Stakeholder classification.
D) Project risk information.
ANSWER: D
CLASSIFICATION OF THE ENGAGEMENT LEVELS OF STAKEHOLDERS INCLUDES ALL OF THE FOLLOWING EXCEPT:
A) Resistant.
B) Neutral.
C) Supportive.
D) Manipulative.
ANSWER: D
MANAGE STAKEHOLDER ENGAGEMENT INVOLVES ALL OF THE FOLLOWING ACTIVITIES EXCEPT:
A) Clarifying and resolving issues that have been identified.
B) Avoiding potential concerns that have not yet become issues.
C) Anticipating future problems that may be raised by stakeholders.
D) Managing stakeholders' expectations through negotiation and communication.
ANSWER: B
Control Scope:
A) Work performance information
B) Project schedule network diagrams
C) Variance analysis
D) Rolling wave planning
ANSWER: A
The customer communicates a request for a change in your project plan. What should be your first step towards addressing the change request?
A) Talk with team members to understand implications of the change.
B) Communicate the change to the management to get their inputs.
C) Open up a change control.
D) Implement the change and communicate to the customer.
ANSWER: A
Validate Scope
A) Decision making
B) Decomposition
C) Organizational process assets
D) Project management plan
ANSWER: A
One of the tools and techniques used inValidate Scope is
A) Decision making
B) Decomposition
C) Organizational process assets
D) Project management plan
ANSWER: A
Estimate Costs
A) Three-point estimating
B) To-complete performance index
C) Project charter
D) Project documents
ANSWER: A
THE PMBOK┬« GUIDE IS THE STANDARD FOR:
A) Managing all projects all of the time
B) Managing all projects most of the time
C) Managing most projects most of the time
D) Managing some projects some of the time
ANSWER: C
Validate Scope
A) Decision making
B) Decomposition
C) Organizational process assets
D) Project management plan
ANSWER: A
The benefit of Control Scope is:
A) The scope baseline is maintained throughout the project.
B) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
C) It generates a schedule model with planned dates for completing project activities.
D) It determines the cost baseline against which project performance can be monitored and controlled.
ANSWER: A
Which of the following is the most widely used contract type?
A) Cost plus incentive fee contracts
B) Fixed price incentive fee contracts
C) Cost plus award fee contracts
D) Firm fixed price contracts
ANSWER: D
You are considering whether to buy or make a software product. If you want to buy, the cost is $80,000, and the cost of procuring and integrating the product in your company is $1,000. If you want to build it yourself, the product will require seven engineers working for three months. The salary of each software engineer is $4,000 per month. The other related miscellaneous costs allocated to the project are $2,000. Which option will you choose?
A) Buy
B) Build
C) Neither build nor buy
D) Need more information on suppliers to make a decision
ANSWER: A
One of the inputs for Control Scope is:
A) Work performance data
B) Project charter
C) Meetings
D) Data gathering
ANSWER: A
PROJECT SCOPE MANAGEMENT IS:
A) Used to make sure that all work required, and only the work required, is included in order to complete the project successfully
B) The features to be included in a product or service
C) Is synonymous with change control management
D) Is conducted primarily by external stakeholders
ANSWER: A
One of the outputs of Control Scop is
A) Work performance information
B) Project schedule network diagrams
C) Variance analysis
D) Rolling wave planning
ANSWER: A
Control Scope
A) The scope baseline is maintained throughout the project.
B) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
C) It generates a schedule model with planned dates for completing project activities.
D) It determines the cost baseline against which project performance can be monitored and controlled.
ANSWER: A
You are considering whether to buy or make a software product. If you want to buy, the cost is $80,000, and the cost of procuring and integrating the product in your company is $1,000. If you want to build it yourself, the product will require seven engineers working for three months. The salary of each software engineer is $4,000 per month. The other related miscellaneous costs allocated to the project are $2,000. Which option will you choose?
A) Buy
B) Build
C) Neither build nor buy
D) Need more information on suppliers to make a decision
ANSWER: A
ALL OF THE FOLLOWING ARE COMPONENTS OF CULTURE EXCEPT:
A) Values.
B) Norms.
C) Intelligence
D) Beliefs
ANSWER: C
Control Scope:
A) Work performance data
B) Project charter
C) Meetings
D) Data gathering
ANSWER: A
MONITOR STAKEHOLDER ENGAGEMENT TOOLS AND TECHNIQUES INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Decision making.
B) Stakeholder analysis.
C) Meetings.
D) Issue log.
ANSWER: D
THE POWER/INTEREST GRID CLASSIFICATION MODEL FOR STAKEHOLDERS' ANALYSIS SUGGESTS:
A) Keeping high-power/high-interest stakeholders informed.
B) Keeping high-power/low-interest stakeholders satisfied.
C) Monitoring low-power/high-interest stakeholders.
D) Managing low-power/low-interest stakeholders closely.
ANSWER: B
DURING A PUBLIC HEARING REGARDING YOUR COMPANY'S PROPOSED STATE-OF-THE-ART WATER OF THE TOWER, A HIGHLY INTERESTED RESIDENT OF THE AREA CHALLENGES YOU: "WOULD YOU HAVE THIS THING BUILT IN YOUR OWN BACKYARD?" YOUR BEST ANSWER CAN BEGIN BY SAYING:
A) Given that you are not listed in the stakeholder register, I cannot take your concerns seriously.
B) I am sorry that you appear to dislike having this water tower as your neighbor. We will look for another location for it.
C) C. Given that the experts provided ample information. That the proposed location is the most suitable. I would be pleased to have this state-of the art water tower as a neighbor.
D) If you want to have usable water pressure in your residence, you should not interfere with outwork.
ANSWER: C
EXAMPLES OF INTERPERSONAL SKILLS THAT A PROJECT MANAGER USES MOST OFTEN INCLUDE ALL OF THE FOLLOWING INDICATORS EXCEPT:
A) Leadership.
B) Influencing.
C) Governance.
D) Effective decision making.
ANSWER: C
ALL OF THE FOLLOWING ARE TRUE ABOUT PROJECTS AND OPERATIONS EXCEPT:
A) Operations are ongoing endeavors that produce repetitive outputs, with resources assigned to do basically the same set of tasks according to the standards institutionalized in a product life cycle, whereas projects are temporary endeavors.
B) Projects require project management activities and skill sets, whereas operations require business process management, operations management activities, and skill sets.
C) Projects can intersect with operations at various points during the product life cycle. At each point, deliverables and knowledge are transferred between the project and operations for implementation of the delivered work.
D) Because of their temporary nature, projects cannot help achieve an organizationظآs long-term goals. Therefore, strategic activities in the organization can be generally addressed within the organization's normal operations
ANSWER: D
YOUR JOB RESPONSIBILITY IS TO ALIGN COMPONENTS (PROJECTS, PROGRAMS, OR RELATED OPERATIONS) TO THE ORGANIZATIONAL STRATEGY, ORGANIZED INTO PORTFOLIOS OR SUBSIDIARY PORTFOLIOS TO OPTIMIZE PROJECTOR PROGRAM OBJECTIVES, DEPENDENCIES, COSTS, TIMELINES, BENEFITS, RESOURCES, AND RISKS. THIS IS KNOWN AS:
A) Components management.
B) Process management.
C) Program management.
D) Portfolio management.
ANSWER: D
THE COLLECTION OF GENERALLY SEQUENTIAL AND SOMETIMES OVERLAPPING PROJECT PHASES, WHOSE NAME AND NUMBER ARE DETERMINED BY THE MANAGEMENT AND CONTROL NEEDS OF THE ORGANIZATION OR ORGANIZATIONS INVOLVED IN THE PROJECT, IS KNOWN AS THE:
A) Project waterfall.
B) A.┬ب┬ب┬ب┬ب┬ب Project life cycle.Project life cycle.
C) Project life stages.
D) Project Management Process Groups .
ANSWER: B
ALL OF THE FOLLOWING ARE TRUE ABOUT PROJECT PHASES AND THE PROJECT LIFE CYCLE EXCEPT:
A) Stakeholder influences, risk, and uncertainty are greatest at the start of the project. These factors decrease over the life of the project.
B) The ability to influence the final characteristics of the project's product, without significantly impacting cost, is highest at the start of the project and decreases as the project progresses toward completion.
C) The cost of changes and correcting errors typically increases substantially as the project approaches completion.
D) Cost and staffing levels are generally steady throughout the project life cycle .
ANSWER: D
ALL OF THE FOLLOWING STATEMENTS ABOUT THE PROJECT LIFE CYCLE AND THE PRODUCT LIFE CYCLE ARE TRUE EXCEPT:
A) In the project predictive life cycle, the project scope and the time and cost required to deliver that scope are determined as early in the project life cycle as practically possible.
B) In the project iterative and incremental life cycles, project phases intentionally repeat one or more project activities as the project teamظآs understanding of the product increases.
C) The product life cycle is the series of phases that represent the evolution of a product, from concept through delivery, growth, maturity, and to retirement
D) The product life cycle is contained within the predictive project life cycle.
ANSWER: D
Plan Schedule Management:
A) Schedule management plan
B) Duration estimates
C) Meetings
D) Dependency determination and integration
ANSWER: A
Control Scope
A) Variance analysis
B) Rolling wave planning
C) Organizational process assets
D) Stakeholder management plan
ANSWER: A
One of the tools and techniques used in Control Scope is
A) Variance analysis
B) Rolling wave planning
C) Organizational process assets
D) Stakeholder management plan
ANSWER: A
THE FIVE PROJECT MANAGEMENT PROCESS GROUPS ARE:
A) Planning, Checking, Directing, Monitoring, and Recording.
B) Initiating, Planning, Executing, Monitoring and Controlling, and Closing.
C) Planning, Executing, Directing, Closing, and Commissioning.
D) Initiating, Executing, Monitoring, Evaluating, and Closing.
ANSWER: B
Control Scope
A) Variance analysis
B) Rolling wave planning
C) Organizational process assets
D) Stakeholder management plan
ANSWER: A
The benefit of Plan Schedule Management is:
A) It provides guidance and direction on how the project schedule will be managed throughout the project.
B) It provides the amount of time each activity will take to complete.
C) The schedule baseline is maintained throughout the project.
D) The cost baseline is maintained throughout the project.
ANSWER: A
During the Identify Stakeholders process, which document may provide some initial idea of who the stakeholders are for a project?
A) Communications management plan
B) Project charter
C) Human resource contracts
D) Responsibility assignment matrix
ANSWER: B
During the Identify Stakeholders process, which document may provide some initial idea of who the stakeholders are for a project?
A) Communications management plan
B) Project charter
C) Human resource contracts
D) Responsibility assignment matrix
ANSWER: B
One of the inputs for Plan Schedule Management is:
A) Organizational process assets
B) Work performance data
C) MeetingsMeetings
D) Parametric estimating
ANSWER: A
WHICH OF THE FOLLOWING IS NOT AN OUTPUT OF THE INITIATION PROCESS:
A) Project charter
B) Constraints
C) Alternatives identification
D) Assignment of the PM
ANSWER: C
One of the outputs of Plan Schedule Management is
A) Schedule management plan
B) Duration estimates
C) Meetings
D) Dependency determination and integration
ANSWER: A
Plan Schedule Management
A) It provides guidance and direction on how the project schedule will be managed throughout the project.
B) It provides the amount of time each activity will take to complete.
C) The schedule baseline is maintained throughout the project.
D) The cost baseline is maintained throughout the project.
ANSWER: A
During the Identify Stakeholders process, which document may provide some initial idea of who the stakeholders are for a project?
A) Communications management plan
B) Project charter
C) Human resource contracts
D) Responsibility assignment matrix
ANSWER: B
WHEN PERFORMING INTEGRATION ON THE PROJECT, THE ROLE OF THE PROJECT MANAGER IS:
A) To work with the project sponsor to understand the strategic objectives and ensure the alignment of the project objectives and results with those of the project and business area.
B) To perform all of the work that is required to get the project approved and baselined for communication to the team
C) To complete the project charter and seek formal approval from the sponsor of the project.
D) To involve the team in group activities to facilitate teamwork, which builds an integrated project organizational structure
ANSWER: A
Plan Schedule Management:
A) Organizational process assets
B) Work performance data
C) MeetingsMeetings
D) Parametric estimating
ANSWER: A
YOU ARE MANAGING A PROJECT IN WHICH YOU INTEND TO RESPOND TO HIGH LEVELS OF CHANGE AND ONGOING STAKEHOLDER INVOLVEMENT. THE MOST SUITABLE PROJECT LIFE CYCLE FOR YOUR PROJECT IS THE:
A) Predictive life cycle.
B) Adaptive life cycle.
C) Waterfall life cycle.
D) Configuration management life cycle.
ANSWER: B
PROJECT MANAGEMENT PROCESSES:
A) May be overlapping activities that occur throughout the project.
B) May be overlapping activities that generally occur at the same level of intensity within each phase of the project.
C) Are generally discrete, one-time events.
D) Are discrete, repetitive events that occur generally at the same level of intensity throughout each phase of the project.
ANSWER: A
THE LINKAGES BETWEEN PROJECT MANAGEMENT PROCESSES ARE BEST DESCRIBED BY THE FOLLOWING
A) The work breakdown structure links processes.
B) Processes are linked by their planned objectives- the summary objective of one often becomes the detailed action plan for another within the project, subproject, or project phase.
C) Processes are linked by the outputs that arc producedظ¤the output of one process generally becomes an input to another process or is a deliverable of the project, subproject, or project phase.
D) There are no significant links between discrete processes.
ANSWER: C
FOR A PROJECT TO BE SUCCESSFUL, THE PROJECT SHOULD GENERALLY ACHIEVE ALL OF THE FOLLOWING EXCEPT:
A) Achieving stakeholder satisfaction.
B) Striving to obtain acceptable customer/end-user adoption.
C) Appling knowledge, skills, and processes within the Project Management Process Groups uniformly to meet the project objectives.
D) Fulfilling other agreed-upon success measures or criteria.
ANSWER: C
THE PROJECT BUSINESS CASE IS ALL OF THE FOLLOWING EXCEPT:
A) Documented economic feasibility study used to establish the validity of the benefits of a selected component lacking sufficient definition and that is used as a basis for the authorization of further project management activities.
B) A document that lists the objectives and reasons for project initiation.
C) A document that serves as an important input to the project initiation and is seldom used after the project is approved.
D) An important document that may result in a go/no- go decision for the project.
ANSWER: C
THE KEY ELEMENTS OF THE BENEFITS MANAGEMENT PLAN ARE ALL OF THE FOLLOWING EXCEPT:
A) Work Breakdown Structure.
B) Benefits owner.
C) Assumptions.
D) Strategic alignment.
ANSWER: C
A SIGNIFICANT AMOUNT OF DATA IS COLLECTED AND ANALYZED THROUGHOUT THE PROJECT. ALL OF THE FOLLOWING ARE EXAMPLES OF PROJECT DATA AND INFORMATION EXCEPT:
A) Work performance data.
B) Work performance analysis.
C) Work performance information.
D) Work performance reports.
ANSWER: B
PROJECT TAILORING IS AN IMPORTANT CONSIDERATION FOR MOST PROJECTS. WHICH OF THE FOLLOWING IS THE LEAST LIKELY PROJECT CONSIDERATION?
A) Project managerظآs skills and competency.
B) Each project is unique.
C) Addressing competing constraints.
D) Level of project governance varies.
ANSWER: A
ALL OF THE FOLLOWING ARE EXTERNAL ENVIRONMENTAL FACTORS EXCEPT:
A) Legal restrictions.
B) Organizational values and principles.
C) Competitive movements.
D) Economic conditions.
ANSWER: B
Define Activities:
A) Activity list
B) Risk register
C) Rolling wave planning
D) Parametric estimating
ANSWER: A
Plan Schedule Management
A) Meetings
B) Dependency determination and integration
C) Organizational process assets
D) Project charter
ANSWER: A
One of the tools and techniques used in Plan Schedule Management is
A) Meetings
B) Dependency determination and integration
C) Organizational process assets
D) Project charter
ANSWER: A
YOU ARE INVOLVED IN COLLECTING REQUIREMENTS FOR YOUR PROJECT. YOU ARE LIKELY TO USE THE STAKEHOLDER REGISTER FOR ALL OF THE FOLLOWING EXCEPT:
A) Identifying stakeholders who can provide information on the requirements.
B) Capturing major requirements that stakeholders may have for the project.
C) Capturing main expectations that stakeholders may have for the project.
D) Evaluating the product breakdown structure (PBS) associated with each of the key stakeholders.
ANSWER: D
Plan Schedule Management
A) Meetings
B) Dependency determination and integration
C) Organizational process assets
D) Project charter
ANSWER: A
The benefit of Define Activities is:
A) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
B) It generates a schedule model with planned dates for completing project activities.
C) It provides guidance and direction on how the project costs will be managed throughout the project.
D) It provides guidance and direction on how quality will be managed and verified throughout the project.
ANSWER: A
You are the project manager working on a project to develop a new 4-color erasable pen. The customer, PM study.com, is very excited to offer this innovative pen to participants in their PMP prep boot camp class, as it will allow them to erase mistakes made when creating their detailed process chart. PM study also wants to use the pen to help promote their other brands like My IT study.com and SCRUM study.com, so they have asked for their affiliate logos to appear on the pen.They also want the product development to be rushed as they are running low on current inventory and want their next order to consist of the new pen. Since the product is a new concept and the customer is an important one, you decide to create a prototype of the pen during the design phase.After reviewing the prototype, PM studyظآs CEO advises that he is not happy with the design and the size of the logos. The Quality and Marketing Directors and other PM study stakeholders are happy with the prototype and feel that all their requirements were met. What could be the most likely cause of this situation?
A) The CEO changed his requirements after seeing the prototype.
B) The team rushed through collecting the requirements and developing the prototype, since the timeline was tight, so they missed some key requirements.
C) The CEO was not identified as a key project stakeholder.
D) All of the requirements approved for the prototype were not implemented.
ANSWER: C
One of the inputs for Define Activities is:
A) Project management plan
B) Stakeholder management plan
C) Project management information system
D) Risk categorization
ANSWER: A
THE LOWEST LEVEL OF THE WBS IS:
A) Control account
B) Code of accounts
C) Work Package
D) Deliverable
ANSWER: C
Define Activities
A) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
B) It generates a schedule model with planned dates for completing project activities.
C) It provides guidance and direction on how the project costs will be managed throughout the project.
D) It provides guidance and direction on how quality will be managed and verified throughout the project.
ANSWER: A
One of the outputs of Define Activities is
A) Activity list
B) Risk register
C) Rolling wave planning
D) Parametric estimating
ANSWER: A
PERFORMING INTEGRATION IS A CORNERSTONE SKILL FOR ALL PROJECT MANAGERS; THE FOLLOWING DESCRIBE THE THREE DIFFERENT LEVELS OF PERFORMING INTEGRATION EXCEPT:
A) Cognitive level.
B) Process level.
C) Complexity level.
D) Context level.
ANSWER: C
Define Activities:
A) Project management plan
B) Stakeholder management plan
C) Project management information system
D) Risk categorization
ANSWER: A
ORGANIZATIONAL PROCESS ASSETS (OPAS) INFLUENCE THE MANAGEMENT OF PROJECTS. WHICH ONE OF THE FOLLOWING BEST DESCRIBES THE IMPORTANT CATEGORIES OF OPAS?
A) Organizational knowledge bases and processes
B) Processes, policies, procedures, tools, and techniques.
C) Organizational knowledge bases, processes, policies, and procedures.
D) Organizational knowledge bases, tools, and techniques.
ANSWER: C
THE ORGANIZATION'S PROCESSES AND PROCEDURES FOR CONDUCTING PROJECT WORK DURING PROJECT INITIATION AND PLANNING INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Preapproved supplier list.
B) Traceability matrices.
C) Tailoring guidelines for project management processes and procedures.
D) Product and project life cycles, and methods and procedures.
ANSWER: B
THE ORGANIZATION'S PROCESSES AND PROCEDURES FOR CONDUCTING PROJECT WORK DURING EXECUTING, MONITORING, AND CONTROLLING INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Change control procedure.
B) Issue and defect management procedures.
C) Resource availability control and assignment management.
D) Project closing guidelines.
ANSWER: C
THE INTERACTION OF THE VARIOUS SYSTEM COMPONENTS CREATES THE ORGANIZATIONAL CULTURE AND CAPABILITIES THAT ARE IMPORTANT FOR PROJECTS. WHICH ROLE IS TYPICALLY RESPONSIBLE FOR ESTABLISHING THE SYSTEM?
A) Organization's management.
B) Project sponsor.
C) Project manager.
D) Project team.
ANSWER: A
GOVERNANCE IS THE FRAMEWORK WITHIN WHICH AUTHORITY IS EXERCISED IN ORGANIZATIONS. THIS FRAMEWORK INCLUDES ALL OF THE FOLLOWING COMPONENTS EXCEPT:
A) Rules.
B) Policies.
C) Techniques.
D) Relationships.
ANSWER: C
WHICH OF THE FOLLOWING BEST DESCRIBE MANAGEMENT ELEMENTS?
A) Management elements are the components that comprise the key functions or principles of general management in the organization.
B) Management elements are the project management principles that guide how projects are executed in the organization.
C) Management elements are established by PMOs to guide project implementation.
D) Management elements are influenced by the governance framework, established for effective implementation of projects.
ANSWER: A
COMPLEXITY WITHIN PROJECTS IS A RESULT OF MANY DIFFERENT ORGANIZATIONAL BEHAVIORS; THE DIMENSIONS OF COMPLEXITY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) System behavior.
B) Human behavior.
C) Ambiguity.
D) Process behavior.
ANSWER: D
WHICH OF THE FOLLOWING IS LEAST LIKELY TO BE A PROJECT MANAGER'S ROLE?
A) Evaluation and analysis of project-related activities prior to project initiation.
B) Consulting with business leaders on advancing strategic objectives.
C) Assisting in business analysis, business case development, and aspects of portfolio management for a project.
D) Ensuring that organizations are operating efficiently.
ANSWER: D
WHICH OF THE FOLLOWING IS LEAST LIKELY TO BE WITHIN THE PROJECT MANAGER'S SPHERE OF INFLUENCE?
A) Government.
B) Project team.
C) Sponsors
D) Customers
ANSWER: A
Sequence Activities:
A) Project schedule network diagrams
B) Schedule forecasts
C) Dependency determination and integration
D) Critical path method
ANSWER: A
Define Activities
A) Rolling wave planning
B) Parametric estimating
C) Organizational process assets
D) Team performance assessments
ANSWER: A
One of the tools and techniques used in Project charter is
A) Rolling wave planning
B) Parametric estimating
C) Organizational process assets
D) Team performance assessments
ANSWER: A
WHICH OF THE FOLLOWING IS NOT AN OUTPUT OF THE CONTROL SCOPE PROCESS?
A) Work performance information.
B) Change requests.
C) Project documents updates.
D) Accepted deliverables.
ANSWER: D
Project charter
A) Rolling wave planning
B) Parametric estimating
C) Organizational process assets
D) Team performance assessments
ANSWER: A
The benefit of Sequence Activities is:
A) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
B) The schedule baseline is maintained throughout the project.
C) It determines the monetary resources required for the project.
D) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
ANSWER: A
One of the inputs for Sequence Activities is:
A) Project documents
B) Project charter
C) Expert judgment
D) Individual and team assessments
ANSWER: A
ACCEPTANCE OF WORK RESULTS IS CRUCIAL TO WHAT PHASE OF THE SCOPE MANAGEMENT PROCESS:
A) Initiation
B) Scope planning
C) Scope change control
D) Scope verification
ANSWER: D
Sequence Activities
A) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
B) The schedule baseline is maintained throughout the project.
C) It determines the monetary resources required for the project.
D) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
ANSWER: A
One of the outputs of Sequence Activities is
A) Project schedule network diagrams
B) Schedule forecasts
C) Dependency determination and integration
D) Critical path method
ANSWER: A
WHICH OF THE FOLLOWING PROCESSES IS INCLUDED IN PROJECT INTEGRATION MANAGEMENT?
A) Develop project management plan.
B) Control scope definition.
C) Review scope validation.
D) Conduct procurement surveillance.
ANSWER: A
Sequence Activities
A) Project documents
B) Project charter
C) Expert judgment
D) Individual and team assessments
ANSWER: A
THE FOLLOWING ARE ALL KEY COMPETENCIES OF A PROJECT MANAGER EXCEPT:
A) Technical project management.
B) Operational management.
C) Leadership.
D) Strategic management.
ANSWER: B
THE FOLLOWING ARE ALL KEY DIFFERENCES BETWEEN MANAGEMENT AND LEADERSHIP EXCEPT:
A) Directing vs. influencing.
B) Focus on systems vs. focus on relationships.
C) Accept status quo vs. challenge status quo.
D) Concentrate on project activities vs. emphasis on results.
ANSWER: D
LEADERSHIP AND MANAGEMENT ARE ULTIMATELY ABOUT BEING ABLE TO GET THINGS DONE, AND POWER PLAYS AN IMPORTANT PART. WHICH OF THE FOLLOWING BEST DESCRIBE THE VARIOUS FORMS OF POWER?
A) Positional, referent, personal, cultural, and relational
B) Positional, personal, relational, guilt-based, informational, and expertise.
C) Referent, personal, expertise, and cultural.
D) Positional and pressure-based.
ANSWER: B
PERSONALITY REFERS TO THE INDIVIDUAL DIFFERENCES IN CHARACTERISTIC PATTERNS OF THINKING, FEELING, AND BEHAVING. WHICH OF THE FOLLOWING ARE THE LEAST APPROPRIATE CHARACTERISTICS FOR PROJECT MANAGERS?
A) Authentic, courteous, creative, cultural, and emotional.
B) Intellectual, managerial, political, service-oriented, and social.
C) Authentic, managerial, service-oriented, social, and system.
D) Complexity, courteous, intellectual, cultural, and managerial
ANSWER: D
PROJECT MANAGERS EXHIBIT DIFFERENT LEADERSHIP STYLES. WHICH OF THE FOLLOWING IS NOT A LEADERSHIP STYLE?
A) Laissez-faire.
B) Motivational.
C) Charismatic.
D) Servant.
ANSWER: B
COMPLEXITY EXHIBITS ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) Containing multiple parts.
B) Containing high-risk parts.
C) Exhibiting dynamic interactions between the parts
D) Exhibiting emergent behavior, which cannot be easily explained as the simple sum of parts.
ANSWER: B
PROJECT MANAGERS ARE SIMILAR TO CONDUCTORS OF LARGE ORCHESTRA, EXCEPT:
A) They are responsible for the final result of the team.
B) They communicate with the team.
C) They need to integrate multiple disciplines.
D) They need to be an expert or knowledgeable of all aspects of their endeavor.
ANSWER: D
A CHANGE CONTROL BOARD (CCB) IS:
A) A formally chartered group of stakeholders responsible for ensuring that only a minimal amount of changes occurs on the project.
B) A formal or an informal group of stakeholders that has oversight of project execution.
C) A formally chartered group responsible for reviewing, evaluating, approving, delaying, or rejecting changes to the project, and for recording and communicating such decisions.
D) A dashboard that provides integrated information to help control changes to cost, schedule, and specifications throughout the life of the project
ANSWER: C
SOME OF THE CONFIGURATION MANAGEMENT ACTIVITIES INCLUDED IN THE PERFORM INTEGRATED CHANGE CONTROL PROCESS INCLUDE ALL OF THE FOLLOWING ACTIVITIES EXCEPT:
A) Identification and selection of a configuration item to provide the basis for which the product configuration is defined and verified, products and documents are labeled, changes are managed, and accountability is maintained.
B) Monitoring changes in resource-leveling heuristics to ensure efficient resource utilization throughout the life cycle of the project.
C) Configuration status accounting, in which information is recorded and reported as to when appropriate data about the configuration item should be provided.
D) Configuration verification and configuration audits that ensure that the composition of a projectظآs configuration items is correct and that corresponding changes are registered, assessed, approved, tracked, and correctly implemented.
ANSWER: B
ACTIONS AND ACTIVITIES NECESSARY TO TRANSFER THE PROJECT'S PRODUCTS, SERVICES, OR RESULTS TO THE NEXT PHASE OR TO PRODUCTION AND/OR OPERATIONS ARE ADDRESSED:
A) As part of the Close Project or Phase process.
B) Following the plan outlined in the Quality Management process.
C) As requested by senior executives.
D) As the last step in project management.
ANSWER: A
Estimate Activity Durations:
A) Duration estimates
B) Cost management plan
C) Parametric estimating
D) Leads and lags
ANSWER: A
Sequence Activities
A) Dependency determination and integration
B) Critical path method
C) Procurement documentation
D) Project documents
ANSWER: A
One of the tools and techniques used in Sequence Activities is
A) Dependency determination and integration
B) Critical path method
C) Procurement documentation
D) Project documents
ANSWER: A
Sequence Activities
A) Dependency determination and integration
B) Critical path method
C) Procurement documentation
D) Project documents
ANSWER: A
The benefit of Estimate Activity Durations is:
A) It provides the amount of time each activity will take to complete.
B) It provides guidance and direction on how the project costs will be managed throughout the project.
C) It determines the cost baseline against which project performance can be monitored and controlled.
D) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
ANSWER: A
THREE-POINT ESTIMATING USES:
A) An optimistic, pessimistic, and most likely estimate to calculate the estimate.
B) The weighted average of optimistic, pessimistic, and most likely estimates to calculate the expected duration of the activity.
C) Dummy activities to represent logic links among three or more activities.
D) Free float instead of total float in the schedule calculations.
ANSWER: A
One of the inputs for Estimate Activity Durations is:
A) Organizational process assets
B) Stakeholder management plan
C) Rolling wave planning
D) Critical path method
ANSWER: A
AN ACTIVITY HAS A OPTIMISTIC DURATION ESTIMATE OF 2 DAYS, A MOSTLY LIKELY ESTIMATE OF 5 DAYS, AND A PESSIMISTIC ESTIMATE OF 8 DAYS. WHAT IS THE WEIGHTED AVERAGE DURATION?
A) 4
B) 5
C) 5.2
D) 6
ANSWER: B
Estimate Activity Durations
A) It provides the amount of time each activity will take to complete.
B) It provides guidance and direction on how the project costs will be managed throughout the project.
C) It determines the cost baseline against which project performance can be monitored and controlled.
D) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
ANSWER: A
One of the outputs of Estimate Activity Durations is
A) Duration estimates
B) Cost management plan
C) Parametric estimating
D) Leads and lags
ANSWER: A
ALL OF THE FOLLOWING ARE CHARACTERISTICS OF THE PROJECT CHARTER EXCEPT:
A) It formally authorizes the existence of a project.
B) Projects are initiated by an entity external to the project. The project initiator or sponsor should be at the level that is appropriate to procure funding and commit resources to the project.
C) It is used primarily to request bids for a project or a specific phase of a project.
D) It provides the project manager with the authority to apply organizational resources to project activities.
ANSWER: C
Estimate Activity Durations:
A) Organizational process assets
B) Stakeholder management plan
C) Rolling wave planning
D) Critical path method
ANSWER: A
OUTPUTS OF THE MONITOR AND CONTROL PROJECT WORK PROCESS INCLUDE ALL OF THE FOLLOWING EXCEPT
A) Change requests.
B) Project management plan updates.
C) Work performance reports.
D) Final product, service, or result transition.
ANSWER: D
ALL OF THE FOLLOWING ARE INPUTS TO MANAGE PROJECT KNOWLEDGE EXCEPT:
A) Deliverables
B) Knowledge management.
C) Lessons learned register.
D) Project management plan.
ANSWER: B
ALL OF THE FOLLOWING ARE KNOWLEDGE MANAGEMENT TOOLS AND TECHNIQUES EXCEPT:
A) Discussion forums.
B) Storytelling.
C) Work shadowing and reverse shadowing.
D) Regression analysis.
ANSWER: D
LESSONS LEARNED DOCUMENTATION GENERALLY INCLUDES ALL OF THE FOLLOWING EXCEPT:
A) The causes of issues.
B) Updates of the statement of work to reflect training and learning requirements.
C) Reasoning behind the corrective action chosen.
D) Other types of lessons learned about communications management.
ANSWER: D
ALL OF THE FOLLOWING ARE TRUE ABOUT THE PROJECT SCOPE MANAGEMENT PLAN EXCEPT:
A) It enables the creation of the WBS from the detailed project scope statement.
B) It describes how the scope will be defined, developed, monitored, controlled, and validated.
C) It can be formal or informal, broadly framed or highly detailed, based on the needs of the project.
D) It is not related to the project management plan.
ANSWER: D
COLLECT REQUIREMENTS IS THE PROCESS OF DETERMINING, DOCUMENTING, AND MANAGING STAKEHOLDER NEEDS AND REQUIREMENTS TO MEET PROJECT OBJECTIVES. ALL OF THE FOLLOWING ARE TRUE ABOUT THIS PROCESS EXCEPT:
A) The project's success is directly influenced by active stakeholder involvement in the discovery and decomposition of needs into requirements and by the care taken in determining, documenting,and managing the requirements of the product, service, or result of the project.
B) Requirements become the foundation of the WBS. Cost, schedule, quality planning, and sometimes procurement are all based upon these requirements.
C) The development of requirements begins with an analysis of the information contained in the project charter, the risk register, and the stakeholder engagement plan.
D) Requirements need to be elicited, analyzed, and recorded in enough detail to be included in the scope baseline and to be measured once project execution begins.
ANSWER: C
YOU ARE DEVELOPING A DOCUMENT THAT LINKS PRODUCT REQUIREMENTS FROM THEIR ORIGIN TO THE DELIVERABLES THAT SATISFY THEM TO HELP ENSURE THAT EACH REQUIREMENT ADDS BUSINESS VALUE AND TO MANAGE CHANGES TO THE PRODUCT SCOPE THIS IS KNOWN AS THE:
A) Configuration management system.
B) Business case.
C) New product development matrix.
D) Requirements traceability matrix.
ANSWER: D
AN OUTPUT OF THE DEFINE SCOPE PROCESS IS:
A) Work breakdown structure (WBS).
B) Resource breakdown structure (RBS).
C) Project scope statement.
D) Scope and schedule delays control plan.
ANSWER: C
ALL OF THE FOLLOWING ARE TRUE ABOUT THE PROJECT SCOPE STATEMENT EXCEPT:
A) It is an output of the Validate Scope process.
B) It describes, in detail, the projectظآs deliverables and the work required to create those deliverables.
C) It provides a common understanding of the project scope among project stakeholders.
D) It may contain explicit scope exclusions that can assist in managing stakeholder expectations .
ANSWER: A
The critical path in this network is:
A) A-B-C
B) A-B-D
C) A-C-D
D) A-B-C-D
ANSWER: B
Develop Schedule:
A) Project schedule
B) Basis of estimates
C) Critical path method
D) Decomposition
ANSWER: A
Estimate Activity Durations
A) Parametric estimating
B) Leads and lags
C) Project charter
D) Work performance reports
ANSWER: A
One of the tools and techniques used in Estimate Activity Durations is
A) Parametric estimating
B) Leads and lags
C) Project charter
D) Work performance reports
ANSWER: A
Estimate Activity Durations
A) Parametric estimating
B) Leads and lags
C) Project charter
D) Work performance reports
ANSWER: A
The benefit of Develop Schedule is:
A) It generates a schedule model with planned dates for completing project activities.
B) It determines the monetary resources required for the project.
C) The cost baseline is maintained throughout the project.
D) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
ANSWER: A
THE CRITICAL PATH IN THIS NETWORK IS:
A) A-B-C.
B) A-B-D.
C) A-C-D.
D) A-B-C-D.
ANSWER: B
One of the inputs for Develop Schedule is:
A) Project management plan
B) Verified deliverables
C) Meetings
D) Representations of uncertainty
ANSWER: A
WHICH METHOD DOES NOT USE BOXES OR NODES TO REPRESENT WORK OR ACTIVITIES?
A) PERT
B) PDM
C) ADM
D) GERT
ANSWER: C
Develop Schedule
A) It generates a schedule model with planned dates for completing project activities.
B) It determines the monetary resources required for the project.
C) The cost baseline is maintained throughout the project.
D) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
ANSWER: A
One of the outputs of Develop Schedule is
A) Project schedule
B) Basis of estimates
C) Critical path method
D) Decomposition
ANSWER: A
ALL OF THE FOLLOWING ARE CHARACTERISTICS OF THE PROJECT MANAGEMENT INFORMATION SYSTEM (PMIS) EXCEPT:
A) Automated gathering and reporting on key performance indicators (KPIs) can be part of this system.
B) It provides access to information technology (IT) software tools, such as scheduling software tools, work authorization systems, and configuration management systems.
C) It is used as part of the Direct and Manage Project Work.
D) It is used by the project manager and the project management team primarily to generate presentations to key stakeholders.
ANSWER: D
Develop Schedule:
A) Project management plan
B) Verified deliverables
C) Meetings
D) Representations of uncertainty
ANSWER: A
YOU ARE MANAGING A GLOBAL PROJECT THAT INVOLVES STAKEHOLDERS IN SEVERAL INTERNATION.IL LOCATIONS. YOU ARE LIKELY TO CONSULT THE WBS DICTIONARY TO FIND:
A) The language translation of technical terms used in the project.
B) Detailed deliverable, activity, and scheduling information about each component in the WBS.
C) Information relating the legal constraints of relevant international locations to the development of the WBS.
D) Strengths, weaknesses, opportunities, and threats (SWOT) of key stakeholders and their impact on the WBS.
ANSWER: B
PROJECT INTEGRATION MANAGEMENT INCLUDES ALL OF THE FOLLOWING EXCEPT:
A) Prevention is preferred over inspection. It is better to design quality into deliverables, rather than to find quality issues during inspection. The cost of preventing mistakes is generally much less than the cost of correcting mistakes when they are found by inspection or during usage.
B) Projects and project management are integrative by nature, with most tasks involving more than one Knowledge Area
C) The relationships of processes within and between the Project Management Process Groups are iterative.
D) Managing project performance and changes to the project activities .
ANSWER: C
DESCRIBE CAPABILITIES THAT ARE TEMPORARY AND ARE NO LONGER NEEDED AFTER THE NEW PRODUCT/SERVICE/RESULT IS READY.
A) Business requirements
B) Solution requirements
C) Quality requirements
D) Transition requirements
ANSWER: D
AGILE SCOPE PLANNING IS ESPECIALLY USEFUL WHEN:
A) Solution requirements are emerging all the time.
B) Quality requirements are not stable.
C) Business requirements are not stable.
D) Scope is well understood at the beginning.
ANSWER: C
INPUTS TO THE DEFINE ACTIVITIES PROCESS ARE:
A) Schedule management plan, work breakdown structure, project schedule, and network diagram
B) Project schedule, resource estimates, progress reports, and change requests.
C) Scope management plan, project network diagram, constraints, and assumptions.
D) Schedule management plan, scope baseline, enterprise environmental factors, and organizational process assets.
ANSWER: D
THE PRECEDENCE DIAGRAMMING METHOD (PDM) SHOWS:
A) Various levels of the work breakdown structure.
B) Activities likely to be involved in project integration and resource allocation processes.
C) The logical relationships that exist between activities.
D) The project completion date based on normal resource availability.
ANSWER: C
AS ONE OF THE TOOLS AND TECHNIQUES OF THE SEQUENCE ACTIVITIES PROCESS, A LEAD:
A) Directs a delay in the successor activity.
B) Could be accomplished by a finish-to-start relationship with a delay time.
C) Means that the successor activity cannot start until after the predecessor is completed.
D) Is the amount of time whereby a successor activity can be started before the previous activity is completed.
ANSWER: D
ANALOGOUS DURATION ESTIMATING IS:
A) Frequently used to estimate project duration when there is a limited amount of detailed information about the project.
B) A bottom-up estimating technique.
C) Based on multiple duration estimating.
D) Generally more accurate than other duration estimating methods when expert judgment is used .
ANSWER: A
The free float for activity C is:
A) +4
B) +2
C) 0
D) -2
ANSWER: B
Control Schedule:
A) Schedule forecasts
B) Scope baseline
C) Leads and lags
D) Three-point estimating
ANSWER: A
Develop Schedule
A) Critical path method
B) Decomposition
C) Project charter
D) Verified deliverables
ANSWER: A
One of the tools and techniques used in Develop Schedule is
A) Critical path method
B) Decomposition
C) Project charter
D) Verified deliverables
ANSWER: A
Develop Schedule
A) Critical path method
B) Decomposition
C) Project charter
D) Verified deliverables
ANSWER: A
The benefit of Control Schedule is:
A) The schedule baseline is maintained throughout the project.
B) It determines the cost baseline against which project performance can be monitored and controlled.
C) It provides guidance and direction on how quality will be managed and verified throughout the project.
D) Identifies the type, quantity, and characteristics of resources required to complete the project.
ANSWER: A
THE FREE FLOAT FOR ACTIVITY C IS:
A) A.+4.
B) +2.
C) 0.
D) -2.
ANSWER: B
One of the inputs for Control Schedule is:
A) Project management plan
B) Project funding requirements
C) Expert judgment
D) Strategies for threats
ANSWER: A
A METHOD OF SHORTENING THE DURATION OF THE PROJECT IS:
A) Lead
B) Creating milestones
C) Fast tracking
D) Leveling
ANSWER: D
Control Schedule
A) The schedule baseline is maintained throughout the project.
B) It determines the cost baseline against which project performance can be monitored and controlled.
C) It provides guidance and direction on how quality will be managed and verified throughout the project.
D) Identifies the type, quantity, and characteristics of resources required to complete the project.
ANSWER: A
One of the outputs of Control Schedule is
A) Schedule forecasts
B) Scope baseline
C) Leads and lags
D) Three-point estimating
ANSWER: A
WHICH OF THE FOLLOWING IS NOT TRUE ABOUT TOOLS AND TECHNIQUES OF PERFORM INTEGRATED CHANGE CONTROL?
A) They include expert judgment.
B) They include change control meetings.
C) A change control board (CCB) is responsible for meeting and reviewing the change requests and approving, rejecting, or other disposition of those changes.
D) They include project plan updates.
ANSWER: D
Control Schedule:
A) Project management plan
B) Project funding requirements
C) Expert judgment
D) Strategies for threats
ANSWER: A
CONSIDER THE FOLLOWING THREE ESTIMATES FOR THE DURATION OF AN ACTIVITY:OPTIMISTIC (TO) = 4 WEEKS.MOST LIKELY (TM) = 5 WEEKS.PESSIMISTIC (TP) = 9 WEEKS.┬ب USING THE BETA DISTRIBUTION AND THE THREE- POINT ESTIMATING APPROACH, THE CALCULATED EXPECTED ACTIVITY DURATION (TE) IS:
A) 4.0weeks.
B) 4.5weeks.
C) 5.5weeks.
D) 6.5weeks.
ANSWER: C
1.┬ب┬ب┬ب┬ب┬ب┬ب CONSIDER THE FOLLOWING INFORMATION ABOUT THE DURATION OF AN ACTIVITY:CALCULATED EXPECTED (TE) = 5 WEEKS.OPTIMISTIC (TO) = 4 WEEKS.PESSIMISTIC (TP) = 8 WEEKS. USING THE BETA DISTRIBUTION AND THE THREE- POINT ESTIMATING APPROACH, THE MOST LIKELY (TM) ACTIVITY DURATION IS:
A) A.4.0weeks.
B) B.4.5weeks.
C) C.5.0 weeks.
D) 6.0weeks.
ANSWER: B
1.┬ب┬ب┬ب┬ب┬ب┬ب CONSIDER THE FOLLOWING THREE ESTIMATES FOR THE DURATION OF AN ACTIVITY:Optimistic (tO) = 6 weeks.Most likely (tM) = 9 weeks.Pessimistic (tP) = 15 weeks.┬بUSING THE TRIANGULAR DISTRIBUTION, THE CALCULATED EXPECTED ACTIVITY DURATION (TE) IS:
A) A.10.0weeks.
B) 10.5 weeks.
C) 11.5weeks.
D) D.12.0weeks.
ANSWER: A
AN ACTIVITY IN A PROJECT NETWORK HAS THE FOLLOWING CHARACTERISTICS: ES = 5, EF = 10, AND LF = 14. THEREFORE, LS.=
A) 9.0 weeks.
B) 10.0weeks.
C) 11.0weeks.
D) 12.0weeks.
ANSWER: A
AN ACTIVITY IN A NETWORK HAS THE FOLLOWING CHARACTERISTICS: ES = 12, EF = 22, AND LS 14. ES AND LS RELATE TO THE BEGINNING OF THE WEEK, WHEREAS EF RELATES TO THE END OF THE WEEK. THE DURATION OF THE ACTIVITY IS:
A) 8.0weeks.
B) 11.0weeks.
C) 12.0weeks.
D) 14.0weeks.
ANSWER: B
"CRASHING" IN SCHEDULE MANAGEMENT IS:
A) A schedule compression technique used to shorten the schedule duration for the least incremental cost by adding resources.
B) A schedule compression technique in which phases or activities that are normally done in sequence are performed in parallel.
C) The timely input of data to calculate the critical path
D) Equivalent to minimizing float in the project schedule network.
ANSWER: A
THE CONTROL SCHEDULE PROCESS FOR A PROJECT:
A) Focuses on starting the project earlier than scheduled to help mitigate schedule risk and to achieve the approved schedule baseline.
B) Is the process of monitoring the status of the project to update the project schedule and managing changes to the schedule baseline?
C) Is concerned mainly with activities that are on the critical path.
D) Should focus primarily on activities that are difficult to carry out.
ANSWER: B
1.┬ب┬ب┬ب┬ب┬ب┬ب YOU HAVE BEEN PROMOTED TO THE POSITION OF PROJECT MANAGER FOR A LARGE PROJECT, DUE TO THE ABRUPT TRANSFER OF THE PREVIOUS PROJECT MANAGER. ON THE FIRST DAY IN YOUR NEW, EXCITING POSITION, YOU FIND A FOLDER ON YOUR DESK ENTITLED: EARNED VALUE MANAGEMENT. IN THAT FOLDER, YOU FIND ONLY THE FOLLOWING CHART RELATED TO YOUR PROJECT WITH THE DATA DATE OF A FEW DAYS AGO:┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬ب┬بBASED ON THIS CHART, YOU CONCLUDE THAT:
A) The project is below budget and probably ahead of schedule.
B) The project is over budget and probably behind schedule.
C) The project is below budget but probably behind schedule.
D) The performance on this project compared to budget and schedule cannot be determined because this chart does not show any values.
ANSWER: B
Which is a valid response to negative risks?
A) Exploit
B) Share
C) Enhance
D) Mitigation
ANSWER: D
A resource pool description provides
A) The unit cost for each resource
B) What are the resources are available, at what times and in what patterns
C) Performance of the pool resources
D) Duration of the project
ANSWER: B
Of the following types of contracts - which has the HIGHEST risk for the seller?
A) Cost plus fixed fee - CPFF
B) Time and Material - T and M
C) Firm Fixed Price Contract - FFP
D) Cost plus Incentive fee - CPIF
ANSWER: C
The key benefits of ____________ process is that it will maintain or increase the efficiency and effectiveness of stakeholder engagement activities as the project evolves and environment changes.
A) Plan Stakeholder Management
B) Identify Stakeholders
C) Manage Stakeholder Engagement
D) Control Stakeholder Engagement
ANSWER: D
As a project manager, which scheduling approach will you use for an agile project?
A) Pull based one-demand scheduling (Kanban)
B) Iterative scheduling using a backlog
C) Create the final detailed schedule once and then begin project execution
D) A and B
ANSWER: D
An important output of the Manage Knowledge process is the:
A) Knowledge log
B) Knowledge management plan
C) Lessons learned register
D) Knowledge register
ANSWER: C
A PM has been assigned to manage a project in a foreign country. Which of the following describes the disorientation the PM will likely experience as he gets acclimated to the country?
A) The Sapir-Whorf hypothesis
B) Time dimension
C) Ethnocentrism
D) Culture shock
ANSWER: D
According to EVM, which┬بterm below represents the┬بoutstanding amount of money required to finish the project?
A) Planned Value (PV)
B) Earned Value (EV)
C) Estimate to Complete (ETC)
D) Estimate at Completion (EAC)
ANSWER: C
Project management is
A) The integration of the critical path method and the Earned Value Management system.
B) The application of knowledge, skills, wisdom, science, and art to organizational activities to achieve operational excellence.
C) A subset of most engineering and other technical disciplines.
D) The application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.
ANSWER: D
primary function of a project management office (PMO) is to support project managers in a variety of ways, which may include all of the following EXCEPT
A) Identifying and developing project management methodology, best practices, and standards
B) Intervening in project execution directly and without involving the project manager
C) Managing shared resources across all projects administered by the PMO
D) Coaching, mentoring, training, and oversight
ANSWER: B
You are the project manager of a housing project in which a total of 10 houses are to be build over 10 months (1 house per month). The total budget for the housing project is $1,000,000. The project is now at the end of the 6th month with 5 houses built and $500,000 spent. The project is behind schedule owing to a work strike for a month. The Cost┬بPerformance Index (CPI) for the project is:
A) 1.0
B) 0.9
C) 1.1
D) 1.2
ANSWER: A
The three factors namely management elements, governance frameworks and organizational structures which interact and determine the power, influence, interests, competence and political capabilities of the people in an organization, are together known as
A) The project environment
B) The program environment
C) Company culture
D) An organizational system
ANSWER: D
Examples of documents created in pre-project:
A) Project charter
B) Project charter and stakeholder register
C) Project business case and project benefits management plan
D) Project charter and project management plan
ANSWER: C
The Scope Baseline consists of the following:
A) Approved Project Scope Statement, WBS, WBS Dictionary
B) Preliminary Project Scope Statement, Approved Project Scope Statement, WBS, WBS Dictionary
C) Scope Management Plan, WBS, WBS Dictionary
D) Scope Management Plan, Approved Project Scope Statement, WBS Dictionary
ANSWER: A
You are working in the Project Management Office (PMO) of your organization. Your job responsibility is to:
A) Manage the operational activities in the company
B) Manage human resource and risk management issues for individual projects
C) Provide support functions to project managers in the form of training, providing software, standardizing policies, etc.
D) Provide subject matter expertise in the functional areas of the project
ANSWER: C
Develop Project Management Plan
A) Expert judgment
B) Knowledge management
C) Agreements
D) Enterprise environmental factors
ANSWER: A
One of the tools and techniques used in Direct and Manage Project Work is
A) Expert judgment
B) Knowledge management
C) Agreements
D) Enterprise environmental factors
ANSWER: A
Direct and Manage Project Work
A) Expert judgment
B) Knowledge management
C) Agreements
D) Enterprise environmental factors
ANSWER: A
┬بThe benefit of Develop Project Management Plan is:
A) The production of a comprehensive document that defines the basis of all project work.
B) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
C) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
D) It provides a framework of what has to be delivered.
ANSWER: A
In a kick-off meeting for your project, you provided information to your team members about the different process groups to be followed in the project. According to PMI, which are the project management process groups?
A) Conceptualizing, Initiating, Executing, Monitoring and Controlling, and Closing
B) Initiating, Planning, Executing, Monitoring and Controlling, and Closing
C) Initiating, Verifying, Executing, Monitoring and Controlling, and Closing
D) Initiating, Planning, Executing, Controlling, and Administrative Closure
ANSWER: B
One of the inputs for Develop Project Management Plan is:
A) Project charter
B) Work performance reports
C) Leads and lags
D) Cost aggregation
ANSWER: A
One of the outputs of Develop Project Management Plan is
A) Project management plan
B) Work performance reports
C) Expert judgment
D) Knowledge management
ANSWER: A
In the agreement document of the project, the time schedules and deliverables in each phase are clearly stipulated. From a project management perspective, this is:
A) Risk
B) Assumption
C) Constraint
D) Issue
ANSWER: C
A PROJECT IS A _____________ EFFORT UNDERTAKEN TO CREATE A _____________ PRODUCT OR SERVICE.
A) unique, temporary
B) significant, necessary
C) organized, profitable
D) temporary, unique
ANSWER: D
Develop Project Management Plan
A) The production of a comprehensive document that defines the basis of all project work.
B) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
C) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
D) It provides a framework of what has to be delivered.
ANSWER: A
In the agreement document of the project, the time schedules and deliverables in each phase are clearly stipulated. From a project management perspective, this is:
A) Risk
B) Assumption
C) Constraint
D) Issue
ANSWER: C
Develop Project Management Plan:
A) Project charter
B) Work performance reports
C) Leads and lags
D) Cost aggregation
ANSWER: A
Examples of documents created in pre-project:
A) Project charter
B) Project charter and stakeholder register
C) Project business case and project benefits management plan
D) Project charter and project management plan
ANSWER: C
Develop Project Management Plan:
A) Project management plan
B) Work performance reports
C) Expert judgment
D) Knowledge management
ANSWER: A
The Scope Baseline consists of the following:
A) Approved Project Scope Statement, WBS, WBS Dictionary
B) Preliminary Project Scope Statement, Approved Project Scope Statement, WBS, WBS Dictionary
C) Scope Management Plan, WBS, WBS Dictionary
D) Scope Management Plan, Approved Project Scope Statement, WBS Dictionary
ANSWER: A
ALL OF THE FOLLOWING ARE QUESTIONS THAT THE KEY STAKEHOLDERS AND PROJECT MANAGERS SHOULD ANSWER TO DEVELOP THE PROJECT SUCCESS MEASURES EXCEPT:
A) What does success look like for the project?
B) How will success be measured?
C) What are the communication requirements?
D) What factors may impact success?
ANSWER: C
As a project manager, which scheduling approach will you use for an agile project?
A) Pull based one-demand scheduling (Kanban)
B) Iterative scheduling using a backlog
C) Create the final detailed schedule once and then begin project execution
D) A and B
ANSWER: D
A project has a CPI of 0.7 and an SPI of 1.2. What does this tell us about the project?
A) It is ahead of schedule and over budget
B) It is ahead of schedule and under budget
C) It is behind schedule and over budget
D) It is behind schedule and under budget
ANSWER: A
The Project Quality Management process must __________.
A) Address the quality of the management and product
B) Improve the project management and the quality of the product
C) Ensure that the project satisfies customer requirements
D) All of the above
ANSWER: D
Project management is:
A) The integration of the critical path method and the Earned Value Management system.
B) The application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.
C) The application of knowledge, skills, wisdom, science, and art to organizational activities to achieve operational excellence.
D) A subset of most engineering and other technical disciplines.
ANSWER: B
Plan Cost Management:
A) Cost management plan
B) Cost forecasts
C) Expert judgment
D) Cost aggregation
ANSWER: A
Control Schedule
A) Leads and lags
B) Three-point estimating
C) Project charter
D) Project management plan
ANSWER: A
One of the tools and techniques used in Control Schedule is
A) Leads and lags
B) Three-point estimating
C) Project charter
D) Project management plan
ANSWER: A
Control Schedule
A) Leads and lags
B) Three-point estimating
C) Project charter
D) Project management plan
ANSWER: A
The benefit of Plan Cost Management is:
A) It provides guidance and direction on how the project costs will be managed throughout the project.
B) The cost baseline is maintained throughout the project.
C) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
D) Outlines and guide the selection of resources and assigns them to their respective activities.
ANSWER: A
One of the inputs for Plan Cost Management is:
A) Organizational process assets
B) Project funding requirements
C) Dependency determination and integration
D) Leads and lags
ANSWER: A
WHICH IS A TOOL OR TECHNIQUE OF THE SCHEDULE DEVELOPMENT PROCESS?
A) Resource pool description
B) Supporting detail
C) Duration compression
D) Activity duration estimates
ANSWER: C
Plan Cost Management
A) It provides guidance and direction on how the project costs will be managed throughout the project.
B) The cost baseline is maintained throughout the project.
C) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
D) Outlines and guide the selection of resources and assigns them to their respective activities.
ANSWER: A
One of the outputs of Plan Cost Management is
A) Cost management plan
B) Cost forecasts
C) Expert judgment
D) Cost aggregation
ANSWER: A
YOU ARE MANAGING A $10 MILLION PROJECT. WHICH OF THE FOLLOWING IS AN ACCEPTABLE CAUSE FOR "RE-BASELINING" THIS PROJECT?
A) The client has approved an addition to the scope of the project with a $150,000 budget increase and a two-week extension of the scheduled completion.
B) The contractorظآs company has instituted a quality assurance program in which it has pledged to spend $1 million during the next year.
C) The productivity in the design department is lower than estimated, which has resulted in 1,000 additional hours over what was budgeted and a forecasted two-week delay of the scheduled completion.
D) The engineering department of the performing organization has converted to a new $250,000 CAD system.
ANSWER: B
Plan Cost Management:
A) Organizational process assets
B) Project funding requirements
C) Dependency determination and integration
D) Leads and lags
ANSWER: A
Estimate Costs:
A) Basis of estimates
B) Quality management plan
C) Three-point estimating
D) To-complete performance index
ANSWER: A
Estimate Costs
A) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
B) It determines the monetary resources required for the project.
C) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
D) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
ANSWER: B
Plan Cost Management
A) Expert judgment
B) Cost aggregation
C) Project charter
D) Procurement documentation
ANSWER: A
One of the tools and techniques used in Plan Cost Management is
A) Expert judgment
B) Project charter
C) Procurement documentation
D) Project documents
ANSWER: A
Plan Cost Management
A) Expert judgment
B) Project charter
C) Procurement documentation
D) Project documents
ANSWER: A
One of the inputs for Estimate Costs is:
A) Enterprise environmental factors
B) Work performance data
C) Decision making
D) Rolling wave planning
ANSWER: A
WHICH TYPE OF COST ESTIMATE IS BASED ON INDIVIDUAL ACTIVITIES?
A) Top-down
B) Parametric
C) Bottom-up
D) Analogous
ANSWER: C
One of the outputs of Estimate Costs is
A) Basis of estimates
B) Quality management plan
C) Three-point estimating
D) To-complete performance index
ANSWER: A
The benefit of Estimate Costs is:
A) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
B) It determines the monetary resources required for the project.
C) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
D) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
ANSWER: B
WHICH OF THE FOLLOWING STATEMENTS IS TRUE ABOUT THE WORK BREAKDOWN STRUCTURE (WBS)?
A) The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables.
B) The WBS is a simple list of project activities in chart form.
C) The WBS is the same as the organizational breakdown structure (OBS ).
D) The WBS is the bill of materials (BOM) needed to accomplish the project objectives and create the required deliverables.
ANSWER: A
Estimate Costs:
A) Enterprise environmental factors
B) Work performance data
C) Decision making
D) Rolling wave planning
ANSWER: A
Determine Budget:
A) Agreements
B) Approved change requests
C) Decision making
D) Alternatives analysis
ANSWER: A
Determine Budget:
A) Cost baseline
B) Test and evaluation documents
C) Cost aggregation
D) Test and inspection planning
ANSWER: A
Determine Budget
A) It determines the cost baseline against which project performance can be monitored and controlled.
B) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
C) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
D) Influences team behavior, manages conflict, and resolves issues.
ANSWER: A
One of the tools and techniques used in Estimate Costs is
A) Three-point estimating
B) To-complete performance index
C) Project charter
D) Project documents
ANSWER: A
Estimate Costs
A) Three-point estimating
B) To-complete performance index
C) Project charter
D) Project documents
ANSWER: A
One of the inputs for Determine Budget is:
A) Agreements
B) Approved change requests
C) Decision making
D) Alternatives analysis
ANSWER: A
USING THE CHART BELOW, WHAT IS THE COST VARIANCE?PVEVAC$10,000$12,000$15,000
A) US $ 3,000
B) US $ 5,000
C) US $ 3,000
D) US $ 2,000
ANSWER: A
One of the outputs of Determine Budget is
A) Cost baseline
B) Test and evaluation documents
C) Cost aggregation
D) Test and inspection planning
ANSWER: A
The benefit of Determine Budget is:
A) It determines the cost baseline against which project performance can be monitored and controlled.
B) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
C) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
D) Influences team behavior, manages conflict, and resolves issues.
ANSWER: A
THE FOLLOWING IS AN EXAMPLE OF A CONSTRAINT ASSOCIATED WITH THE PROJECT SCOPE THAT LIMITS THE TEAM'S OPTIONS IN SCOPE DEFINITION:
A) A predefined budget or any imposed dates or schedule milestones that are issued by the customer or performing organization.
B) The threat of a strike by a subcontractor.
C) Existing relationships with sellers, suppliers, or others in the supply chain.
D) The method used to measure project performance.
ANSWER: A
AN INPUT TO THE DEFINE SCOPE PROCESS IS:
A) The type of contract detail language.
B) Project charter.
C) Work breakdown structure (WBS).
D) Decomposition.
ANSWER: B
Control Costs:
A) Project funding requirements
B) Approved change requests
C) Communication methods
D) Meetings
ANSWER: A
Control Costs:
A) Cost forecasts
B) Verified deliverables
C) To-complete performance index
D) Audits
ANSWER: A
Control Costs
A) The cost baseline is maintained throughout the project.
B) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
C) Identifies the type, quantity, and characteristics of resources required to complete the project.
D) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
ANSWER: A
Determine Budget
A) Cost aggregation
B) Test and inspection planning
C) Project charter
D) Project documents
ANSWER: A
One of the tools and techniques used in Determine Budget is
A) Cost aggregation
B) Test and inspection planning
C) Project charter
D) Project documents
ANSWER: A
Determine Budget
A) Cost aggregation
B) Test and inspection planning
C) Project charter
D) Project documents
ANSWER: A
One of the inputs for Control Costs is:
A) Project funding requirements
B) Approved change requests
C) Communication methods
D) Meetings
ANSWER: A
WHICH IS NOT A PART OF THE COST BUDGETING PROCESS?
A) Project schedule
B) Cost estimates
C) Resource requirements
D) WBS
ANSWER: C
One of the outputs of Control Costs is
A) Cost forecasts
B) Verified deliverables
C) To-complete performance index
D) Audits
ANSWER: A
The benefit of Control Costs is:
A) The cost baseline is maintained throughout the project.
B) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
C) Identifies the type, quantity, and characteristics of resources required to complete the project.
D) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
ANSWER: A
WHAT IS THE WBS TYPICALLY USED FOR?
A) To organize and define the total scope of the project.
B) To identify the logical person to be project sponsor.
C) To define the level of reporting that the seller provides the buyer.
D) As a record of when work elements are assigned to individuals.
ANSWER: A
Plan Quality Management:
A) Project charter
B) Project funding requirements
C) Three-point estimating
D) Test and inspection planning
ANSWER: A
Plan Quality Management:
A) Quality management plan
B) Resource management plan
C) Test and inspection planning
D) Inspection
ANSWER: A
Plan Quality Management
A) It provides guidance and direction on how quality will be managed and verified throughout the project.
B) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
C) Outlines and guide the selection of resources and assigns them to their respective activities.
D) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
ANSWER: A
Control Costs
A) To-complete performance index
B) Audits
C) Project charter
D) Agreements
ANSWER: A
One of the tools and techniques used in Control Costs is
A) To-complete performance index
B) Audits
C) Project charter
D) Agreements
ANSWER: A
Control Costs
A) To-complete performance index
B) Audits
C) Project charter
D) Agreements
ANSWER: A
One of the inputs for Plan Quality Management is:
A) Project charter
B) Project funding requirements
C) Three-point estimating
D) Test and inspection planning
ANSWER: A
COST ESTIMATING IS:
A) Assessing how much the organization will charge for the product or service
B) Assessing how much it will cost the organization to provide the product or service
C) Establishing a baseline to use in measuring project performance
D) Analyzing positive and negative variances
ANSWER: B
One of the outputs of Plan Quality Management is
A) Quality management plan
B) Resource management plan
C) Test and inspection planning
D) Inspection
ANSWER: A
The benefit of Plan Quality Management is:
A) It provides guidance and direction on how quality will be managed and verified throughout the project.
B) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
C) Outlines and guide the selection of resources and assigns them to their respective activities.
D) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
ANSWER: A
The benefit of Manage Quality is:
A) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
B) Identifies the type, quantity, and characteristics of resources required to complete the project.
C) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
D) Enables an efficient and effective information flow between the project team and the stakeholders.
ANSWER: A
THE FOLLOWING IS TRUE ABOUT THE WBS:
A) The WBS is another term for the bar (Gantt) chart.
B) Each descending level of the WBS represents an increasingly detailed definition of the project work.
C) Work not in the WBS is usually defined in the scope statement of the project.
D) The WBS shows only the critical path activities.
ANSWER: B
Manage Quality:
A) Project management plan
B) Work performance data
C) Risk categorization
D) Project management information system
ANSWER: A
Manage Quality:
A) Test and evaluation documents
B) Resource breakdown structure
C) Audits
D) Critical path method
ANSWER: A
Manage Quality
A) It increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
B) Identifies the type, quantity, and characteristics of resources required to complete the project.
C) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
D) Enables an efficient and effective information flow between the project team and the stakeholders.
ANSWER: A
Plan Quality Management
A) Test and inspection planning
B) Inspection
C) Project documents
D) Organizational process assets
ANSWER: A
One of the tools and techniques used in Plan Quality Management is
A) Test and inspection planning
B) Inspection
C) Project documents
D) Organizational process assets
ANSWER: A
Plan Quality Management
A) Test and inspection planning
B) Inspection
C) Project documents
D) Organizational process assets
ANSWER: A
One of the inputs for Manage Quality is:
A) Project management plan
B) Work performance data
C) Risk categorization
D) Project management information system
ANSWER: A
EARNED VALUE IS:
A) The amount future value of a present investment
B) The actual hours worked on the project multiplied by the budgeted labor rate
C) Budgeted value of work actually accomplished
D) PV-AC
ANSWER: C
One of the outputs of Manage Quality is
A) Test and evaluation documents
B) Resource breakdown structure
C) Audits
D) Critical path method
ANSWER: A
Which of the following Is true? about the Validate Scope process?
A) It is the process of formalizing acceptance of the completed project deliverables.
B) It is not necessary if the project completes on time and within budget.
C) It occurs primarily when revisions or changes are made to project scope.
D) Scope validation is primarily concerned with correctness of the deliverables, whereas quality control is primarily concerned with acceptance of the deliverables and meeting the quality requirements specified for the deliverables.
ANSWER: A
The benefit of Control Quality is:
A) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
B) Outlines and guide the selection of resources and assigns them to their respective activities.
C) Influences team behavior, manages conflict, and resolves issues.
D) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
ANSWER: A
Control Quality:
A) Approved change requests:
B) Work performance reports
C) Alternatives analysis
D) Decomposition
ANSWER: A
Control Quality:
A) Verified deliverables
B) Resource calendars
C) Inspection
D) Analogous estimating
ANSWER: A
Control Quality
A) Verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance.
B) Outlines and guide the selection of resources and assigns them to their respective activities.
C) Influences team behavior, manages conflict, and resolves issues.
D) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
ANSWER: A
Manage Quality
A) Audits
B) Critical path method
C) Project documents
D) Organizational process assets
ANSWER: A
One of the tools and techniques used in Manage Quality is
A) Audits
B) Critical path method
C) Project documents
D) Organizational process assets
ANSWER: A
Manage Quality
A) Audits
B) Critical path method
C) Project documents
D) Organizational process assets
ANSWER: A
One of the inputs for Control Quality is:
A) Approved change requests:
B) Work performance reports
C) Alternatives analysis
D) Decomposition
ANSWER: A
THE FUTURE VALUE OF $3000 INVESTED FOR 5 YEARS AT 12 INTEREST IS:
A) US $ 4,982.00
B) US $ 4,702.00
C) US $ 5,287.00
D) US $ 5,394.00
ANSWER: C
One of the outputs of Control Quality is
A) Verified deliverables
B) Resource calendars
C) Inspection
D) Analogous estimating
ANSWER: A
IN ROLLING WAVE PLANNING:
A) Focus is maintained on long-term objectives, allowing near-term objectives to be rolled out as part of the ongoing wave of activities.
B) The work to be accomplished in the near term is planned in detail, whereas the work in the future is planned at a higher level.
C) The work far in the future is planned in detail for work packages that are at a low level of the WBS.
D) A wave of detailed activities is planned during strategic planning to ensure that WBS deliverables and project milestones are achieved.
ANSWER: B
Plan Resource Management:
A) Organizational process assets
B) Team performance assessments
C) Parametric estimating
D) Expert judgment
ANSWER: A
The benefit of Plan Resource Management is:
A) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
B) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
C) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
D) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
ANSWER: A
Plan Resource Management:
A) Resource management plan
B) Team performance assessments
C) Expert judgment
D) Virtual teams
ANSWER: A
Plan Resource Management
A) Establishes the approach and level of management effort needed for managing project resources based on the type and complexity of the project.
B) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
C) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
D) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
ANSWER: A
Control Quality
A) Inspection
B) Analogous estimating
C) Project documents
D) Project charter
ANSWER: A
One of the tools and techniques used in Control Quality is
A) Inspection
B) Analogous estimating
C) Project documents
D) Project charter
ANSWER: A
Control Quality
A) Inspection
B) Analogous estimating
C) Project documents
D) Project charter
ANSWER: A
One of the inputs for Plan Resource Management is:
A) Organizational process assets
B) Team performance assessments
C) Parametric estimating
D) Expert judgment
ANSWER: A
WHICH OF THE FOLLOWING IS NOT PART OF THE QUALITY ASSURANCE PROCESS?
A) Operational definitions
B) Quality policy
C) Quality audits
D) Quality improvement
ANSWER: B
One of the outputs of Plan Resource Management is
A) Resource management plan
B) Team performance assessments
C) Expert judgment
D) Virtual teams
ANSWER: A
THE DURATION OF THE ACTIVITY IS AFFECTED BY ALL OF THE FOLLOWING EXCEPT:
A) The estimated activity resource requirements
B) The types of resources assigned to the activity
C) The availability of the resources assigned to the activity.
D) Using the precedence diagramming method (PDM) for scheduling activities instead of using the critical path method (CPM).
ANSWER: D
Estimate Activity Resources:
A) Project management plan
B) Project charter
C) Representations of uncertainty
D) Data analysis
ANSWER: A
The benefit of Estimate Activity Resources is:
A) Identifies the type, quantity, and characteristics of resources required to complete the project.
B) Influences team behavior, manages conflict, and resolves issues.
C) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
D) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
ANSWER: A
Estimate Activity Resources:
A) Resource breakdown structure
B) Project charter
C) Analogous estimating
D) Individual and team assessments
ANSWER: A
Estimate Activity Resources
A) Identifies the type, quantity, and characteristics of resources required to complete the project.
B) Influences team behavior, manages conflict, and resolves issues.
C) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
D) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
ANSWER: A
Plan Resource Management
A) Expert judgment
B) Virtual teams
C) Project documents
D) Work performance data
ANSWER: A
One of the tools and techniques used in Plan Resource Management is
A) Expert judgment
B) Project documents
C) Work performance data
D) Virtual teams
ANSWER: A
Plan Resource Management
A) Expert judgment
B) Project documents
C) Work performance data
D) Virtual teams
ANSWER: A
One of the inputs for Estimate Activity Resources is:
A) Project management plan
B) Project charter
C) Representations of uncertainty
D) Data analysis
ANSWER: A
A PACKING PROCESS RESULTS A PRODUCT WITH A MEAN WEIGHT OF 8 OUNCES. THE PROCESS HAS A STANDARD DEVIATION OF 0.5 OUNCE. WHAT PERCENTAGE OF SAMPLES WILL WEIGH BETWEEN 7.5 AND 8 OUNCES?
A) 31.74
B) 34.13
C) 68.26
D) 95.46
ANSWER: B
One of the outputs of Estimate Activity Resources is
A) Resource breakdown structure
B) Project charter
C) Analogous estimating
D) Individual and team assessments
ANSWER: A
A SCHEDULE COMPRESSION TECHNIQUE USED TO SHORTEN THE SCHEDULE DURATION FOR THE LEAST INCREMENTAL COST BY ADDING RESOURCES IS CALLED:
A) Crashing.
B) Program evaluation and review technique (PFRT).
C) Precedence diagramming method (PDM).
D) Fast tracking.
ANSWER: A
Acquire Resources:
A) Project documents
B) Project charter
C) Analogous estimating
D) Interpersonal and team skills
ANSWER: A
The benefit of Acquire Resources is:
A) Outlines and guide the selection of resources and assigns them to their respective activities.
B) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
C) Enables an efficient and effective information flow between the project team and the stakeholders.
D) Focuses efforts on high-priority risks.
ANSWER: A
Acquire Resources:
A) Resource calendars
B) Project charter
C) Virtual teams
D) Decomposition
ANSWER: A
Acquire Resources
A) Outlines and guide the selection of resources and assigns them to their respective activities.
B) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
C) Enables an efficient and effective information flow between the project team and the stakeholders.
D) Focuses efforts on high-priority risks.
ANSWER: A
Estimate Activity Resources
A) Analogous estimating
B) Individual and team assessments
C) Project documents
D) Project management plan
ANSWER: A
one of the tools and techniques used in Estimate Activity Resources is
A) Analogous estimating
B) Individual and team assessments
C) Project documents
D) Project management plan
ANSWER: A
Estimate Activity Resources
A) Analogous estimating
B) Individual and team assessments
C) Project documents
D) Project management plan
ANSWER: A
One of the inputs for Acquire Resources is:
A) Project documents
B) Project charter
C) Analogous estimating
D) Interpersonal and team skills
ANSWER: A
WHICH OF THE FOLLOWING IS A PRIMARY MOTIVATIONAL TOOL OF MCGREGORظآS THEORY X?
A) Trust
B) Safety
C) Self Esteem
D) Self Actualization
ANSWER: B
One of the outputs of Acquire Resources is
A) Resource calendars
B) Project charter
C) Virtual teams
D) Decomposition
ANSWER: A
The key processes of Project Risk Management are:
A) Plan Risk Management. Identify Risks. Assess Risks, Mitigate Risks, Transfer Risks, and Document Outcomes
B) Identify Risks. Plan Risk Management. Evaluate Risks. Develop Risk Responses, Mitigate Risks, and Document Results
C) Identify Risks. Perform Qualitative Risk Validation, Perform Quantitative Impact Assessment, Develop Risk Response Strategies. Document Response Strategies, and Monitor Risk Responses
D) Plan Risk Management. Identify Risks. Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis. Plan Risk Responses, Implement Risk Responses, and Monitor Risks
ANSWER: D
Plan Resource Management should generally include all of the following EXCEPT
A) Roles and responsibilities
B) Identification of resources
C) Acquiring resources
D) Project interfaces
ANSWER: D
The purpose of a contract is to distribute a reasonable amount of _________ between the buyer and seller.
A) Risk
B) Responsibility
C) Reward
D) None
ANSWER: A
Stakeholder classification done in __________ process.
A) Identify Stakeholders
B) Plan Stakeholder Management
C) Manage Stakeholder Engagement
D) Control Stakeholder Engagement
ANSWER: A
An activity is most likely expected to take 7 days. The maximum duration is expected to be 10 days and the minimum 5 days. Calculate the expected duration for this activity.
A) 7.16 days
B) 12.1 days
C) 15.4 days
D) 17 days
ANSWER: A
The project management plan includes which of the following:
A) Project charter and project documents
B) Subsidiary plans, baselines and additional components
C) Project reports and project documents
D) Project baselines and project documents
ANSWER: B
A project with both Schedule Performance Index (SPI) and Cost Performance Index (CPI) of 0.80. The project is currently:
A) Ahead of schedule and under budget
B) Behind schedule and under budget
C) Ahead of schedule and over budget
D) Behind schedule and over budget
ANSWER: D
Which of the following is NOT a characteristic of a project.
A) Constrained by limited resources
B) Planned, executed, and controlled
C) Creates a unique product or service
D) Ongoing and repetitive
ANSWER: D
In which of the following organizational structure types is the project manager's role full time
A) Balanced matrix
B) Multi-divisional
C) Project-oriented
D) Functional
ANSWER: C
Project managers exhibit different leadership styles. Which of the following is NOT a leadership styl
A) Laissez-faire
B) Motivational
C) Charismatic
D) Servant
ANSWER: B
Which of the following is not a core value per PMIظآs Code of Ethics and Professional Conduct?
A) Trust
B) Responsibility
C) Honesty
D) Fairness
ANSWER: A
Which of the below statement(s) is/are correct with respect to the Validate Scope process?
A) Accepted deliverables are inputs, verified deliverables are outputs
B) Deliverables are inputs, verified deliverables are outputs
C) Verified deliverables are inputs, accepted deliverables are outputs
D) Deliverables are inputs, accepted deliverables are outputs
ANSWER: C
In a job interview, you are asked to define the most important characteristic of a project manager. Which of the following will be the best answer?
A) Subject matter expert
B) Integrator
C) Creative person
D) Risk minimizer
ANSWER: B
Direct and Manage Project Work
A) Meetings
B) Agreements
C) Decomposition
D) Approved change requests
ANSWER: A
One of the tools and techniques used in Direct and Manage Project Work is
A) Meetings
B) Decomposition
C) Agreements
D) Approved change requests
ANSWER: A
Direct and Manage Project Work
A) Meetings
B) Decomposition
C) Agreements
D) Approved change requests
ANSWER: A
The benefit of Direct and Manage Project Work is:
A) It provides overall management of the project work and deliverables, thus improving the probability of project success.
B) It allows for documented changes of the overall project objectives or plans.
C) It provides guidance and direction on how scope will be managed throughout the project.
D) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
ANSWER: A
As a project manager for a construction company, you are responsible to Define Scope, Define Activities, Develop Schedule, and Determine Budget. These responsibilities are performed as part of:
A) Closing
B) Initiating
C) Planning
D) Monitoring and Controlling
ANSWER: C
One of the inputs for Direct and Manage Project Work: is
A) Approved change requests
B) Accepted deliverables
C) Meetings
D) Data analysis
ANSWER: A
One of the outputs of Direct and Manage Project Work is
A) Deliverables
B) Approved change requests
C) Meetings
D) Decomposition
ANSWER: A
In a job interview, you are asked to define the most important characteristic of a project manager. Which of the following will be the best answer?
A) Subject matter expert
B) Integrator
C) Creative person
D) Risk minimizer
ANSWER: B
POSSIBLE SOCIOECONOMIC INFLUENCES ON THE PROJECT INCLUDE:
A) Budgetary considerations
B) Internationalization
C) Activity based costing
D) Matrix organization
ANSWER: A
Direct and Manage Project Work
A) It provides overall management of the project work and deliverables, thus improving the probability of project success.
B) It allows for documented changes of the overall project objectives or plans.
C) It provides guidance and direction on how scope will be managed throughout the project.
D) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
ANSWER: A
In a job interview, you are asked to define the most important characteristic of a project manager. Which of the following will be the best answer?
A) Subject matter expert
B) Integrator
C) Creative person
D) Risk minimizer
ANSWER: B
Direct and Manage Project Work:
A) Approved change requests
B) Accepted deliverables
C) Meetings
D) Data analysis
ANSWER: A
Direct and Manage Project Work:
A) Deliverables
B) Approved change requests
C) Meetings
D) Decomposition
ANSWER: A
Which of the below statement(s) is/are correct with respect to the Validate Scope process?
A) Accepted deliverables are inputs, verified deliverables are outputs
B) Deliverables are inputs, verified deliverables are outputs
C) Verified deliverables are inputs, accepted deliverables are outputs
D) Deliverables are inputs, accepted deliverables are outputs
ANSWER: C
PORTFOLIO MANAGEMENT REFERS TO:
A) Managing various contents of the project file.
B) Managing the levels of the levels of financial authority to facilitate
C) project decision making
D) The centralized management of one or more portfolios to achieve strategic objectives.
E) Applying resource leveling heuristics across all the organizationظآs strategic objectives.
ANSWER: C
A PROGRAM IS A:
A) Group of related tasks lasting one year or less.
B) Group of related projects, subsidiary programs, and program activities managed in a coordinated manner.
C) Large projects with significant cost and resource requirements.
D) Sequence of activities constituting a major project.
ANSWER: B
An activity is most likely expected to take 7 days. The maximum duration is expected to be 10 days and the minimum 5 days. Calculate the expected duration for this activity.
A) 7.16 days
B) 12.1 days
C) 15.4 days
D) 17 days
ANSWER: A
A 10 km long rail track is estimated to cost $5000 based on verified historical data. Based on this information, it is estimated that 1500 km of rail track would cost $750000. Which estimation technique has been applied here?
A) Analogous estimating
B) Parametric estimating
C) 3-point estimating (PERT technique)
D) Bottom-up estimating
ANSWER: B
As a project manager - you are expected to calculate the cost of Poor Quality - the project work is in progress - what costs would you consider?
A) Cost of Hiring.
B) Prevention costs.
C) Appraisal costs.
D) External and Internal Failure costs
ANSWER: D
THE "FAST TRACKING" METHOD OF SCHEDULE COMPRESSION INVOLVES:
A) The use of industrial engineering techniques to improve productivity, thereby finishing the project earlier than originally planned.
B) Performing in parallel for at least a portion of their duration activities or phases that are normally done in sequence, which may result in rework and increased risk.
C) Going on a ظ£mandatory overtime scheduleظإ to complete the project on schedule or earlier if possible.
D) Assigning ظ£dedicated teamsظإ to critical path activities to achieve project schedule objectives.
ANSWER: B
Develop Team:
A) Project management plan
B) Work performance reports
C) Strategies for threats
D) Source selection analysis
ANSWER: A
The benefit of Develop Team is:
A) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
B) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
C) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
D) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
ANSWER: A
Develop Team
A) Team performance assessments
B) Communications management plan
C) Individual and team assessments
D) Problem solving
ANSWER: A
Develop Team
A) Results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance.
B) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
C) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
D) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
ANSWER: A
Acquire Resources
A) Virtual teams
B) Decomposition
C) Project documents
D) Agreements
ANSWER: A
One of the tools and techniques used inAcquire Resources is
A) Virtual teams
B) Project documents
C) Agreements
D) Project charter
ANSWER: A
Acquire Resources
A) Virtual teams
B) Project documents
C) Agreements
D) Project charter
ANSWER: A
One of the inputs for Develop Team is:
A) Project management plan
B) Work performance reports
C) Strategies for threats
D) Source selection analysis
ANSWER: A
WHICH OF THE FOLLOWING IS NOT PART OF A MODERN QUALITY MANAGEMENT CONCEPT?
A) Performance standard is zero defects
B) Quality must be inspected in
C) 85% of failures occur because of the process, not the worker
D) Quality is a 4 cycle process ظô plan/do/check/act
ANSWER: B
One of the outputs of Develop Team is
A) Team performance assessments
B) Communications management plan
C) Individual and team assessments
D) Problem solving
ANSWER: A
AN EXAMPLE OF A MANDATORY DEPENDENCY IS:
A) A dependency established based on knowledge of best practices within a particular application area.
B) A dependency established based on some unusual aspect of the project where a specific sequence is desired.
C) On a construction project, to erect the superstructure only after the foundation has been built.
D) On a software development project, to start design only after completion and approval of all project requirements.
ANSWER: C
Manage Team:
A) Team performance assessments
B) Work performance data
C) Inspection
D) Communication skills
ANSWER: A
The benefit of Manage Team is:
A) Influences team behavior, manages conflict, and resolves issues.
B) Enables an efficient and effective information flow between the project team and the stakeholders.
C) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
D) Identifies appropriate ways to address overall project risk and individual project risks.
ANSWER: A
Manage Team:
A) Project documents updates
B) Project communications
C) Interpersonal and team skills
D) Communication methods
ANSWER: A
Manage Team
A) Influences team behavior, manages conflict, and resolves issues.
B) Enables an efficient and effective information flow between the project team and the stakeholders.
C) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
D) Identifies appropriate ways to address overall project risk and individual project risks.
ANSWER: A
Develop Team
A) Individual and team assessments
B) Project management information system
C) Project documents
D) Project charter
ANSWER: A
One of the tools and techniques used in Develop Team is
A) Individual and team assessments
B) Project management information system
C) Project documents
D) Project charter
ANSWER: A
Develop Team
A) Individual and team assessments
B) Project management information system
C) Project documents
D) Project charter
ANSWER: A
One of the inputs for Manage Team is:
A) Team performance assessments
B) Work performance data
C) Inspection
D) Communication skills
ANSWER: A
WHICH OF THE FOLLOWING IS NOT A CONSIDERED A FAILURE COST?
A) Rework
B) Training
C) Rejects
D) Scrap
ANSWER: B
One of the outputs of Manage Team is
A) Project documents updates
B) Project communications
C) Interpersonal and team skills
D) Communication methods
ANSWER: A
PROJECT COST MANAGEMENT INCLUDES ALL OF THE FOLLOWING PROCESSES EXCEPT:
A) Plan cost management.
B) Level resources.
C) Determine budget.
D) Control costs.
ANSWER: B
Control Resources:
A) Risk register
B) Project charter
C) Bidder conferences
D) Meetings
ANSWER: A
The benefit of Control Resources is:
A) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
B) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
C) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
D) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
ANSWER: A
Control Resources
A) Project management plan updates
B) Work performance data
C) Problem solving
D) Project reporting
ANSWER: A
Control Resources
A) Ensures that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed.
B) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
C) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
D) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
ANSWER: A
One of the tools and techniques used in Manage Team is
A) Interpersonal and team skills
B) Project funding requirements
C) Organizational process assets
D) Communication methods
ANSWER: A
Manage Team
A) Interpersonal and team skills
B) Project funding requirements
C) Organizational process assets
D) Communication methods
ANSWER: A
One of the inputs for Control Resources is:
A) Risk register
B) Project charter
C) Bidder conferences
D) Meetings
ANSWER: A
A PERSON WHO IS ATTEMPTING TO FULFILL THE NEED FOR SAFETY HAS ALREADY SATISFIED WHICH NEEDS?
A) Esteem
B) Self-Actualization
C) Physiological
D) Social
ANSWER: C
One of the outputs of Control Resources is
A) Project management plan updates
B) Work performance data
C) Problem solving
D) Project reporting
ANSWER: A
THE COST MANAGEMENT PLAN HAS ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) It is based on project cost estimates and is separate from the project management plan.
B) It may specify variance thresholds for monitoring cost performance to indicate an agreed-upon amount of variation to be allowed before some action needs to be taken.
C) It may specify the level of precision, which is the degree to which activity cost estimates will be rounded up or down.
D) It describes how the project costs will be planned, structured, and controlled.
ANSWER: A
Plan Communications Management:
A) Project charter
B) Procurement documentation
C) Cost aggregation
D) Audits
ANSWER: A
The benefit of Plan Communications Management is:
A) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
B) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
C) Focuses efforts on high-priority risks.
D) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
ANSWER: A
Plan Communications Management
A) Communications management plan
B) Risk management plan
C) Communication methods
D) Project management information system
ANSWER: A
Plan Communications Management
A) Provides a documented approach to effectively and efficiently engage stakeholders by presenting relevant information in a timely manner.
B) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
C) Focuses efforts on high-priority risks.
D) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
ANSWER: A
Control Resources
A) Problem solving
B) Risk categorization
C) Project management plan
D) Stakeholder management plan
ANSWER: A
One of the tools and techniques used in Control Resources is
A) Problem solving
B) Risk categorization
C) Project management plan
D) Stakeholder management plan
ANSWER: A
Control Resources
A) Problem solving
B) Risk categorization
C) Project management plan
D) Stakeholder management plan
ANSWER: A
One of the inputs for Plan Communications Management is:
A) Project charter
B) Procurement documentation
C) Cost aggregation
D) Audits
ANSWER: A
WHICH OF THE FOLLOWING IS AN INPUT TO THE TEAM DEVELOPMENT PROCESS?
A) General management skills
B) Inputs to performance appraisals
C) Staffing pool description
D) External feedback
ANSWER: D
One of the outputs of Plan Communications Management is
A) Communications management plan
B) Risk management plan
C) Communication methods
D) Project management information system
ANSWER: A
WHICH OF THE FOLLOWING REPRESENTS PROCESSES CONCERNED WITH ESTABLISHING AND CONTROLLING THE COST BASELINE?
A) Plan Resource Management and Control Costs
B) Estimate Costs, Develop Budget, and Adhere to Baseline.
C) Determine Budget and Control Costs.
D) Plan Resource Management, Cost Estimating, and Cost Control.
ANSWER: C
Manage Communications:
A) Work performance reports
B) Procurement documentation
C) Expert judgment
D) Decision making
ANSWER: A
The benefit of Manage Communications is:
A) Enables an efficient and effective information flow between the project team and the stakeholders.
B) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
C) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
D) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
ANSWER: A
Manage Communications:
A) Project communications
B) Work performance data
C) Project reporting
D) Decomposition
ANSWER: A
Manage Communications
A) Enables an efficient and effective information flow between the project team and the stakeholders.
B) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
C) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
D) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
ANSWER: A
Plan Communications Management
A) Communication methods
B) Project management information system
C) Project management plan
D) Stakeholder management plan
ANSWER: A
One of the tools and techniques used in Control Resources is
A) Problem solving
B) Project management plan
C) Stakeholder management plan
D) Risk categorization
ANSWER: A
Control Resources
A) Problem solving
B) Project management plan
C) Stakeholder management plan
D) Risk categorization
ANSWER: A
One of the inputs for Manage Communications is:
A) Work performance reports
B) Procurement documentation
C) Expert judgment
D) Decision making
ANSWER: A
IN WHICH ORGANIZATIONAL STRUCTURE IS THE PROJECT MANAGER LIKELY TO HAVE THE MOST AUTHORITY?
A) Functional
B) Weak Matrix
C) Projectized
D) Strong Matrix
ANSWER: C
One of the outputs of Manage Communications is
A) Project communications
B) Work performance data
C) Project reporting
D) Decomposition
ANSWER: A
THE COST PERFORMANCE BASELINE HAS ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) It is the approved version of the time-phased project budget, excluding any management reserves, and is used as a basis for comparison with actual results.
B) It shows the actual cost expenditures throughout the project life cycle.
C) It is developed as a summation of the approved budgets for the different schedule activities.
D) It is typically displayed in the form of an S-curve.
ANSWER: B
Monitor Communications:
A) Work performance data
B) Project funding requirements
C) Communication skills
D) Expert judgment
ANSWER: A
The benefit of Monitor Communications is:
A) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
B) Focuses efforts on high-priority risks.
C) Identifies appropriate ways to address overall project risk and individual project risks.
D) Selects a qualified seller and implements the legal agreement for delivery.
ANSWER: A
Monitor Communications:
A) Work performance information
B) Project charter
C) Project management information system
D) Critical path method
ANSWER: A
Monitor Communications
A) The optimal information flow as defined in the communications management plan and the stakeholder engagement plan.
B) Focuses efforts on high-priority risks.
C) Identifies appropriate ways to address overall project risk and individual project risks.
D) Selects a qualified seller and implements the legal agreement for delivery.
ANSWER: A
Monitor Communications
A) Project management information system
B) Critical path method
C) Project management plan
D) Project funding requirements
ANSWER: A
One of the tools and techniques used in Plan Communications Management is
A) Communication methods
B) Project management information system
C) Project management plan
D) Stakeholder management plan
ANSWER: A
Plan Communications Management
A) Communication methods
B) Project management information system
C) Project management plan
D) Stakeholder management plan
ANSWER: A
One of the inputs for Monitor Communications is:
A) Work performance data
B) Project funding requirements
C) Communication skills
D) Expert judgment
ANSWER: A
WHICH THEORY SPECIFIES MONEY AS AN IMPORTANT EMPLOYEE MOTIVATOR?
A) Theory X
B) Theory Y
C) Theory Z
D) Theory Q
ANSWER: A
One of the outputs of Monitor Communications is
A) Work performance information
B) Project charter
C) Project management information system
D) Critical path method
ANSWER: A
One of the outputs of Plan Risk Management is
A) Risk management plan
B) Project charter
C) Meetings
D) Risk categorization
ANSWER: A
PROJECT COST CONTROL INCLUDES ALL OF THE FOLLOWING EXCEPT:
A) Informing appropriate stakeholders of all approved changes and associated costs.
B) Monitoring cost performance to isolate and understand variances from the approved cost baseline.
C) Influencing the factors that create changes to the authorized cost baseline.
D) Allocating the overall estimates to individual work packages to establish a cost baseline .
ANSWER: D
Plan Risk Management:
A) Project charter
B) Work performance reports
C) To-complete performance index
D) Inspection
ANSWER: A
The benefit of Plan Risk Management is:
A) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
B) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
C) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
D) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
ANSWER: A
Plan Risk Management:
A) Risk management plan
B) Project charter
C) Meetings
D) Risk categorization
ANSWER: A
Plan Risk Management
A) Ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders
B) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
C) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
D) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
ANSWER: A
Plan Risk Management
A) Meetings
B) Risk categorization
C) Project management plan
D) Project documents
ANSWER: A
One of the tools and techniques used in Manage Communications is
A) Project reporting
B) Decomposition
C) Project management plan
D) Agreements
ANSWER: A
Manage Communications
A) Project reporting
B) Decomposition
C) Project management plan
D) Agreements
ANSWER: A
One of the inputs for Plan Risk Management is
A) Project charter
B) Work performance reports
C) To-complete performance index
D) Inspection
ANSWER: A
DUAL REPORTING IS MOST LIKELY TO OCCUR IN WHICH TYPE OF ORGANIZATION?
A) Functional
B) Projectized
C) Matrix
D) Laissez-faire
ANSWER: C
One of the outputs of Identify Risks is
A) Risk register
B) Change requests
C) Expert judgment
D) Representations of uncertainty
ANSWER: A
PROJECT QUALITY MANAGEMENT INCLUDES THE PROCESSES FOR INCORPORATING THE ORGANIZATION'S QUALITY POLICY REGARDING PLANNING, MANAGING, AND CONTROLLING PROJECT AND PRODUCT QUALITY REQUIREMENTS IN ORDER TO:
A) Meet stakeholdersظآ objectives.
B) Improve process capability.
C) Control products, services, and results.
D) Meet standards of performance for the project team.
ANSWER: A
Identify Risks:
A) Procurement documentation
B) Approved change requests
C) Critical path method
D) Three-point estimating
ANSWER: A
Identify Risks:
A) Risk register
B) Change requests
C) Expert judgment
D) Representations of uncertainty
ANSWER: A
One of the tools and techniques used in Monitor Communications is
A) Project management information system
B) Critical path method
C) Project management plan
D) Project funding requirements
ANSWER: A
Monitor Communications
A) Project management information system
B) Critical path method
C) Project management plan
D) Project funding requirements
ANSWER: A
One of the inputs for Identify Risks is:
A) Procurement documentation
B) Approved change requests
C) Critical path method
D) Three-point estimating
ANSWER: A
WHICH OF THE FOLLOWING IS NOT A PART OF THE INFORMATION DISTRIBUTION PROCESS?
A) Project plan
B) Project records
C) Communication skills
D) Stakeholder analysis
ANSWER: D
One of the outputs of Perform Qualitative Risk Analysis is
A) Project documents updates
B) Change requests
C) Risk categorization
D) Strategies for threats
ANSWER: A
QUALITY AND GRADE ARE NOT THE SAME┬بA FUNDAMENTAL DISTINCTION IS THAT:
A) Quality as a delivered performance or result is the degree to which a set of inherent characteristics fulfills requirements; grade as a design intent is a category assigned to deliverables having the same functional use but different technical characteristics.
B) A quality level that fails to meet quality requirements may not be a problem; a low grade of quality is always a problem.
C) Delivering the required levels of quality is not included in the responsibilities of the project manager and the project team.
D) Delivering the required levels of grade is not included in the responsibilities of the project manager and the project team.
ANSWER: A
Perform Qualitative Risk Analysis:
A) Project documents
B) Work performance data
C) Virtual teams
D) Problem solving
ANSWER: A
The benefit of Identify Risks is:
A) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
B) Identifies appropriate ways to address overall project risk and individual project risks.
C) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
D) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
ANSWER: A
The benefit of Perform Qualitative Risk Analysis is:
A) Focuses efforts on high-priority risks.
B) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
C) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
D) Provides an actionable plan to interact effectively with stakeholders.
ANSWER: A
Perform Qualitative Risk Analysis:
A) Project documents updates
B) Change requests
C) Risk categorization
D) Strategies for threats
ANSWER: A
Identify Risks
A) Documentation of existing individual project risks and the sources of overall project risk & Brings together information so the project team can respond appropriately to identified risks.
B) Identifies appropriate ways to address overall project risk and individual project risks.
C) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
D) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
ANSWER: A
Perform Qualitative Risk Analysis
A) Focuses efforts on high-priority risks.
B) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
C) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
D) Provides an actionable plan to interact effectively with stakeholders.
ANSWER: A
Identify Risks
A) Expert judgment
B) Representations of uncertainty
C) Project management plan
D) Risk register
ANSWER: A
One of the tools and techniques used in Identify Risks is
A) Expert judgment
B) Representations of uncertainty
C) Project management plan
D) Risk register
ANSWER: A
Identify Risks
A) Expert judgment
B) Representations of uncertainty
C) Project management plan
D) Risk register
ANSWER: A
One of the inputs for Perform Qualitative Risk Analysis is:
A) Project documents
B) Work performance data
C) Virtual teams
D) Problem solving
ANSWER: A
WHICH IS THE PROCESS THAT INVOLVES DOCUMENTING PROJECT RESULTS IN ORDER TO FORMALIZE THE ACCEPTANCE OF THE PRODUCT BY THE SPONSOR, CLIENT, OR CUSTOMER?
A) Information distribution
B) Scope acceptance
C) Performance reporting
D) Administrative closure
ANSWER: D
One of the outputs of Perform Quantitative Risk Analysis is
A) Project documents updates
B) Project charter
C) Representations of uncertainty
D) Project management information system
ANSWER: A
UNDERSTANDING, EVALUATING, DEFINING, AND MANAGING REQUIREMENTS ARE ESSENTIAL TO SATISFYING:
A) Customer expectations.
B) The scope statements.
C) Upper management.
D) Functional requirements.
ANSWER: A
Perform Quantitative Risk Analysis:
A) Enterprise environmental factors
B) Project charter
C) Variance analysis
D) Dependency determination and integration
ANSWER: A
The benefit of Perform Quantitative Risk Analysis is:
A) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
B) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
C) Selects a qualified seller and implements the legal agreement for delivery.
D) Allows the project manager to increase support and minimize resistance from stakeholders.
ANSWER: A
Perform Quantitative Risk Analysis:
A) Project documents updates
B) Project charter
C) Representations of uncertainty
D) Project management information system
ANSWER: A
Perform Quantitative Risk Analysis
A) Quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.
B) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
C) Selects a qualified seller and implements the legal agreement for delivery.
D) Allows the project manager to increase support and minimize resistance from stakeholders.
ANSWER: A
Perform Qualitative Risk Analysis
A) Risk categorization
B) Strategies for threats
C) Project management plan
D) Work performance reports
ANSWER: A
One of the tools and techniques used in Perform Qualitative Risk Analysis is
A) Risk categorization
B) Project management plan
C) Work performance reports
D) Strategies for threats
ANSWER: A
Perform Qualitative Risk Analysis
A) Risk categorization
B) Project management plan
C) Work performance reports
D) Strategies for threats
ANSWER: A
One of the inputs for Perform Quantitative Risk Analysis is:
A) Enterprise environmental factors
B) Project charter
C) Variance analysis
D) Dependency determination and integration
ANSWER: A
_________________ SPECIFIES TO WHOM INFORMATION WILL FLOW AND WHAT METHOD WILL BE USED TO DISTRIBUTE VARIOUS TYPES OF INFORMATION.
A) Collection and filing structure
B) Communications requirements
C) Distribution structure
D) Communications management plan
ANSWER: D
How many communication channels will be required in a project in which 10 individual are participating?
A) 45
B) 46
C) 9
D) 10
ANSWER: A
A project with Earned Value (EV) = $250, Actual Cost (AC) = $200 and Planned Value (PV) = $350. What is the Schedule Performance Index (SPI)?
A) 1.25
B) 0.80
C) 0.71
D) 1.40
ANSWER: C
ظ£Your duty to take ownership for the decisions you make or fail to make, the actions you take or fail to take, and the consequences that resultظإ is part of ___________.
A) Respect
B) Responsibility
C) Honesty
D) Fairness
ANSWER: B
Which of the below statements best describes rolling wave planning?
A) Near term work is planned in detail while work further in the future is planned at a higher level
B) Near term work is planned at a high level
C) Work which will happen late in future is planned in detail
D) All the work of the project is planned in detail irrespective of whether it will happen soon or much later
ANSWER: A
While creating a project schedule, what duration should a milestone have?
A) Zero
B) Duration equal to the phase duration
C) Duration equal to the time required for a particular task to be completed
D) Duration of the complete project till the milestone date
ANSWER: A
Manage Project Knowledge
A) Knowledge management
B) Change control tools
C) Agreements
D) Approved change requests
ANSWER: A
One of the tools and techniques used in Manage Project Knowledge is
A) Knowledge management
B) Agreements
C) Approved change requests
D) Approved change requests
ANSWER: A
Manage Project Knowledge
A) Knowledge management
B) Agreements
C) Approved change requests
D) Approved change requests
ANSWER: A
The benefit of Direct and Manage Project Work is:
A) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
B) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
C) It provides the basis for defining the product scope and project scope.
D) The scope baseline is maintained throughout the project.
ANSWER: A
In the project, the sponsor has provided a budget of $20 million. This is an example of a/an:
A) Constraint
B) Assumption
C) Kill point
D) Risk
ANSWER: A
One of the inputs for Manage Project Knowledge is:
A) Deliverables
B) Project charter
C) ┬بData analysis
D) Variance analysis
ANSWER: A
One of the outputs of Manage Project Knowledge is
A) Lessons learned register
B) Final product, service, or result transition
C) Knowledge management
D) Change control tools
ANSWER: A
The customer communicates a request for a change in your project plan. What should be your first step towards addressing the change request?
A) Talk with team members to understand implications of the change.
B) Communicate the change to the management to get their inputs.
C) Open up a change control.
D) Implement the change and communicate to the customer.
ANSWER: A
BASED ON THE LIFE CYCLE MODEL OF THE TYPICAL PROJECT, WHICH STAGE IS EXPECTED TO EXPERIENCE THE HIGHEST RESOURCE USAGE?
A) Initial phase(s)
B) Intermediate phase(s)
C) Closing phase(s)
D) Staffing phase(s)
ANSWER: B
Direct and Manage Project Work
A) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
B) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
C) It provides the basis for defining the product scope and project scope.
D) The scope baseline is maintained throughout the project.
ANSWER: A
The customer communicates a request for a change in your project plan. What should be your first step towards addressing the change request?
A) Talk with team members to understand implications of the change.
B) Communicate the change to the management to get their inputs.
C) Open up a change control.
D) Implement the change and communicate to the customer.
ANSWER: A
Manage Project Knowledge:
A) Deliverables
B) Project charter
C) ┬بData analysis
D) Variance analysis
ANSWER: A
Manage Project Knowledge:
A) Lessons learned register
B) Final product, service, or result transition
C) Knowledge management
D) Change control tools
ANSWER: A
Which of the below statements best describes rolling wave planning?
A) Near term work is planned in detail while work further in the future is planned at a higher level
B) Near term work is planned at a high level
C) Work which will happen late in future is planned in detail
D) All the work of the project is planned in detail irrespective of whether it will happen soon or much later
ANSWER: A
ENTERPRISE ENVIRONMENTAL FACTORS REFER TO BOTH INTERNAL AND EXTERNAL ENVIRONMENTAL FACTORS THAT SURROUND OR INFLUENCE A PROJECT'S SUCCESS. ALL OF THE FOLLOWING ARE TRUE ABOUT THESE FACTORS EXCEPT:
A) Enterprise environmental factors include organizational culture, structure, and processes.
B) Enterprise environmental factors include government or industry standards, such as regulatory agency regulations, codes of conduct, product standards, quality standards, and workmanship standards.
C) Enterprise environmental factors include information technology software (e.g., an automated tool, such as a scheduling software tool, a configuration management system, an information collection and distribution system, or web interfaces to other online automated systems).
D) ┬بEnterprise environmental factors exclude personnel administration functions (e.g., staffing and retention guidelines, employee performance reviews and training records, and time tracking) because these are considered to be functions of the human resources department.
ANSWER: D
A process with lack of consistency and predictability is called:
A) In control
B) Out of control
C) Bad quality
D) Quality noise
ANSWER: B
One of the outputs of Plan Risk Responses is
A) Change requests
B) Work performance data
C) Strategies for threats
D) Decomposition
ANSWER: A
ALL OF THE FOLLOWING ARE PRIMARY BENEFITS OF MEETING QUALITY REQUIREMENTS EXCEPT:
A) Less rework.
B) Higher productivity.
C) Lower costs.
D) Fewer change orders.
ANSWER: D
Plan Risk Responses:
A) Project documents
B) Project charter
C) Individual and team assessments
D) Communication methods
ANSWER: A
The benefit of Plan Risk Responses is:
A) Identifies appropriate ways to address overall project risk and individual project risks.
B) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
C) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
D) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
ANSWER: A
Plan Risk Responses:
A) Change requests
B) Work performance data
C) Strategies for threats
D) Decomposition
ANSWER: A
Plan Risk Responses
A) Identifies appropriate ways to address overall project risk and individual project risks.
B) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
C) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
D) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
ANSWER: A
Perform Quantitative Risk Analysis
A) Representations of uncertainty
B) Project management information system
C) Project management plan
D) Stakeholder management plan
ANSWER: A
One of the tools and techniques used in Perform Quantitative Risk Analysis is
A) Representations of uncertainty
B) Project management information system
C) Project management plan
D) Stakeholder management plan
ANSWER: A
Perform Quantitative Risk Analysis
A) Representations of uncertainty
B) Project management information system
C) Project management plan
D) Stakeholder management plan
ANSWER: A
One of the inputs for Plan Risk Responses is:
A) Project documents
B) Project charter
C) Individual and team assessments
D) Communication methods
ANSWER: A
WHICH OF THE FOLLOWING IS NOT ONE OF THE RISK MANAGEMENT PROCESSES?
A) Risk identification
B) Risk quantification
C) Risk assessment
D) Risk response planning
ANSWER: C
One of the outputs of Implement Risk Responses is
A) Change requests
B) Selected sellers
C) Project management information system
D) Source selection analysis
ANSWER: A
INPUTS TO CONTROL QUALITY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Project management plan.
B) Quality metrics.
C) Work performance data.
D) PERT chart.
ANSWER: D
Implement Risk Responses:
A) Project documents
B) Agreements
C) Interpersonal and team skills
D) Project reporting
ANSWER: A
The benefit of Implement Risk Responses is:
A) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
B) Selects a qualified seller and implements the legal agreement for delivery.
C) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
D) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
ANSWER: A
Implement Risk Responses:
A) Change requests
B) Selected sellers
C) Project management information system
D) Source selection analysis
ANSWER: A
Implement Risk Responses
A) Ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
B) Selects a qualified seller and implements the legal agreement for delivery.
C) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
D) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
ANSWER: A
Plan Risk Responses
A) Strategies for threats
B) Decomposition
C) Project management plan
D) Approved change requests
ANSWER: A
One of the tools and techniques used in Plan Risk Responses is
A) Strategies for threats
B) Project management plan
C) Approved change requests
D) Stakeholder management plan
ANSWER: A
Plan Risk Responses
A) Strategies for threats
B) Project management plan
C) Approved change requests
D) Stakeholder management plan
ANSWER: A
One of the inputs for Implement Risk Responses is:
A) Project documents
B) Agreements
C) Interpersonal and team skills
D) Project reporting
ANSWER: A
RISK RESPONSE PLANNING IS ONE OF THE _______________ PROCESSES
A) Planning core processes
B) Planning facilitating processes
C) Controlling core processes
D) Controlling facilitating processes
ANSWER: B
One of the outputs of Monitor Risks is
A) Organizational process assets updates
B) Closed procurements
C) Data analysis
D) Bidder conferences
ANSWER: A
THE QUALITY MANAGEMENT PLAN IS A COMPONENT OF THE WHICH DESCRIBES HOW THE ORGANIZATION'S QUALITY POLICIES WILL BE IMPLEMENTED.
A) Project management plan
B) Program management plan
C) Project scope
D) Governance management plan
ANSWER: A
Monitor Risks:
A) Work performance data
B) Project charter
C) Data analysis
D) Meetings
ANSWER: A
The benefit of Monitor Risks is:
A) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
B) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
C) Provides an actionable plan to interact effectively with stakeholders.
D) The production of a comprehensive document that defines the basis of all project work.
ANSWER: A
Monitor Risks:
A) Organizational process assets updates
B) Closed procurements
C) Data analysis
D) Bidder conferences
ANSWER: A
Monitor Risks
A) Enables project decisions to be based on current information about overall project risk exposure and individual project risks.
B) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
C) Provides an actionable plan to interact effectively with stakeholders.
D) The production of a comprehensive document that defines the basis of all project work.
ANSWER: A
Implement Risk Responses
A) Project management information system
B) Source selection analysis
C) Project management plan
D) Deliverables
ANSWER: A
One of the tools and techniques used in Implement Risk Responses is
A) Project management information system
B) Source selection analysis
C) Project management plan
D) Deliverables
ANSWER: A
Implement Risk Responses
A) Project management information system
B) Source selection analysis
C) Project management plan
D) Deliverables
ANSWER: A
One of the inputs for Monitor Risks is:
A) Work performance data
B) Project charter
C) Data analysis
D) Meetings
ANSWER: A
USING A CONTRACTOR TO PERFORM A HIGH RISK TASK IS WHICH FORM OF RISK RESPONSE?
A) Mitigation
B) Acceptance
C) Transference
D) Avoidance
ANSWER: C
MANAGE QUALITY IS THE PROCESS OF:
A) Applying planned, systematic quality activities to ensure effective policing and conformance of the project team to the approved specifications.
B) Providing the project team and stakeholders with standards by which project performance is measured.
C) Translating the quality management plan into executable quality activities that incorporate the organization's quality policies into the project.
D) Assuring the implementation of appropriate specifications, which generally reduces the probability of the project being completed on schedule.
ANSWER: C
Plan Procurement Management:
A) Project charter
B) Project funding requirements
C) Test and inspection planning
D) Expert judgment
ANSWER: A
The benefit of Plan Procurement Management is:
A) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
B) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
C) Allows the project manager to increase support and minimize resistance from stakeholders.
D) It provides overall management of the project work and deliverables, thus improving the probability of project success.
ANSWER: A
Plan Procurement Management
A) Determines whether to acquire goods and services from outside the project, what to acquire as well as how and when to acquire it.
B) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
C) Allows the project manager to increase support and minimize resistance from stakeholders.
D) It provides overall management of the project work and deliverables, thus improving the probability of project success.
ANSWER: A
Monitor Risks
A) Data analysis
B) Bidder conferences
C) ┬ب Risk register
D) Project charter
ANSWER: A
One of the tools and techniques used in Monitor Risks is
A) Data analysis
B) Risk register
C) Project charter
D) Bidder conferences
ANSWER: A
Monitor Risks
A) Data analysis
B) Risk register
C) Project charter
D) Bidder conferences
ANSWER: A
One of the inputs for Plan Procurement Management is:
A) Project charter
B) Project funding requirements
C) Test and inspection planning
D) Expert judgment
ANSWER: A
THE CONTRACT TYPE THAT REPRESENTS THE LOWEST RISK TO THE BUYER IS:
A) CPIF
B) FPI
C) FFP
D) CPFF
ANSWER: C
One of the outputs of Conduct Procurements is
A) Selected sellers
B) Stakeholder engagement plan
C) Bidder conferences
D) Critical path method
ANSWER: A
COST OF QUALITY INCLUDES ALL OF THE FOLLOWING EXCEPT:
A) Preventing nonconformance to requirement
B) Appraising the product or service for conformance to requirements
C) Failing to meet requirements (rework).
D) ┬بOperating computers required for the project.
ANSWER: D
Conduct ProcurementS:
A) Project management plan
B) Stakeholder management plan
C) Project management information system
D) Bidder conferences
ANSWER: A
The benefit of Conduct Procurements is:
A) Selects a qualified seller and implements the legal agreement for delivery.
B) Provides an actionable plan to interact effectively with stakeholders.
C) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
D) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
ANSWER: A
Conduct Procurements:
A) Selected sellers
B) Stakeholder engagement plan
C) Bidder conferences
D) Critical path method
ANSWER: A
Conduct Procurements
A) Selects a qualified seller and implements the legal agreement for delivery.
B) Provides an actionable plan to interact effectively with stakeholders.
C) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
D) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
ANSWER: A
Plan Procurement Management
A) Source selection analysis
B) Inspection
C) Team performance assessments
D) Work performance data
ANSWER: A
One of the tools and techniques used in Plan Procurement Management is
A) Source selection analysis
B) Inspection
C) Team performance assessments
D) Work performance data
ANSWER: A
Plan Procurement Management
A) Source selection analysis
B) Inspection
C) Team performance assessments
D) Work performance data
ANSWER: A
One of the inputs for Conduct Procurements is:
A) Project management plan
B) Stakeholder management plan
C) Project management information system
D) Bidder conferences
ANSWER: A
WHICH IS A DOCUMENT IS NOT USED TO SOLICIT PROPOSALS FROM POTENTIAL BUYERS?
A) IFB
B) IFQ
C) RFP
D) RFQ
ANSWER: B
One of the outputs of Control Procurements is
A) Closed procurements
B) Project charter
C) Inspection
D) Critical path method
ANSWER: A
BECAUSE OF THE TEMPORARY NATURE OF PROJECTS AND THE POTENTIAL BENEFITS THAT MAY BE DERIVED FROM REDUCING THE POST-PROJECT COST┬بOF QUALITY, MAY CHOOSE TO INVEST┬بIN PRODUCT QUALITY IMPROVEMENT, ESPECIALLY IN THE AREAS OF PREVENTION AND APPRAISAL:
A) Sponsoring organizations
B) The project management team
C) The project executive management team
D) The project quality function deployment (QFD) organization
ANSWER: A
Control Procurements:
A) Agreements
B) Resources management plan
C) Change control tools
D) Prototypes
ANSWER: A
The benefit of Control Procurements is:
A) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
B) Allows the project manager to increase support and minimize resistance from stakeholders.
C) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
D) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
ANSWER: A
Control Procurements:
A) Closed procurements
B) Project charter
C) Inspection
D) Critical path method
ANSWER: A
Control Procurements
A) Ensures that both the sellerظآs and buyerظآs performance meet the projectظآs requirements according to the terms of the legal agreement.
B) Allows the project manager to increase support and minimize resistance from stakeholders.
C) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
D) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
ANSWER: A
Conduct Procurements
A) Bidder conferences
B) Critical path method
C) Verified deliverables
D) Project documents
ANSWER: A
One of the tools and techniques used in Conduct Procurements is
A) Bidder conferences
B) Critical path method
C) Verified deliverables
D) Project documents
ANSWER: A
Conduct Procurements
A) Bidder conferences
B) Critical path method
C) Verified deliverables
D) Project documents
ANSWER: A
One of the inputs for Control Procurements is:
A) Agreements
B) Resources management plan
C) Change control tools
D) Prototypes
ANSWER: A
WHICH IS NOT A PROCESS OF PROCUREMENT MANAGEMENT?
A) Solicitation planning
B) Solicitation
C) Solicitation selection
D) Contract administration
ANSWER: C
One of the outputs of Identify Stakeholders is
A) Stakeholder register
B) Work performance reports
C) Expert judgment
D) Communication skills
ANSWER: A
CONTROL CHARTS HAVE ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) They are used to determine whether or not a process is stable or has predictable performance.
B) They can be used to monitor various types of output variables.
C) They are used to illustrate how various factors might be linked to potential problems or effects.
D) They are graphical displays of process data over time and against established control limits, which has a centerline that assists in detecting a trend of plotted values toward either control limit.
ANSWER: C
Identify Stakeholders:
A) Project charter
B) Risk register
C) Audits
D) Analogous estimating
ANSWER: A
The benefit of Identify Stakeholders is:
A) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
B) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
C) The production of a comprehensive document that defines the basis of all project work.
D) It allows for documented changes of the overall project objectives or plans.
ANSWER: A
Identify Stakeholders:
A) Stakeholder register
B) Work performance reports
C) Expert judgment
D) Communication skills
ANSWER: A
Identify Stakeholders
A) Enables the project team to identify the appropriate focus for engagement of each stakeholder or group of stakeholders.
B) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
C) The production of a comprehensive document that defines the basis of all project work.
D) It allows for documented changes of the overall project objectives or plans.
ANSWER: A
Control Procurements
A) Inspection
B) Critical path method
C) Work performance data
D) Organizational process assets
ANSWER: A
One of the tools and techniques used in Control Procurements is
A) Inspection
B) Critical path method
C) Work performance data
D) Organizational process assets
ANSWER: A
Control Procurements
A) Inspection
B) Critical path method
C) Work performance data
D) Organizational process assets
ANSWER: A
One of the inputs for Identify Stakeholders is:
A) Project charter
B) Risk register
C) Audits
D) Analogous estimating
ANSWER: A
One of the outputs of Plan Stakeholder Engagement is
A) Stakeholder engagement plan
B) Project charter
C) Meetings
D) Decomposition
ANSWER: A
IN RELATION TO CONTROL CHARTS, WHAT ARE THE UPPER AND LOWER SPECIFICATION LIMITS BASED ON?
A) The requirements, reflecting the maximum and minimum values allowed.
B) The control limits.
C) The specifications, reflecting the maximum and minimum values allowed.
D) The requirements and control limits.
ANSWER: A
Plan Stakeholder Engagement:
A) Project documents
B) Project funding requirements
C) Problem solving
D) Project management information system
ANSWER: A
The benefit of Plan Stakeholder Engagement is:
A) Provides an actionable plan to interact effectively with stakeholders.
B) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
C) It provides overall management of the project work and deliverables, thus improving the probability of project success.
D) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
ANSWER: A
Plan Stakeholder Engagement:
A) Stakeholder engagement plan
B) Project charter
C) Meetings
D) Decomposition
ANSWER: A
Plan Stakeholder Engagement
A) Provides an actionable plan to interact effectively with stakeholders.
B) To link the project to the strategic objectives & to formally authorize the project and get commitment of resources.
C) It provides overall management of the project work and deliverables, thus improving the probability of project success.
D) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
ANSWER: A
Identify Stakeholders
A) Expert judgment
B) Communication skills
C) Work performance data
D) Enterprise environmental factors
ANSWER: A
One of the tools and techniques used in Identify Stakeholders is
A) Expert judgment
B) Communication skills
C) Work performance data
D) Enterprise environmental factors
ANSWER: A
Identify Stakeholders
A) Expert judgment
B) Communication skills
C) Work performance data
D) Enterprise environmental factors
ANSWER: A
One of the inputs for Plan Stakeholder Engagement is:
A) Project documents
B) Project funding requirements
C) Problem solving
D) Project management information system
ANSWER: A
One of the outputs of Manage Stakeholder Engagement is
A) Change requests
B) Project charter
C) Communication skills
D) Critical path method
ANSWER: A
┬بIS THE PROCESS OF AUDITING?┬بTHE QUALITY REQUIREMENTS AND THE RESULTS FROM QUALITY CONTROL MEASUREMENTS TO ENSURE THAT APPROPRIATE QUALITY STANDARDS AND OPERATIONAL DEFINITIONS ARE USED.
A) Plan quality management
B) Manage quality
C) Control quality
D) Plan quality assurance
ANSWER: B
Manage Stakeholder Engagement
A) Project management plan
B) Approved change requests
C) Data analysis
D) Inspection
ANSWER: A
The benefit of Manage Stakeholder Engagement is:
A) Allows the project manager to increase support and minimize resistance from stakeholders.
B) The production of a comprehensive document that defines the basis of all project work.
C) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
D) It provides guidance and direction on how scope will be managed throughout the project.
ANSWER: A
Manage Stakeholder Engagement:
A) Change requests
B) Project charter
C) Communication skills
D) Critical path method
ANSWER: A
Manage Stakeholder Engagement
A) Allows the project manager to increase support and minimize resistance from stakeholders.
B) The production of a comprehensive document that defines the basis of all project work.
C) Prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases.
D) It provides guidance and direction on how scope will be managed throughout the project.
ANSWER: A
Identify Stakeholders
A) Meetings
B) Decomposition
C) Work performance data
D) Project charter
ANSWER: A
One of the tools and techniques used in Plan Stakeholder Engagement is
A) Meetings
B) Decomposition
C) Work performance data
D) Project charter
ANSWER: A
Plan Stakeholder Engagement
A) Meetings
B) Decomposition
C) Work performance data
D) Project charter
ANSWER: A
One of the inputs for Manage Stakeholder Engagement is:
A) Project management plan
B) Approved change requests
C) Data analysis
D) Inspection
ANSWER: A
One of the outputs of Monitor Stakeholder Engagement is
A) Change requests
B) Deliverables
C) Data analysis
D) Decomposition
ANSWER: A
IN USING COST-BENEFIT ANALYSIS IN THE PLAN QUALITY MANAGEMENT PROCESS, IT CAN BE NOTED THAT:
A) The primary benefit of meeting quality requirements is the reduced cost associated with project quality management activities.
B) The primary benefits of meeting quality requirements include less rework, higher productivity, lower costs, increased stakeholder satisfaction, and increased profitability.
C) The primary cost of meeting quality requirements is the increased rework to ensure stakeholder satisfaction.
D) Quality cost cannot be evaluated in relationship to the expected benefit of quality in a given project
ANSWER: B
Monitor Stakeholder Engagement:
A) Project management plan
B) Deliverables
C) Source selection analysis
D) Expert judgment
ANSWER: A
The benefit of Monitor Stakeholder Engagement is:
A) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
B) It provides overall management of the project work and deliverables, thus improving the probability of project success.
C) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
D) It provides the basis for defining the product scope and project scope.
ANSWER: A
Monitor Stakeholder Engagement:
A) Change requests
B) Deliverables
C) Data analysis
D) Decomposition
ANSWER: A
Monitor Stakeholder Engagement
A) Maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes
B) It provides overall management of the project work and deliverables, thus improving the probability of project success.
C) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
D) It provides the basis for defining the product scope and project scope.
ANSWER: A
One of the tools and techniques used in Manage Stakeholder Engagement is
A) Communication skills
B) Work performance reports
C) Project documents
D) Monitor Stakeholder Engagement
ANSWER: A
Manage Stakeholder Engagement
A) Communication skills
B) Work performance reports
C) Project documents
D) Monitor Stakeholder Engagement
ANSWER: A
One of the inputs for Monitor Stakeholder Engagement is:
A) Project management plan
B) Deliverables
C) Source selection analysis
D) Expert judgment
ANSWER: A
Which is not an example of formal communication?
A) Contract
B) Email
C) Project status report
D) Status meeting
E)
ANSWER: B
A project with Earned Value (EV) = $250, Actual Cost (AC) = $200 and Planned Value (PV) = $350. What is the Cost Performance Index (CPI)?
A) 1.25
B) 0.80
C) 0.71
D) 1.40
ANSWER: A
Negotiating in good faith and not acting in an abusive manner toward othersظإ are the mandatory standards of ______________.
A) RespectRespect
B) Responsibility
C) Honesty
D) Fairness
ANSWER: A
The scope baseline is a component of the project management plan and is critical for you to verify scope and perform scope control. Which of the following is NOT a component of the scope baseline?
A) Project Scope Statement
B) WBS
C) WBS dictionary
D) Activity list
ANSWER: D
Manage Project Knowledge
A) Knowledge management
B) Change control tools
C) Agreements
D) Approved change requests
ANSWER: A
One of the tools and techniques used in Manage Project Knowledge is
A) Knowledge management
B) Change control tools
C) Agreements
D) Approved change requests
ANSWER: A
Manage Project Knowledge
A) Knowledge management
B) Change control tools
C) Agreements
D) Approved change requests
ANSWER: A
The benefit of Monitor and Control Project Work is:
A) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
B) It provides guidance and direction on how scope will be managed throughout the project.
C) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
D) It provides guidance and direction on how the project schedule will be managed throughout the project.
ANSWER: A
The scope baseline is a component of the project management plan and is critical for you to verify scope and perform scope control. Which of the following is NOT a component of the scope baseline?
A) Project Scope Statement
B) WBS
C) WBS dictionary
D) Activity list
ANSWER: D
One of the inputs for Monitor and Control Project Work is:
A) Enterprise environmental factors
B) Business documents
C) Decomposition
D) Meetings
ANSWER: A
One of the outputs of Monitor and Control Project Work is
A) Work performance reports
B) Scope management plan
C) Decision making
D) Decomposition
ANSWER: A
The scope baseline is a component of the project management plan and is critical for you to verify scope and perform scope control. Which of the following is NOT a component of the scope baseline?
A) Project Scope Statement
B) WBS
C) WBS dictionary
D) Activity list
ANSWER: D
WHICH IS NOT A FACILITATING PROCESS?
A) Solicitation planning
B) Quality planning
C) Communications planning
D) Resource planning
ANSWER: D
Monitor and Control Project Work
A) It allows stakeholders to understand the current state of the project, Recognize the actions taken to address any performance issues & To have visibility into the future project status with cost and schedule forecasts.
B) It provides guidance and direction on how scope will be managed throughout the project.
C) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
D) It provides guidance and direction on how the project schedule will be managed throughout the project.
ANSWER: A
The scope baseline is a component of the project management plan and is critical for you to verify scope and perform scope control. Which of the following is NOT a component of the scope baseline?
A) Project Scope Statement
B) WBS
C) WBS dictionary
D) Activity list
ANSWER: D
Monitor and Control Project Work:
A) Enterprise environmental factors
B) Business documents
C) Decomposition
D) Meetings
ANSWER: A
Monitor and Control Project Work:
A) Work performance reports
B) Scope management plan
C) Decision making
D) Decomposition
ANSWER: A
PROJECT MANAGERS SPEND THE MAJORITY OF THEIR TIME COMMUNICATING WITH TEAM MEMBERS AND OTHER PROJECT STAKEHOLDERS. TO COMMUNICATE EFFECTIVELY, THE PROJECT MANAGER SHOULD GENERALLY PERFORM ALL OF THE FOLLOWING EXCEPT:
A) Calculating the potential number of communication channels accurately.
B) Developing finely tuned skills using multiple methods of communication.
C) Incorporating feedback channels.
D) Seeking to understand project stakeholders' communication needs
ANSWER: A
BENCHMARKING INVOLVES COMPARING ACTUAL OR PLANNED PROJECT PRACTICES TO THOSE OF COMPARABLE PROJECTS WITH ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) To identify best practices and generate ideas for improvement.
B) To provide a basis for measuring performance.
C) Within the performing organization or outside of it.
D) Within the same application area but not in a different application area.
ANSWER: D
Monitor Stakeholder Engagement
A) Monitor Stakeholder Engagement
B) Data analysis
C) Work performance reports
D) Work performance reports
ANSWER: A
THE BASIS FOR CONTINUOUS QUALITY IMPROVEMENT IS THE:
A) Plan-do-check-act (PDCA) cycle as defined by Shewhart and modified by Deming.
B) Process decision program chart (PDPC).
C) Ready-aim-fire (RAF) cycle linked by results.
D) Conceptualize-design-execute-finish (CDEF) cycle.
ANSWER: A
ALL OF THE FOLLOWING ARE TRUE ABOUT AFFINITY DIAGRAMS EXCEPT:
A) They are used to identify the key issues and the suitable alternatives to be prioritized as a set of decisions for implementation.
B) They are similar to mind-mapping techniques
C) They are used to generate ideas that can be linked to form organized patterns of thought about a problem.
D) They can be used in project management to give structure to the decomposition of scope and enhance the creation of the WBS.
ANSWER: A
ALL OF THE FOLLOWING ARE CONSIDERATIONS FOR TAILORING IN PROJECT QUALITY MANAGEMENT EXCEPT:
A) Standards are regulatory' compliance.
B) Policy compliance and auditing.
C) Continuous improvement.
D) Stakeholder management.
ANSWER: D
PLANNING QUALITY MANAGEMENT TO IDENTIFY┬بQUALITY REQUIREMENTS AND/OR STANDARDS FOR THE PROJECT AND ITS DELIVERABLES AND DOCUMENTING HOW THE PROJECT WILL DEMONSTRATE COMPLIANCE WITH QUALITY REQUIREMENTS IS PART OF THE:
A) Conceptual phase.
B) Planning Process Group.
C) Project implementation phase.
D) Control Quality process.
ANSWER: B
THE MAJOR PROCESSES OF PROJECT RESOURCE MANAGEMENT ARE:
A) Leadership, Management, Team Building, and Negotiation.
B) Develop Project Staffing Plan, Recruit Project Team, Administer Personnel Actions, and Manage Labor Relations.
C) Plan Organizational Structure, Build Project Team, Develop Communications Plan, and Manage Team Conflicts.
D) Plan Resource Management, Estimate Activity Resources, Acquire Resources, Develop Team, Manage Team, and Control Resources.
ANSWER: D
THE RESPONSIBILITY ASSIGNMENT MATRIX (RAM) IS
A) Used for development of the project budget and network diagrams.
B) Developed at the activity level and used to closely link project roles and responsibilities to project network activities.
C) Used to illustrate the connections between work packages or activities and project team members It ensures that there is only one person accountable for any one task to avoid confusion of responsibility
D) Used to identify accountabilities and responsibilities in individual performance appraisals of project team members.
ANSWER: C
PLAN RESOURCE MANAGEMENT SHOULD GENERALLY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Roles and responsibilities.
B) Identification of resources.
C) Acquiring resources.
D) Project interfaces.
ANSWER: D
QUESTIONS THAT ARISE WHEN PLANNING THE ACQUISITION OF TEAM MEMBERS GENERALLY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Whether the resources come from within the organization or from external, contracted sources.
B) The costs associated with each level of expertise needed for the project.
C) The compensation of senior executives.
D) The level of assistance that the organizationظآs human resource department and functional managers are able to provide to the project management team
ANSWER: C
ACQUIRE RESOURCES IS THE PROCESS OF CONFIRMING RESOURCE AVAILABILITY AND OBTAINING THE TEAM NECESSARY TO COMPLETE PROJECT ACTIVITIES. THE ENTERPRISE ENVIRONMENTAL FACTORS THAT CAN INFLUENCE THIS PROCESS GENERALLY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Organizational structure.
B) Political philosophy.
C) Competency levels, prior experience, and cost rate.
D) Personnel administration policies, such as those that affect outsourcing.
ANSWER: B
For the project with original┬بproject budget $1000 and both┬بthe Cost Performance Index (CPI) and Schedule Performance Index (SPI) equal┬ب1. Assuming┬بthe┬بproject will continue to spend money at the same rate,┬بwhat is the Estimate At Completion (EAC) of the project?
A) $833
B) $933
C) $1,000
D) $1,033
ANSWER: C
You are the project manager of a road paving┬بproject. A total of 10km of road is to be paved over a 5-month period. The total budget for the project is $10,000. The project is now at the end of the 3rd┬بmonth with 8km of road┬بpaved and $8,000 spent. The Schedule┬بPerformance Index (SPI) for the project is:
A) 0.78
B) 0.98
C) 1.20
D) 1.33
ANSWER: D
FACTORS THAT CAN AFFECT THE CHOICE OF COMMUNICATION TECHNOLOGY GENERALLY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Urgency of the need for information.
B) Availability of technology.
C) Executive requirements.
D) Sensitivity and confidentiality of the information
ANSWER: C
As a project manager, in approximating costs, you consider the possible causes of variation of the cost estimates, including risks. For your project, which is in the initiation phase, your team has suggested a rough order of magnitude estimate. This could be in the range of:
A) -75% to +90%
B) -25% to +75%
C) -10% to +25%
D) -5% to +10%
ANSWER: B
Monitor and Control Project Work
A) Decision making
B) Rolling wave planning
C) Approved change requests
D) Accepted deliverables
ANSWER: A
One of the tools and techniques used in Monitor and Control Project Work is
A) Decision making
B) Rolling wave planning
C) Approved change requests
D) Accepted deliverables
ANSWER: A
Monitor and Control Project Work
A) Decision making
B) Rolling wave planning
C) Approved change requests
D) Accepted deliverables
ANSWER: A
The benefit of Perform Integrated Change Control is:
A) It allows for documented changes of the overall project objectives or plans.
B) It provides the basis for defining the product scope and project scope.
C) It provides a framework of what has to be delivered.
D) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
ANSWER: A
You are a project manager for a $50 million project that is highly complex and involves more than 100 people. To successfully execute the project, you decide to break it down into smaller manageable units. Which of the following processes will you use?
A) Control ScopeCollect Requirements
B) Collect Requirements
C) Define Scope
D) Create WBS
ANSWER: D
One of the outputs of Perform Integrated Change Control is
A) Approved change requests
B) Requirements traceability matrix
C) Change control tools
D) Alternatives analysis
ANSWER: A
Your company exhibited a car model in two international auto expos and obtained feedback from the global automobile industry, auto magazines, and others. The company decided to go ahead with the designing and manufacturing of the car, taking into consideration the feedback received. Which of the following methods did your company use to make this decision?
A) Observation technique
B) Prototype
C) Requirement documentation
D) Requirement traceability matrix
ANSWER: B
One of the inputs for Perform Integrated Change Control is:
A) Work performance reports
B) Business documents
C) Data gathering
D) Knowledge management
ANSWER: A
CORE PROCESSES:
A) Can interact differently with one-another, depending on the nature of the project
B) Have clear dependencies
C) Must be preformed simultaneously
D) Are managed by the same staff members throughout the project
ANSWER: B
Perform Integrated Change Control
A) It allows for documented changes of the overall project objectives or plans.
B) It provides the basis for defining the product scope and project scope.
C) It provides a framework of what has to be delivered.
D) It decomposes work packages into schedule activities that provide a basis for estimating, scheduling, executing, monitoring, and controlling the project work.
ANSWER: A
Your company exhibited a car model in two international auto expos and obtained feedback from the global automobile industry, auto magazines, and others. The company decided to go ahead with the designing and manufacturing of the car, taking into consideration the feedback received. Which of the following methods did your company use to make this decision?
A) Observation technique
B) Prototype
C) Requirement documentation
D) Requirement traceability matrix
ANSWER: B
Perform Integrated Change Control:
A) Approved change requests
B) Requirements traceability matrix
C) Change control tools
D) Alternatives analysis
ANSWER: A
Perform Integrated Change Control:
A) Work performance reports
B) Business documents
C) Data gathering
D) Knowledge management
ANSWER: A
IT IS IMPORTANT THAT THE RESOURCE MANAGEMENT PLAN ADDRESSES HOW TEAM MEMBERS WILL BE RELEASED WHEN THEY ARE NO LONGER NEEDED ON THE PROJECT FOR ALL OF THE FOLLOWING REASONS EXCEPT:
A) To reduce project costs.
B) To improve morale when smooth transitions to upcoming projects are already planned.
C) To optimize the utilization of human and material resources.
D) To help mitigate resource risks that may occur during or at the end of a project.
ANSWER: C
TO BE EFFECTIVE, RECOGNITION AND REWARDS SYSTEMS SHOULD HAVE THE FOLLOWING CHARACTERISTICS EXCEPT:
A) Clear criteria for rewards and a planned system for their use to help promote and reinforce desired behaviors.
B) Being based on activities and performance under a person's control.
C) Cultural differences should be considered when determining recognition and rewards.
D) The required performance for rewards should be made unachievable for most team members, to ensure that all team members strive for excellence throughout the project.
ANSWER: D
TOOLS AND TECHNIQUES TO ACQUIRE RESOURCES INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Decision making.
B) Acquisition.
C) Interpersonal and team skills.
D) Pre-assignment.
ANSWER: C
ALL OF THE FOLLOWING ARE TRUE ABOUT CONFLICT MANAGEMENT EXCEPT:
A) It is inevitable in a project environment and should be addressed early.
B) It should usually be addressed in private.
C) It should be addressed only when it becomes disruptive, and at an official team meeting.
D) It should be addressed using a direct, collaborative approach.
ANSWER: C
TEAM BUILDING HAS ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) Team-building activities can vary from a five-minute agenda item in a status review meeting to an off-site, professionally facilitated experience designed to improve interpersonal relationships
B) Team building should be primarily considered after major conflicts within the project team, because they generally waste precious resource time and cause schedule delays.
C) Team-building strategies are particularly valuable when team members operate from remote locations without the benefit of face-to-face contact.
D) Team building is essential during the front end of a project and is an ongoing process. To effectively manage inevitable changes in the project environment, a continued or renewed team-building effort is required.
ANSWER: B
TRAINING HAS ALL OF THE FOLLOWING CHARACTERISTICS EXCEPT:
A) It includes all activities designed to enhance the competencies of the project team members.
B) It can be formal or informal. Examples of training methods include classroom, online, computer- based, on-the-job training from another project team member, mentoring, and coaching.
C) If project team members lack necessary management or technical skills, the project should be deemed outside the core competencies of the performing organization, outsourced, or abandoned.
D) If project team members lack the necessary management or technical skills, such skills can be developed as part of the project work.
ANSWER: C
EFFECTIVE TEAM DEVELOPMENT STRATEGIES AND ACTIVITIES ARE EXPECTED TO INCREASE THE TEAM'S PERFORMANCE, WHICH INCREASES THE LIKELIHOOD OF MEETING PROJECT OBJECTIVES. THE EVALUATION OF A TEAM'S EFFECTIVENESS MAY INCLUDE ALL OF THE FOLLOWING INDICATORS EXCEPT:
A) Improvements in skills that allow individuals to perform assignments more effectively.
B) Improvements in competencies that help the team perform better as a unit.
C) Improvements in the overall project performance as a result of increased intensity of conflict among project team members.
D) Reduced staff turnover rate.
ANSWER: C
GENERALLY ACKNOWLEDGED TECHNIQUES FOR RESOLVING CONFLICT INCLUDE:
A) Smooth, compromise, collaborate, and co-locating.
B) Accept, compromise, attack, and separate
C) Accommodate, compromise, force, and collaborate.
D) Withdraw, force, elaborate, and provide sensitivity training.
ANSWER: C
MANAGING AND LEADING THE PROJECT TEAM INCLUDES:
A) The process of tracking team member performance, providing feedback, resolving issues, and optimizing project performance.
B) Subscribing to the code of professional conduct but does not involve ensuring that all team members follow professional and ethical behaviors.
C) Influencing the project team to achieve the triple constraints of the project. However, professional and ethical behaviors of project team members are outside the domain of the project management team.
D) Instructing the project team to avoid being caught in repetitive violations of the norms of professional and ethical behaviors specified by the performing organization.
ANSWER: A
TEAM DEVELOPMENT STAGES INCLUDE:
A) Starting, Organizing, Preparing, Executing, and Closing.
B) Forming, Storming, Norming, Performing, and Adjourning.
C) Acquiring, Managing, Leading, Decision Making, and Releasing.
D) Initiating, Planning, Executing, Monitoring and Controlling, and Closing.
ANSWER: B
For the┬بproject with┬بEarned Value (EV) = $360, Actual Cost (AC) = $400 and both Cost Performance Index (CPI) and Schedule Performance Index (SPI) equal 0.90. The original┬بproject budget is $1,000. Assuming the remaining work will be impacted by┬بthe┬بcurrent cost performance and current schedule performance, what is the Estimate At Completion (EAC) of the project?
A) $1,090
B) $1,190
C) $1,290
D) $1,390
ANSWER: B
Your earned value analysis report is due. Project information indicates the following: EV = 150,000, PV = 140,000, AC = 160,000. You will report to your project sponsor that the project is:
A) The project is ahead of schedule and under budget
B) The project is ahead of schedule and over budget
C) The project is behind schedule and over budget
D) The project is behind schedule and under budget
ANSWER: B
You are determining whether the project activities comply with organizational and project policies. This will be done as part of
A) Inspection
B) Quality audits
C) Quality improvement
D) Trend analysis
ANSWER: B
Perform Integrated Change Control
A) Change control tools
B) Prototypes
C) Approved change requests
D) Project management plan
ANSWER: A
One of the tools and techniques used in Perform Integrated Change Control is
A) Change control tools
B) Prototypes
C) Approved change requests
D) Project management plan
ANSWER: A
PROJECTS OPERATE WITHIN THE CONSTRAINTS IMPOSED BY THE ORGANIZATION THROUGH THEIR STRUCTURE AND GOVERNANCE FRAMEWORK. THE SYSTEM FACTORS INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Management elements.
B) Governance framework.
C) Organizational structure types.
D) Project management processes.
ANSWER: D
Perform Integrated Change Control
A) Change control tools
B) Prototypes
C) Approved change requests
D) Project management plan
ANSWER: A
The benefit of Close Project or Phase is:
A) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
B) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
C) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
D) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
ANSWER: A
While creating a project schedule, what duration should a milestone have?
A) Zero
B) Duration equal to the phase duration
C) Duration equal to the time required for a particular task to be completed
D) Duration of the complete project till the milestone date
ANSWER: A
One of the outputs of Close Project or Phase is
A) Final product, service, or result transition
B) Project scope statement
C) Meetings
D) Prototypes
ANSWER: A
You are taking over a project that is currently in the planning stage. The previous project manager worked with the team to finalize the process of defining activities, and you joined the team at the end of this process. The next process requires the determination and documentation of the relationships among project activities. Of the following, which is a tool and technique used in this process?
A) Schedule Baseline
B) Dependency Determination
C) Activity List
D) Schedule Compression
ANSWER: B
One of the inputs for Close Project or Phase is:
A) Accepted deliverables
B) Verified deliverables
C) Meetings
D) Change control tools
ANSWER: A
WHICH OF THE FOLLOWING IS A TOOL OR TECHNIQUE USED IN INTEGRATED CHANGE CONTROL:
A) Organizational procedures
B) Performance reports
C) Project plan updates
D) Performance measurement
ANSWER: D
Close Project or Phase
A) The project or phase information is archived, the planned work is completed & Organizational team resources are released to pursue new endeavors.
B) It describes the product, service, or result boundaries and acceptance criteria & It develops a detailed description of the project and product, service, or result.
C) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
D) It defines the logical sequence of work to obtain the greatest efficiency given all project constraints.
ANSWER: A
You are taking over a project that is currently in the planning stage. The previous project manager worked with the team to finalize the process of defining activities, and you joined the team at the end of this process. The next process requires the determination and documentation of the relationships among project activities. Which of the following is a tool and technique used in this process?
A) Schedule Baseline
B) Dependency Determination
C) Activity List
D) Schedule Compression
ANSWER: B
Close Project or Phase:
A) Final product, service, or result transition
B) Project scope statement
C) Meetings
D) Prototypes
ANSWER: A
THE TYPES OF PROJECT MANAGEMENT OFFICE (PMO) STRUCTURES IN ORGANIZATIONS INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Supportive PMOs that provide a consultative role to projects by supplying templates, best practices, training, access to information, and lessons learned from other projects.
B) Controlling PMOs that provide support and require compliance through various means.
C) Harmonizing PMOs that strive to reduce conflict and improve harmony among project team members.
D) Directive PMOs that take control of the projects by directly managing the projects.
ANSWER: C
Close Project or Phase:
A) Accepted deliverables
B) Verified deliverables
C) Meetings
D) Change control tools
ANSWER: A
ALL OF THE FOLLOWING CHOICES REPRESENT INPUTS TO THE ESTIMATE ACTIVITY RESOURCES PROCESS EXCEPT:
A) Activity list.
B) Enterprise environmental factors.
C) The deliverable-oriented WBS of a previous, similar project.
D) Resource management plan.
ANSWER: C
OUTPUTS FROM THE ESTIMATE ACTIVITY RESOURCES, PROCESS INCLUDE:
A) Job descriptions of resources required for the project.
B) Salary schedules for various project resources
C) Identification of the types and quantities of resources required for each activity in a work package.
D) Analogous estimates of resource requirements for each work package and each work period.
ANSWER: C
It is the process of helping a group of individuals to build a collaborative and cooperative working environment.
A) It is the process of helping a group of individuals to build a collaborative and cooperative working environment.
B) It requires handling project team problems decisively and removing the individual(s) responsible for these problems from the team promptly to ensure a productive, smooth project environment.
C) It can help individual team members work together effectively.
D) It can be particularly valuable when team members operate from remote locations without the benefit of face-to-face contact.
ANSWER: B
MOTIVATING INVOLVES CREATING AN ENVIRONMENT TO MEET PROJECT OBJECTIVES WHILE PROVIDING SATISFACTION RELATED TO WHAT PEOPLE VALUE MOST. ALL OF THE FOLLOWING ARE REASONS OF MOTIVATION EXCEPT:
A) Encouraging someone to act.
B) Participating in decision making.
C) Providing accurate criticism in the annual performance review or after the project is completed.
D) Encouraging people to work independently.
ANSWER: C
THE MAJOR PROCESSES OF PROJECT┬بCOMMUNICATIONS MANAGEMENT ARE:
A) Plan Communications Management, Manage Communications, and Monitor Communications
B) Plan Communications Management, Develop Responses, Report Progress, and Distribute Information.
C) Plan Communications, Distribute Information, and Schedule Reporting.
D) Distribute Information, Report Changes, Update Project Documents, and Accept Project Deliverables.
ANSWER: A
┬بINPUTS TO THE PLAN COMMUNICATIONS MANAGEMENT PROCESS INCLUDE:
A) Project management plan, project documents, enterprise environmental factors, and organizational process assets.
B) Stakeholder requirements, project scope statement, project budget, and project schedule.
C) Organizational structure, stakeholder analysis, project management plan, and communications barriers.
D) Stakeholder management strategy, RAM, WBS, and administrative procedures.
ANSWER: A
THE COMMUNICATIONS MANAGEMENT PLAN USUALLY CONTAINS ALL OF THE FOLLOWING EXCEPT:
A) Information to be communicated, including language, format, content, and level of detail.
B) Time frame and frequency for the distribution of required information and receipt of acknowledgment or response, if applicable.
C) Methods or technologies used to convey the information, such as memos, email, and/or press releases.
D) Email archives, correspondence, reports, and documents related to the project from all stakeholders.
ANSWER: D
HARD-COPY DOCUMENT MANAGEMENT,┬بELECTRONIC COMMUNICATIONS MANAGEMENT, AND WEB INTERFACES TO SCHEDULING AND PROJECT MANAGEMENT SOFTWARE ARE EXAMPLES OF:
A) Project management information systems (PMIS).
B) Internal communications systems (ICS).
C) Internal management systems (IMS).
D) Project records databases.
ANSWER: A
For a project with┬بEstimate at Completion (EAC) =┬ب$120,000┬بand Cost Performance Index (CPI) is 0.90. What is the┬بBudget at Completion (BAC)?
A) $108,000
B) $118,000
C) $158,000
D) $208,000
ANSWER: A
AS PART OF THE COMMUNICATIONS MODEL, THE SENDER IS RESPONSIBLE FOR:
A) Ensuring that the receiver agrees with the message
B) Confirming that the communication is correctly understood.
C) Presenting the information in the most favorable manner.
D) Decoding the medium correctly.
ANSWER: B
What is Tuckman`s stages of group development in their respective order?
A) Forming, Norming, Storming, Performing, Adjourning
B) Forming, Storming, Smoothing, Performing, Adjourning
C) Forming, Storming, Norming, Performing, Adjourning
D) Forming, Norming, Storming, Performing, Closing
ANSWER: C
Close Project or Phase
A) Meetings
B) Prototypes
C) Work performance data
ANSWER: A
One of the tools and techniques used in Close Project or Phase is
A) Meetings
B) Prototypes
C) Business documents
D) Work performance data
ANSWER: A
Close Project or Phase
A) Meetings
B) Prototypes
C) Business documents
D) Work performance data
ANSWER: A
The benefit of Plan Scope Management is:
A) It provides guidance and direction on how scope will be managed throughout the project.
B) It provides a framework of what has to be delivered.
C) The scope baseline is maintained throughout the project.
D) It provides the amount of time each activity will take to complete.
ANSWER: A
As a project manager, in approximating costs, you consider the possible causes of variation of the cost estimates, including risks. For your project, which is in the initiation phase, your team has suggested a rough order of magnitude estimate. This could be in the range of:
A) -75% to +90%
B) -25% to +75%
C) -10% to +25%
D) -5% to +10%
ANSWER: B
One of the outputs of Plan Scope Management is
A) Scope management plan
B) Scope baseline
C) Alternatives analysis
D) Critical path method
ANSWER: A
While doing monitoring and controlling for your project, you notice that the cost variance is negative, but schedule variance is positive. This indicates:
A) Cost and schedule are not dependent on each other
B) Project is under budget and behind schedule
C) Project is over budget and ahead of schedule
D) Crashing may be recommended to make the cost variance positive
ANSWER: C
One of the inputs for Plan Scope Management is:
A) Project charter
B) Verified deliverables
C) Expert judgment
D) To-complete performance index
ANSWER: A
THE PROJECT PLAN:
A) Is a management control that will change only intermittently and only in response to an approved scope change
B) Usually includes the work break down structure but not major milestones
C) Is used to manage project execution
D) Includes open issues, but not pending decisions
ANSWER: C
Plan Scope Management
A) It provides guidance and direction on how scope will be managed throughout the project.
B) It provides a framework of what has to be delivered.
C) The scope baseline is maintained throughout the project.
D) It provides the amount of time each activity will take to complete.
ANSWER: A
While doing monitoring and controlling for your project, you notice that the cost variance is negative, but schedule variance is positive. This indicates that:
A) Cost and schedule are not dependent on each other
B) Project is under budget and behind schedule
C) Project is over budget and ahead of schedule
D) Crashing may be recommended to make the cost variance positive
ANSWER: C
Plan Scope Management:
A) Scope management plan
B) Scope baseline
C) Alternatives analysis
D) Critical path method
ANSWER: A
A PRIMARY FUNCTION OF A PROJECT MANAGEMENT OFFICE (PMO) IS TO SUPPORT PROJECT MANAGERS IN A VARIETY OF WAYS, WHICH MAY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Intervening in project execution directly and without involving the project manager
B) Managing shared resources across all projects administered by the PMO
C) Identifying and developing project management methodology, best practices, and standards
D) Coaching, mentoring, training, and oversight
ANSWER: A
Plan Scope Management
A) Project charter
B) Verified deliverables
C) Expert judgment
D) To-complete performance index
ANSWER: A
AS PART OF THE COMMUNICATIONS MODEL, THE RECEIVER IS RESPONSIBLE FOR:
A) Agreeing with the sender's message.
B) Pretending that the message is received only partially, to encourage further discussions.
C) Ensuring that the information is received in its entirety, understood correctly, and acknowledged or responded to appropriately
D) ┬بSpecifying that a verbal message does not give insight to problem areas, and requiring thatthe message be reduced to writing to avoid potential confusion.
ANSWER: C
SOURCES OF INFORMATION TYPICALLY USED TO IDENTIFY AND DEFINE PROJECT COMMUNICATION REQUIREMENTS INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Project organization and stakeholder responsibility relationships.
B) Disciplines, departments, and specialties involved in the project.
C) Logistics of how many persons will be involved with the project and at which locations.
D) Availability of the project sponsor at the project location.the message be reduced to writing to avoid potential confusion.
ANSWER: D
COMMUNICATION ACTIVITIES HAVE MANY POTENTIAL DIMENSIONS THAT GENERALLY INCLUDE ALL OF THE FOLLOWINGEXCEPT:
A) Written, oral, and nonverbal.
B) Internal and external.
C) Conceptual and definitive.
D) Formal and informal.
ANSWER: C
ALL OF THE FOLLOWING ARE INFORMATION MANAGEMENT AND DISTRIBUTION TOOLS EXCEPT:
A) Hard-copy document management.
B) Electronic communications management.
C) Inputting project performance data into a spreadsheet or database.
D) Electronic project management tools.
ANSWER: C
TECHNIQUES AND CONSIDERATIONS FOR EFFECTIVE COMMUNICATIONS MANAGEMENT GENERALLY INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Meeting management techniques, such as preparing an agenda and dealing with conflicts.
B) Conflict management for building consensus and overcoming obstacles.
C) Listening techniques, such as listening actively and removal of barriers that adversely affect comprehension.
D) Providing a more comfortable environment in project conference rooms to strengthen project team cohesion.
ANSWER: D
MONITOR COMMUNICATIONS IS THE PROCESS OF:
A) Ensuring that information is provided on a need-to-know basis only to avoid unnecessary confusion and possible conflicts.
B) Ensuring that the information needs of the project stakeholders are met throughout the entire project life cycle.
C) Providing all project information to all project stakeholders to enhance full buy-in regarding project requirements.
D) Securing and guarding any negative information related to project performance throughout the entire project life cycle to ensure that the project team can continue working on the project with minimal disruption .
ANSWER: B
THE KEY PROCESSES OF PROJECT RISK MANAGEMENT ARE:
A) Plan Risk Management, Identify Risks, Assess Risks, Mitigate Risks, Transfer Risks, and Document Outcomes.
B) Identify Risks, Plan Risk Management, Evaluate Risks, Develop Risk Responses, Mitigate Risks, and Document Results.
C) Identify Risks, Perform Qualitative Risk Validation, Perform Quantitative Impact Assessment, Develop Risk Response Strategies, Document Response Strategies, and Monitor Risk Responses.
D) Plan Risk Management, Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses, Implement Risk Responses, and Monitor Risks.
ANSWER: D
STRATEGIES TYPICALLY USED TO DEAL WITH THREATS OR RISKS THAT MAY HAVE NEGATIVE IMPACTS ON PROJECT OBJECTIVES IF THEY OCCUR INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Interpreting.
B) Avoiding.
C) Transferring.
D) Mitigating.
ANSWER: A
RISK TRANSFERENCE NEARLY ALWAYS INVOLVES:
A) Eliminating risk through beta testing.
B) Policies and procedures for a response system.
C) Accepting a lower profit if some activities overrun their budget.
D) Payment of a risk premium to the party taking on the risk.
ANSWER: D
IN THE PLAN RISK RESPONSES PROCESS, AN ACCEPT STRATEGY FOR A NEGATIVE RISK OR THREAT INDICATES THAT THE PROJECT TEAM HAS DECIDED:
A) To agree with the project manager.
B) To eliminate a specific risk or threat, to reduce the probability and/or impact of an adverse risk event to be within acceptable threshold limits, or to pursue an opportunity actively.
C) Not to change the project management plan to deal with a risk, or it is unable to identify any other suitable response strategy.
D) To purchase insurance, or to require performance bonds, warranties, and guarantees.
ANSWER: C
The project that you are managing has been successfully completed. The last deliverables have been formally accepted by the client. You had several contractors with whom contracts were prepared. With the project done you decide to communicate the completion details and closure of contracts. Which is the best form of communication?┬ب
A) Formal verbal
B) Informal written
C) Formal written
D) Informal verbal
ANSWER: C
THE BUYER STRUCTURES PROCUREMENT DOCUMENTS, WHICH INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Procurement statement of work.
B) Bid documents.
C) Source selection criteria and independent cost estimates.
D) Control procurement documents.
ANSWER: D
Plan Scope Management
A) Alternatives analysis
B) Critical path method
C) Deliverables
D) Project charter
ANSWER: A
One of the tools and techniques used in Plan Scope Management is
A) Alternatives analysis
B) Critical path method
C) Deliverables
D) Project charter
ANSWER: A
Plan Scope Management
A) Alternatives analysis
B) Critical path method
C) Deliverables
D) Project charter
ANSWER: A
The benefit of Collect Requirements is:
A) It provides the basis for defining the product scope and project scope.
B) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
C) It provides guidance and direction on how the project schedule will be managed throughout the project.
D) It generates a schedule model with planned dates for completing project activities.
ANSWER: A
In your project, you estimate the cost of individual activities or work packages, and then roll up the individual estimates for subsequent reporting and tracking purposes. This can be done using:
A) Bottom-up estimating
B) Analogous estimating
C) Parametric modeling
D) Top-down estimating
ANSWER: A
One of the outputs of Collect Requirements is
A) Requirements traceability matrix
B) Accepted deliverables
C) Prototypes
D) Decomposition
ANSWER: A
In your project, you estimate the cost of individual activities or work packages, and then roll up the individual estimates for subsequent reporting and tracking purposes. This can be done using:
A) Bottom-up estimating
B) Analogous estimating
C) Parametric modeling
D) Top-down estimating
ANSWER: A
One of the inputs for Collect Requirements is:
A) Business documents
B) Work performance data
C) Prototypes
D) Decision making
ANSWER: A
CHANGE CONTROL REQUESTS:
A) Must be relayed in writing
B) Provide the baseline against which changes will be controlled
C) Are always initiated externally
D) Are inputs to integrated change control
ANSWER: D
Collect Requirements
A) It provides the basis for defining the product scope and project scope.
B) Brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
C) It provides guidance and direction on how the project schedule will be managed throughout the project.
D) It generates a schedule model with planned dates for completing project activities.
ANSWER: A
In your project, you estimate the cost of individual activities or work packages, and then roll up the individual estimates for subsequent reporting and tracking purposes. This can be done using:
A) Bottom-up estimating
B) Analogous estimating
C) Parametric modeling
D) Top-down estimating
ANSWER: A
Collect Requirements:
A) Requirements traceability matrix
B) Accepted deliverables
C) Prototypes
D) Decomposition
ANSWER: A
ALL OF THE FOLLOWING ARE POTENTIAL INFORMATION IN ORGANIZATIONAL KNOWLEDGE REPOSITORIES EXCEPT:
A) Metrics used to collect and make available measurement data on processes and products
B) Configuration management
C) Tacit knowledge of previous projects such as project performance data and lessons learned
D) Issue and defect management data
ANSWER: C
Collect Requirements:
A) Business documents
B) Work performance data
C) Prototypes
D) Decision making
ANSWER: A
THE PRIMARY OUTPUT OF THE IDENTIFY RISKS PROCESS IS THE:
A) Risk register.
B) Expected monetary value of the risk events.
C) List of corrective actions.
D) Risk mitigation plan.
ANSWER: A
A THOROUGH ANALYSIS OF THE WILL HELP IDENTIFY POTENTIAL RISKS TO THE PROJECT.
A) Risk identification checklist based on historical information and knowledge
B) Projectظآs change control system
C) Projectظآs mission statement
D) Projectظآs schedule and budget
ANSWER: A
ALL OF THE FOLLOWING ARE INPUTS TO THE IDENTIFY RISKS PROCESS EXCEPT:
A) Risk management plan.
B) Scope baseline.
C) Risk mitigation plan.
D) Quality management plan.
ANSWER: C
OUTPUTS FROM THE PLAN RISK RESPONSES PROCESS INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Change requests.
B) Corrective actions.
C) Project documents updates.
D) Project management plan updates.
ANSWER: B
TOOLS AND TECHNIQUES OF THE PERFORMQUANTITATIVE RISK ANALYSIS PROCESS INCLUDE:
A) Contracting, contingency planning, alternative strategies, and insurance.
B) Interviewing, historical results, workarounds, and response development.
C) Checklists, damage control reports, standard allowances, and inspection.
D) Expert judgment, data gathering, simulations, and decision tree analysis.
ANSWER: D
AS AN OUTPUT OF THE PERFORM QUANTITATIVE RISK ANALYSIS PROCESS, THE RISK REGISTER IS UPDATED. THESE UPDATES GENERALLY INCLUDE:
A) Prioritized list of quantified risks.
B) Qualitative analysis of the threats to ignore and opportunities to accept.
C) Checklists, corrective actions, and qualified decision trees.
D) Direction, resources, and contingency costs.
ANSWER: A
A RISK IMPACT ASSESSMENT TO INVESTIGATE THE POTENTIAL EFFECT ON A PROJECT OBJECTIVE SUCH AS SCHEDULE, COST, QUALITY, OR PERFORMANCE HAS THE FOLLOWING CHARACTERISTICS EXCEPT:
A) Evaluation of each risk can be conducted using a probability and impact matrix that leads to rating the risks as low, moderate, or high priority.
B) Approaches used in evaluating risk impacts related to project objectives could be relative, numerical, or nonlinear.
C) Usually, risk-rating rules are specified by the organization in advance of the project and can be tailored to the specific project.
D) The impact on project objectives should be assessed primarily at the end of the project, as part of the lessons learned
ANSWER: D
THE OUTPUTS FROM THE MONITOR RISKS PROCESS INCLUDE ALL OF THE FOLLOWING EXCEPT:
A) Project documents updates.
B) Work breakdown structure (WBS).
C) Change requests.
D) Project management plan updates.
ANSWER: B
THE RISK RATING:
A) Is calculated by multiplying the probability of the occurrence of a risk times its impact (numerical scale) on an objective (e.g., cost, time, scope, or quality) if it were to occur.
B) Is the sum of squares of the scale values assigned to the estimates of probability and impact.
C) Cannot be used to determine whether a risk is considered low, moderate, or high.
D) Is a commonly used technique for risk avoidance.
ANSWER: A
WHICH ONE OF THE FOLLOWING CHOICES IS THE BEST DESCRIPTION OF SENSITIVITY ANALYSIS?
A) It examines the extent to which the uncertainty of each project objectives affects each project element simultaneously.
B) ┬بIt examines the extent to which the uncertainty of project element affects the objective being studied when all other uncertain elements are held at their baseline values.
C) ┬بIt is a method for assessing stakeholders' tolerance to risk.
D) ┬بIt cannot be used to determine which risks have the most potential impact on the project.
ANSWER: B
Quality checklist, which is a tool in the Manage Quality process, is used for what purpose?
A) To tabulate test results during quality control
B) To measure the various metrics
C) To verify steps in a procedure or whether certain requirements have been satisfied
D) To check the quality report
ANSWER: C
Quantitative risk analysis includes a few complex techniques. Which of the below lists these techniques?
A) Decision tree analysis and influence diagrams
B) Representations of uncertainty, simulation and sensitivity analysis
C) A and B
D) Probability and impact matrix, risk hierarchical chart
ANSWER: C
Four project managers are having lunch together and discussing their projects. Most of the time they are just complaining about how hard projects are to manage in their company. Some complain about the stakeholders and the number of changes they cause. Others talk about how hard it is to get people to cooperate and perform. One project manager wants to focus on the advantages of the matrix type organization they all work in for their projects. Which of the following would he mention?
A) Improved project manager control over resources
B) More than one boss for project teams
C) Communications are easier
D) Reporting is easier
ANSWER: A
Responsibility for the project team's output lies with the:
A) Project manager
B) Project sponsor
C) Project executive
D) PMO (project management office)
ANSWER: A
Reviewing changes between desired and current stakeholder engagement levels, and adjusting communications as necessary is best done by which technique in the Control Communications process?
A) Communication models
B) Communication methods
C) Communication skills
D) Stakeholder engagement assessment matrix
ANSWER: D
Select one or more of the below statements which correctly defines a megaproject.
A) Costs US$1billion or more
B) Affects 1 million people or more
C) Runs for years
D) All of the above
ANSWER: D
Selection of appropriate project management processes, inputs, tools, techniques, outputs and life cycle phases is known as:
A) Customization
B) Adjustment
C) Configuration
D) Tailoring
ANSWER: D
Seller capability, capacity, technical expertise, relevant experience, financial stability and management experience are known as:
A) Terms and conditions
B) Contractual obligations
C) Source selection criteria
D) Procurement strategies
ANSWER: C
Sender, receiver, message, medium, acknowledgement, feedback (response) and noise are elements of:
A) A communication model
B) Communication dimensions
C) A communication system
D) Communication tools and techniques
ANSWER: A
Stakeholder analysis technique is used in which process for the first time?
A) Identify stakeholders
B) Plan stakeholder engagement
C) Manage stakeholder engagement
D) Monitor stakeholder engagement
ANSWER: A
SWOT analysis and prompt lists are techniques in which process?
A) Plan risk management
B) Plan risk responses
C) Perform qualitative risk analysis
D) Identify risks
ANSWER: D
Techniques like communication skills (feedback), ground rules, conflict management, negotiation, observation/conversation, cultural and political awareness are used in which process?
A) Manage stakeholder engagement
B) Plan stakeholder engagement
C) Monitor stakeholder engagement
D) identify stakeholders
ANSWER: A
The assumption log is created as an output in one of the project integration management processes. Which one of the below is it?
A) Develop project charter
B) Develop project management plan
C) Monitor and control project work
D) Direct and manage project work
ANSWER: A
The numerical analysis of combined effect of all project risks is performed in which process?
A) Plan risk management
B) Plan risk responses
C) Perform qualitative risk analysis
D) Perform quantitative risk analysis
ANSWER: D
The project management plan includes which of the following:
A) Project charter and project documents
B) Subsidiary plans, baselines and additional components
C) Project reports and project documents
D) Project baselines and project documents
ANSWER: B
The project manager is the integrator for the project and also plays a key role in integrating the project with organizational strategy. The project manager performs integration at three levels. What are these levels?
A) Project, program and portfolio levels
B) Technical, leadership and business levels
C) Process, cognitive and context levels
D) System behavior, human behavior and ambiguity levels
ANSWER: C
The risk categories described in a structured manner in Risk Management Plan are also known as:
A) Risk register
B) Risk probability and impact
C) Risk breakdown structure
D) Risk identification tools and techniques
ANSWER: C
The three factors namely management elements, governance frameworks and organizational structures which interact and determine the power, influence, interests, competence and political capabilities of the people in an organization, are together known as:
A) The project environment
B) The program environment
C) Company culture
D) An organizational system
ANSWER: D
The three methods of communications are:
A) Interpersonal, small group and public communications
B) Interpersonal, small group and mass communications
C) Interpersonal, small group and social computing communications
D) Push, pull and interactive
ANSWER: D
The work performed in order to deliver a product is called:
A) Product scope
B) Project scope
C) Defined scope
D) Overall scope
ANSWER: B
There are two outputs from the Plan Scope Management process. One of them is Scope Management Plan. Which is the other one?
A) Requirements documentation
B) Requirements traceability matrix
C) Requirements management plan
D) The work breakdown structure
ANSWER: C
Tracking of team member performance, providing feedback, resolving team issues and conflicts, and managing team changes are purposes of which process?
A) Develop team
B) Manage team
C) Control resources
D) Plan resource management
ANSWER: B
Two of the resource optimization techniques are:
A) Crashing and fast tracking
B) Logical relationships and dependencies
C) Resource levelling and resource smoothing
D) What-if scenarios and simulation
ANSWER: C
What are the key skills demonstrated by the best project managers?
A) Ability to use the latest project management tools
B) Relationship and communication skills, displaying a positive attitude
C) Project planning and control skills
D) Business management skills
ANSWER: B
What are the three main types of contracts?
A) Quality and cost based, sole source, fixed budget
B) Fixed price, cost reimbursable, time and material
C) RFI, RFQ and RFP
D) Least cost, qualifications only, quality based/highest technical score
ANSWER: B
What is a risk hierarchical chart?
A) It helps to identify the highest value risks
B) It shows various categories of risks in a diagram
C) It depicts more than two dimensions of data related to risk characteristics
D) It helps to list risks in decreasing or increasing order of their priority
ANSWER: C
What is the main benefit of project stakeholder management?
A) It improves project communications
B) It increases the chances of project success
C) It improves project planning
D) It improves project risk management
ANSWER: B
What other dependency types are possible in a project apart from internal and external dependencies?
A) Soft logic and discretionary
B) Mandatory and discretionary
C) Hard logic and mandatory
D) Preferred logic and discretionary
ANSWER: B
What-if scenario analysis and simulation are techniques under which process of project schedule management?
A) Develop schedule, Control schedule
B) Sequence activities
C) Plan schedule management
D) Estimate activity durations
ANSWER: A
When defining project scope, techniques like systems/value engineering and analysis are used. These are collectively known as:
A) Prototyping
B) Requirements analysis
C) Product analysis
D) Project scope definition
ANSWER: C
When specifying leads and lags in logical relationships, how are leads represented in the activity diagram?
A) With a minus sign
B) With a plus sign
C) With a division sign
D) With a multiplication sign
ANSWER: A
Which among the following approaches to resolve conflicts results in a win-win situation?
A) Withdraw/avoid
B) Smooth/accommodate
C) Compromise/reconcile
D) Collaborate/problem solve
ANSWER: D
Which are the three types of data representation techniques in the Plan Resource Management process, which describe the project team member roles and responsibilities?
A) Hierarchical charts, responsibility assignment matrix (RACI for example) and text oriented formats
B) WBS, OBS and resource breakdown structure
C) Graphical, textual and numerical formats
D) None of the above
ANSWER: A
Which costing approach is used in agile projects?
A) Initially a high level forecast and later detailed estimates for short term planning horizons
B) The final cost is estimated at the start of the project
C) No cost estimation is done as the scope is very flexible
D) Cost for half of the project work is carefully estimated and cost for the remaining half is roughly estimated
ANSWER: A
Which is the correct list of team development stages in the Tuckman ladder model?
A) Initiating, planning, executing, controlling and closing
B) Forming, storming, norming, performing and adjourning
C) Conflict management, influencing, motivation, negotiation and team building
D) Email/chat, shared web portal, audio conferencing, video conferencing and best possible communication technology
ANSWER: B
Which is the most common type of logical relationship used when sequencing activities?
A) FF
B) SS
C) SF
D) FS
ANSWER: D
Which of the below accuracy ranges is applicable for a definitive cost estimate?
A) -25% to +75%
B) -10% to +25%
C) -5% to +10%
D) None of the above
ANSWER: C
Which of the below are methods within the stakeholder representation or mapping technique?
A) Stakeholder analysis
B) Power/impact grid and salience model
C) Stakeholder cube, directions of influence and prioritization
D) B and C
ANSWER: D
Which of the below are tools and techniques of the Plan Communications Management process?
A) Communication styles assessment and stakeholder engagement assessment matrix
B) Communication requirements analysis, communication technology, communication models and communication methods
C) Cultural awareness and political awareness
D) All of the above
ANSWER: D
Which of the below can be the reasons for raising and processing a change request?
A) Corrective and preventive actions
B) Updates to controlled documents (like baselines and plans) and deliverables
C) Defect fixes
D) All of the above
ANSWER: D
Which of the below describes the 100% rule of WBS?
A) The WBS should include all the project and product work
B) The WBS should not include any work which is not part of the project or product work
C) A and B
D) None of the above
ANSWER: C
Which of the below is a correct statement?┬ب
A) Design for excellence (DfX) is a technique in Manage Quality
B) Project quality management utilizes techniques like benchmarking, flowcharts, logical data model, matrix diagrams, scatter diagrams, affinity diagrams
C) Quality improvement methods in the Manage Quality process can include PDCA and Six-sigma methods
D) All of the above
ANSWER: D
Which of the below is a key input for the Plan Stakeholder Engagement process?
A) Communications management plan
B) Scope management plan
C) Cost management plan
D) Schedule management plan
ANSWER: A
Which of the below is a technique in the Monitor and Control Project Work process?
A) Variance analysis
B) Trend analysis
C) A and B
D) Leadership
ANSWER: C
Which of the below is an input of the Close Project or Phase process?
A) Final product, service or result transition
B) Final report
C) Accepted deliverables
D) Verified deliverables
ANSWER: C
Which of the below is an organizational process asset related to project cost management?
A) Published commercial information (external to the organization)
B) Currency exchange rates
C) Financial control procedures of the organization
D) PMIS (project management information system) showing various cost alternatives
ANSWER: C
Which of the below is correct about cost of quality?
A) It is the cost of conformance
B) It is the cost of non-conformance
C) It is the cost of conformance as well as non-conformance. Cost of conformance includes internal and external failure costs
D) It is the cost of conformance as well as non-conformance. Cost of conformance includes prevention and appraisal costs.
ANSWER: D
Which of the below is correct about the 2 types of knowledge?
A) Tacit knowledge is difficult to express and document
B) Explicit knowledge can be documented or codified
C) Tacit knowledge can be easily documented whereas explicit knowledge is difficult to express and document
D) A and B
ANSWER: D
Which of the below is correct about the cost baseline?
A) It is an output of the Estimate Costs process and includes the contingency reserve
B) It is an output of the Estimate Costs process and includes the management reserve
C) It is an output of the Determine Budget process and includes the contingency reserve
D) It is an output of the Determine Budget process and includes the management reserve
ANSWER: C
Which of the below is incorrect about a project manager's sphere of influence?
A) The influence extends beyond the project to the organization
B) The influence extends beyond the organization to the industry
C) The influence extends beyond the industry to the professional (project management) discipline
D) The influence cannot extend beyond the professional (project management) discipline to other disciplines
ANSWER: D
Which of the below is not a project stakeholder?
A) Project sponsor and project manager
B) Customer and suppliers of the project
C) Regulators, lobby groups, environmentalists and financial organizations associated with the project
D) Competitor companies
ANSWER: D
Which of the below is not a valid organizational structure type?
A) Organic or simple
B) Composite or hybrid
C) PMO
D) Criss-crossed
ANSWER: D
Which of the below is not an example of a virtual team?
A) Team members working in different shifts
B) Team members with mobility limitations
C) Employees working from home
D) Placing all or most active team members in the same location
ANSWER: D
Which of the below is not documented in the resource management plan?
A) An estimate of resources required for the project
B) How resources will identified, acquired, managed and controlled
C) How the project team will be trained, developed and recognized
D) Roles and responsibilities
ANSWER: A
Which of the below is not one of the three skills listed for a project manager as per PMI Talent Triangle┬«?
A) Leadership
B) Technology management
C) Technical project management
D) Strategic and business management
ANSWER: B
Which of the below is useful in prioritizing risks using a risk scoring scheme based on risk probabilities and impacts?
A) Probability and impact matrix
B) Probability and impact definitions
C) Risk register
D) Risk breakdown structure
ANSWER: A
Which of the below is/are correct about organizational project management?
A) Value is realized in operations
B) Value decisions are made by portfolios
C) Results are delivered by projects and programs
D) All of the above
ANSWER: D
Which of the below statement(s) is/are correct with respect to the Validate Scope process?
A) Accepted deliverables are inputs, verified deliverables are outputs
B) Deliverables are inputs, verified deliverables are outputs
C) Verified deliverables are inputs, accepted deliverables are outputs
D) Deliverables are inputs, accepted deliverables are outputs
ANSWER: A
Which of the below statements best describes rolling wave planning?
A) Near term work is planned in detail while work further in the future is planned at a higher level
B) Near term work is planned at a high level
C) Work which will happen late in future is planned in detail
D) All the work of the project is planned in detail irrespective of whether it will happen soon or much later
ANSWER: A
Which of the below statements is/are correct about the critical path?
A) It has the shortest path, meaning the total duration of activities in this path is the shortest among all paths
B) It has the longest path, meaning the total duration of activities in this path is the highest among all paths
C) The float for activities on this path will be always more than zero
D) None of the above
ANSWER: B
Which of the below techniques are not used when collecting requirements in a project?
A) Expert judgment, brainstorming, interviews, focus groups, questionnaires and surveys
B) Voting, autocratic decision making, multi-criteria decision analysis and nominal group technique
C) Affinity diagrams and mind mapping
D) Sensitivity analysis and simulation
ANSWER: D
Which of the below will not be documented in Communications Management Plan?
A) Process of maintaining this plan
B) Glossary of communications terms
C) Configuration management details
D) Details of communications which will happen in the project, including related information flow charts, constraints, resources, escalation process, senders, recipients, timeframes, frequencies, methods and technologies
ANSWER: C
Which of the following is a correct statement about portfolios?
A) A temporary activity which drives change in the organization
B) An ongoing operation which results in more profit
C) A group of programs managed together
D) One or more projects, programs and operations managed as a group to achieve strategic objectives
ANSWER: D
Which of the following leadership styles empowers followers, inspires them by giving meaning to their work and encourages innovation?
A) Charismatic leadership
B) Laissez-faire leadership
C) Transactional
D) Transformational leadership
ANSWER: D
Which of the following techniques helps to derive the most accurate estimate?
A) Analogous estimating
B) Parametric estimating
C) 3-point estimating (PERT technique)
D) Bottom-up estimating
ANSWER: D
Which of the following will not be described in the scope management plan?
A) Detailed project and product scope
B) How project scope (project scope statement, work breakdown structure) will be derived
C) How project scope will be managed and controlled
D) How project deliverables will be accepted
ANSWER: A
Which of these statement's is correct regarding a program?
A) A large number of projects grouped together
B) A number of projects of similar nature
C) A group of related projects managed together to obtain benefits not available from the individual projects
D) A complex project with several sub-projects
ANSWER: C
Which process group comes next after the initiating group?
A) Planning
B) Monitoring and controlling
C) Executing
D) Closing
ANSWER: A
Which process group does the Identify Stakeholders process belong to?
A) Planning
B) Executing
C) Initiating
D) Monitoring and controlling
ANSWER: C
Which process provides authority to the project manager to apply organizational resources for the project work?
A) Develop project management plan
B) Plan resource management
C) Develop project charter
D) Manage resources
ANSWER: C
Which risk response strategies are used only to respond to threats?
A) Avoid, mitigate
B) Exploit, enhance
C) Accept, escalate
D) Share, transfer
ANSWER: A
Which technique is common to the two processes Create WBS and Define Activities?
A) Alternatives analysis
B) Decomposition
C) Inspection
D) None of the above
ANSWER: B
Which technique may be used when monitoring stakeholder engagements in order to reduce misunderstandings and miscommunication?
A) Leadership
B) Active listening
C) Networking
D) Political awareness
ANSWER: B
Work performance information is an output of which process?
A) Plan communications management
B) Manage communications
C) Monitor communications
D) Monitor and control project work
ANSWER: C